## Slide 1: RAN5 5G NR DELIVERY phases and targets (Update of RAN5#79)
RAN5#79 meeting R5-183270
Busan, Korea, 21st-25th May 2018

## Slide 2: Introduction & CONTENT
The purpose of this document is to reflect the updated target dates and content of the RAN5 5GS delivery phases agreed at RAN5#79.
The document is used as base for setting the detailed targets in the work plans.
Content
RAN5 phase delivery targets
Content of NSA Option 3 (EN-DC) Phases
Content of SA Option 2 (SA NR) Phases
Content of SA Option 5 (SA E-UTRA) Phases
Common test environment

## Slide 3
RAN5 phases and targets
RAN5#79 May-18
  NSA Option 3 (EN-DC) Phase 1
RAN5#80 Aug-18
  NSA Option 3 (EN-DC) Phase 1.5 -- New (RF FR1)
RAN5#81 Nov-18
  NSA Option 3 (EN-DC) Phase 2
  SA Option 2 (SA NR) Phase 1
  SA Option 5 (SA E-UTRA) Phase 1**
RAN5#83 May-19
  NSA Option 3 (EN-DC) Phase 3
  SA Option 2 (SA NR) Phase 2
  SA Option 5 (SA E-UTRA) Phase 2**
  NSA Option 7 (NGEN-DC) Phase 1*
  NSA Option 4 (NE-DC) Phase 1*
  *ASN.1 late drop freeze March-1 **May be deferred 6 months if Option 5 will be moved from ASN.1 Freeze in Sept-18 to the late drop freeze March-19

## Slide 4: RAN5 phases and targets
Overview: Time line - RAN5 5G NR targets

## Slide 5
General considerations & Definitions
The RF, Demod/CSI reporting and RRM test cases can be divided into the following parts
  Test definition Test case description excluding MU (FR2) and TT (FR1 and FR2) part(s) i.e. non MU/TT parts of minimum requirements, Initial conditions, Test points, Test procedure, Specific message content etc.
  MU Measurement Uncertainty
  TT Test Tolerances
  Complete FR1 test case Test definition + MU + TT
  Complete FR2 test case Test definition + MU + TT
NOTE!
  The completion targets for EN-DC FR2 test cases are set based on the RAN5 MU/TT targets as described in R5-183257.
  Until the MU/TT becomes available it is important that the parts of test definition of the FR2 test cases that are NOT dependent on MU/TT are progressed as far as possible.
Content of RAN5 5GS PHASES

## Slide 6
INCLUDED:
  EN-DC configurations: LTE 1CC + NR FR1 1CC
  Protocol - TS 38.523-x
    54 NR Layer 2 test cases: 23 MAC, 17 RLC and 14 PDCP
    12 RRC test cases for single NR cell scenarios
    3 NAS EPC test cases (all)
  Test environment - TS 36.508, TS 38.508-1, TS 38.508-2
    Common test environment to enable LTE+NR FR1 MCG+SCG and Split bearer testing
  UE test functions - TS 38.509
    UE test loop mode A and UE test loop mode B.
NOT INCLUDED:
  No RF FR1 test cases (TS 38.521-1, TS 38.521-3) due to pending completion of outstanding details in core specifications (TS 38.101-1 and TS 38.101-3).
  No RF FR2, Demod/CSI reporting or RRM test cases (TS 38.521-2, TS 38.521-3, TS 38.533).
  Protocol test cases for EN-DC NR multi-cell scenarios, EN-DC NR CA, dedicated BWPs, SRB3, measurement gaps and CSI-RS, and SS\PBCH based measurements
Note 1: The TS 38.521-3 referenced clauses in TS 38.521-1 and TS 38.521-2 need to be completed as part of the TS 38.521-3 target.
Note 2: Dependency: RAN4 progress until RAN4#87 (May-18)
Note 3: TT needs one more meeting cycle
NSA Option 3 (EN-DC) Phase 1 content
- Target RAN5#79 MAY-18
Completed @ RAN5#79

## Slide 7
New intermediate phase added to add RF test cases originally planned for NSA Option 3 Phase 1, but deferred due to pending completion of a outstanding details in core specifications (TS 38.101-1 and TS 38.101-3).
INCLUDED:
  EN-DC configurations: LTE 1CC + NR FR1 1CC
  RF - TS 38.521-3, TS 38.522, TS 38.521-1 (Note 1), TR 38.903, TR 38.905
    Test definition, MU for all LTE+NR FR1 Rx and Tx test cases, Note 2, Note 3
    Progress on Test definition for all LTE+NR FR2 Rx and Tx test cases, Note 2
Note 1: The TS 38.521-3 referenced clauses in TS 38.521-1 and TS 38.521-2 need to be completed as part of the TS 38.521-3 target.
Note 2: Dependency: RAN4 progress until RAN4#88 (Aug-18)
Note 3: TT needs one more meeting cycle
NSA Option 3 (EN-DC) Phase 1.5 content
Target RAN5#80 Aug-18

## Slide 8
INCLUDED:
  EN-DC configurations: LTE xCC + NR FR1 1CC, where x<=3; and LTE 1CC + NR FR2 1CC
  RF - TS 38.521-3, TS 38.522, TS 38.521-1 (Note 1), TS 38.521-2 (Note 1), TR 38.903, TR 38.905
    Test definition, MU and TT for LTE+NR FR1: Rx and Tx test cases not completed in NSA Opt.3 Phase 1, Note 2
    Test definition, MU and TT for LTE+NR FR2 RF MU/TT Target 1 and Target 2 test cases, Note 3
  Protocol - TS 38.523-x, TS 34.229-x, TS 37.571-x
    Enhanced Layer 2 test coverage
    Enhanced RRC test coverage for NR multi-cell test scenarios, dedicated BWP, SRB3, measurement gaps and CSI-RS, SS\PBCH based measurements
    LTE 1CC + NR FR1 1CC and LTE 1CC + NR FR2 1CC test cases
    Enhanced test coverage for L1 configurations based on industry interest
    Positioning EN-DC test cases
  Test environment - TS 36.508, TS 38.508-1, TS 38.508-2
    Common test environment to enable FR2 testing (RF and protocol)
  UE test functions - TS 38.509
    UBF, SS-RSRPB UE reporting, UE Positioning test functions
NOT INCLUDED:
  RF MU/TT for RF MU/TT Target 3 test cases (TS 38.521-3)
  No LTE + NR FR1 or FR2 Demod/CSI reporting (TS 38.521-4) and No NR FR1 or FR2 RRM (TS 38.533)
  No IMS test cases (TS 34.229-x)
Note 1: The TS 38.521-3 referenced clauses in TS 38.521-1 and TS 38.521-2 need to be completed as part of the TS 38.521-3 target.
Note 2: Dependency: RAN4 progress until RAN4#89 (Nov-18)
Note 3: Dependency: RAN4 progress until RAN4#89 (Nov-18) + RAN5 RF MU/TT progress. For RF MU/TT target 1 and target 2 test cases MU is planned to be completed by RAN5#NR3 (Oct-18) and TT is targeted to be completed by RAN5#81 (Nov-18) (Ref R5-183257)
NSA Option 3 (EN-DC) Phase 2 content
- Target RAN5#81 NOV-18

## Slide 9
NSA Option 3 (EN-DC) Phase 3 content
- Target RAN5#83 MAY-19
INCLUDED:
  EN-DC configurations: LTE xCC + NR FR1/FR2 1CC, where x < 4
  RF - TS 38.521-3, TS 38.522, TS 38.521-1 (Note 1), TS 38.521-2 (Note 1), TS 38.521-4, TS 38.533, TR 38.903, TR 38.905
    TT part for RF MU/TT Target 3 test cases (TS 38-521-3), Note 3
    Test definition and TT for LTE+NR FR1 Demod/CSI reporting (TS 38.521-4) and RRM (TS 38.533), Note 2
    Test definition for LTE+NR FR2 Demod/CSI reporting (TS 38.521-4) and LTE+NR FR2 RRM (TS 38.533), Note 2
  Protocol - TS 38.523-x, TS 34.229-x, TS 37.571-x
    Remaining test cases not completed in NSA Opt.3 Phase 2
    LTE 1CC + NR FR1/FR2 2CC test cases, Note 5
    IMS IR.92 EN-DC test cases
    Test coverage enhancement for L1 configurations.
  Test environment - TS 36.508, TS 38.508-1, TS 38.508-2
    Common test environment to enable LTE xCC + NR FR1 1CC / LTE xCC + NR FR2 1CC test cases
  UE test functions - TS 38.509
    TBD if any additional UE test functions needed
NOT INCLUDED:
  MU/TT part of LTE+NR FR2 Demod/CSI reporting (TS 38.521-4), Note 4
  MU/TT part of LTE+NR FR2 RRM (TS 38.533), Note 4
Note 1: The TS 38.521-3 referenced clauses in TS 38.521-1 and TS 38.521-2 need to be completed as part of the TS 38.521-3 target.
Note 2: Dependency: RAN4 progress until RAN4#89 (May-19)
Note 3: MU part of RF MU/TT target 3 test cases are planned to be completed by RAN5#83 (May 19) and TT part by RAN5#84 (Aug-19). The TT part need thus to be completed after NSA Opt.3 Phase 3. Note 4: There will be a need for a NSA Opt.3 Phase 4 to be added when MU/TT targets for Demod/CSI and RRM test cases becomes available.
Note 5: For protocol test cases it is assumed that EN-DC configurations beyond LTE 1CC + NR FR1/FR2 2CC are implicitly tested by the RF test cases.

## Slide 10
INCLUDED:
  SC FR1 and FR2
  RF - TS 38.521-1, TS 38.521-2, TR 38.903, TR 38.905
    Test definition, MU and TT for all NR FR1 Rx and Tx test cases, Note 1
    Test definition, MU and TT for NR FR2 RF MU/TT Target 1 and Target 2 test cases, Note 2
  Protocol - TS 38.523-x
    Basic NR SA Layer 2, Idle Mode, SDAP and RRC test cases, Note 3
    Basic NAS 5GC test cases, Note 3
  Test environment - TS 38.508-1, TS 38.508-2
    Common test environment to enable NR FR1 and FR2 testing
  UE test functions - TS 38.509
    UE test loop mode A and UE test loop mode B for SA NR
    UBF, SS-RSRPB UE reporting, UE Positioning test functions
NOT INCLUDED:
  RF MU/TT for RF MU/TT Target 3 test cases (TS 38.521-3)
  No NR FR1 or FR2 Demod/CSI reporting (TS 38.521-4)
  No NR FR1 or FR2 RRM (TS 38.533)
Note 1: Dependency: RAN4 progress until RAN4#89 (Nov-18)
Note 2: Dependency: RAN4 progress until RAN4#89 (Nov-18) + RAN5 RF MU/TT progress. For RF MU/TT target 1 and 2 test cases MU is planned to be completed by RAN5#NR3 (Oct-18) and TT is targeted to be completed by RAN5#81 (Nov-18) (Ref R5-183257)
Note 3: Dependency: RAN2/CT1 progress until RAN5#104 & CT1#113 (Nov-18)
SA Option 2 (SA NR) Phase 1 content
- Target RAN5#81 Nov-18

## Slide 11
SA Option 2 (SA NR) Phase 2 content
- Target RAN5#83 MAY-19
INCLUDED:
  SC FR1 and FR2 + CA configurations FR1 xCC,FR2 xCC, (FR1+FR2) xCC:, where x<=4
  RF - TS 38.521-1, TS 38.521-2, TS 38.521-3 (FR1+FR2), TS 38.521-4, TS 38.533, TR 38.903, TR 38.905
    Test definition and MU/TT for NR FR2 Rx and Tx RF MU/TT target 3 test cases where MU/TT analysis completed, Note 2
    Test definition and MU/TT for NR FR1 Demod/CSI reporting (TS 38.521-4), Note 1
    Test definition and MU/TT for NR FR1 RRM (TS 38.533) test definition and TT, Note 1
    Test definition for NR FR2 Demod/CSI reporting (TS 38.521-4), Note 1
    Test definition for NR FR2 RRM (TS 38.533), Note 1
  Protocol - TS 38.523-x, TS 34.229-x, TS 37.571-x
    Enhanced test coverage for NR SA idle mode, SDAP and RRC test cases, Note 3
    SA NR positioning test cases
    5GS IMS, Note 4
  Test environment - TS 38.508-1, TS 38.508-2
    Common test environment to enable to enable NR FR1/FR2/FR1+FR2 CA configurations
  UE test functions - TS 38.509
    TBD if any additional UE test functions needed
NOT INCLUDED:
  MU/TT part of NR FR2 Demod/CSI reporting (TS 38.521-4), Note 2
  MU/TT part of NR FR2 RRM (TS 38.533), Note 2
Note 1: Dependency: RAN4 progress until RAN4#91 (May-19)
Note 2: Dependency: RAN4 progress until RAN4#91 (May-19) + RAN5 RF MU/TT progress. For RF MU/TT target 3 test cases MU is planned to be completed by RAN5#81 (Dec-18) and TT is targeted to be completed by RAN5#NR4 (Jan-19) (Ref R5-183257)
Note 3: There will be a need for a SA Opt.2 Phase 3 to be added when MU/TT targets for Demod/CSI and RRM test cases becomes available.
Note 4: Dependency: RAN2/CT1 progress until RAN2#106 & CT1#115 (May-19)

## Slide 12
INCLUDED:
  Protocol - TS 38.523-x
    Adoption legacy E-UTRA test cases for 5GC
    RRC connected to 5GC test cases, Note 1
    Basic NAS 5GC test cases, Note 1
  Test environment - TS 36.508, TS 38.508-1, TS 38.508-2
    Common test environment to enable SA Option 5 Phase 1 test cases
  UE test functions - TS 38.509
    UE test loop mode A and UE test loop mode B for SA E-UTRA
Note 1: Dependency: RAN2/CT1 progress until RAN5#104 & CT1#113 (Nov-18)
SA Option 5 (SA E-UTRA) Phase 1 content
- Target RAN5#81 Nov-18

## Slide 13
SA Option 5 (SA E-UTRA) Phase 2 content
- Target RAN5#83 MAY-19
INCLUDED:
  Protocol - TS 38.523-x, TS 34.229-x, TS 37.571-x
    Enhanced test coverage for SA Opt.5, Note 1
  Test environment - TS 36.508, TS 38.508-1, TS 38.508-2
    Common test environment to enable SA Option 5 Phase 2 test cases
  UE test functions - TS 38.509
    TBD if any additional UE test functions needed
Note 1: Dependency: RAN2/CT1 progress until RAN5#106 & CT1#115 (May-19)

## Slide 14: REFERENCE slides
The following RAN Plenary and RAN5 planning documents have been taken into account when defining the RAN5 5G NR delivery phases and targets:
RAN#79 (Mar-18) update of 5G NR Rel-15 schedule
RAN5#2-5G-NR-Adhoc (April-18) initial MU/TT targets
RAN5#79 (May-18) updated MU/TT targets

## Slide 15
RAN#79 plenary updateD 5G NR SCHEDULE (Ref:RP-180554)
Rel-15 schedule unchanged
  Architecture Option 3: ASN.1 Freeze March 2018
  Architecture Option 2: ASN.1 Freeze September 2018
  Architecture Option 5: ASN.1 Freeze September 2018 (only impacts LTE ASN.1)
Introduce Late Rel-15 Drop
  Follows Rel-15 completion by 6 months
  The late drop is to exclusively contain NR architecture options that were not completed by September ASN.1 drop
  Options 4, 7 are part of the late drop
  In case Option 5 is not completed by September ASN.1 drop, it will be part of the late drop
  NR-NR DC to be considered to be added to the late drop at RAN#80
  Band combinations which are not completed by June 2018 (other than NR-NR DC combinations) will be moved to Rel-16 band specifications, but continue to be release independent.

## Slide 16: Time line (Ref:RP-180554)

## Slide 17
RAN5#2-5G-NR-Adhoc FR2 MU/TT timeplan
At RAN5#2-5G-NR-ADHOC (APRIL-18) RAN5 endorsed the following initial MU/TT targets (Ref:R5-182092)
  RF MU/TT Target 1: [MU] RAN5#NR3 (Oct-18) [TT] RAN5#NR4 (Jan-19)
  RF MU/TT Target 2: [MU] RAN5#82 (Oct-19) [TT] RAN5#83 (May-19)
  RF MU/TT Target 3: [MU] RAN5#83 (May-19) [TT] RAN5#84 (Aug-19)
RF MU/TT Target 1 test cases (regulatory):
  6.2.1 Max Output Power 7.3 Ref Sensitivity
RF MU/TT Target 2 test cases (regulatory):
  6.3.2 Transmit OFF power 6.4.1 Frequency Error
  6.5.1 Occupied bandwidth 6.5.2.1 Spectrum emission mask
  6.5.2.2 Adjacent Channel Leakage Ratio 6.5.3.1 General spurious emissions
  6.5.3.2 Spurious emissions for UE co-existence 7.7 Receiver Spurious emissions
RF MU/TT Target 3 test cases: all other test cases

## Slide 18
RAN5#79 UPDATED FR2 MU/TT timeplan
At RAN5#79 RAN5 endorsed the following updated MU/TT targets as Best Effort (Ref:R5-183257)
  RF MU/TT Target 1: [MU] RAN5#NR3 (Oct-18) [TT] RAN5#81 (Nov-18,-2m)
  RF MU/TT Target 2: [MU] RAN5#NR3 (Oct-18,-4m) [TT] RAN5#81 (Nov-18, -6m)
  RF MU/TT Target 3: [MU] RAN5#81 (Nov-18, -6m) [TT] RAN5#84 (Jan-19, -7m)
  , where “-xm“ indicates a move of a target by x months compared to previous targets in R5-182092
RF MU/TT Target 1 test cases (regulatory):
  6.2.1 Max Output Power 7.3 Ref Sensitivity
RF MU/TT Target 2 test cases (regulatory):
  6.3.2 Transmit OFF power 6.4.1 Frequency Error
  6.5.1 Occupied bandwidth 6.5.2.1 Spectrum emission mask
  6.5.2.2 Adjacent Channel Leakage Ratio 6.5.3.1 General spurious emissions
  6.5.3.2 Spurious emissions for UE co-existence 7.7 Receiver Spurious emissions
RF MU/TT Target 3 test cases: all other test cases