## Slide 1: RAN5 5G NR STATUS, DELIVERY phases and targets (AUG-19)
3GPP TSG-RAN5#84 R5-196274
Ljubljana, Slovenia, 26 – 30 August, 2019

## Slide 2: Introduction & CONTENT
The purpose of this document is to give high level status of RAN5 completed 5GS test cases and the targets for the next RAN5 5GS delivery phases.
Content
Definitions of RAN5 5GS delivery phases and target dates
FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) targets
Progress - Completed deliveries
Planning content for next deliveries
  NSA Option 3 (EN-DC)
  SA Option 2 (SA NR)
  SA Option 5, NSA Option 4 (NE-DC), NSA Option 7 (NGEN-DC)

## Slide 3: MNO poll options 4, 5 and 7 and on NR-DC
RAN5 have received feedback from Mobile Network Operators on conformance testing needs for 5GS Network Deployment Options 4, 5 and 7 and for NR-DC. The response is summarized in Table 2-1 (Ref: R5-196969).

## Slide 4: Definitions of RAN5 5GS delivery phases and target dates
Overview: Time line - RAN5 5G NR deliveries versus RAN5 meeting
  NSA Option 3 Phase 5 and SA Option 2 Phase 4 was completed at RAN5#84
  Based on the feedback on the anonymous MNO poll on deployment plans options 4, 5 and 7 and on NR-DC RAN5 have updated its plan:
    Start of option 4, 5 and 7 at RAN5#87 (Work plans RAN5#86)
    NR-DC completion for SA Option 2 planned at RAN5#88

## Slide 5: DETAILS Option 4, 5, 7 PLAN
Task | Target
Re-confirming MNO earliest date for conformance test cases to support deployments | Jan-20 (send out request by Dec-19)
Complete impacted work plans for options 4, 5 and 7 | RAN5#86 (Feb-20)
Intermediate delivery of test cases and common test environment for option 4,5 and 7 | RAN5#87 (May-20) & RAN5#88 (Aug-20)
Complete option 4, 5 and 7 conformance tests | RAN5#89 (Nov-20)
It is recommended to request a re-confirmation from MNOs before the RAN5 start the work considering the high impact (especially for signaling/TTCN aspects).

## Slide 6: DETAIL NR-DC PLAN
Task | Target
Complete impacted RF/SIG work plans for synchronous NR-DC including assignment of WP TCs/Tasks | RAN5#85 (Nov-19)
Complete RRM work plan for synchronous NR-DC including assignment of WP TCs/Tasks | RAN5#86 (Feb-20)
Complete synchronous NR-DC FR1-FR2 RF/SIG test cases | RAN5#87 (May-20)
Complete synchronous NR-DC FR1-FR2 RRM test cases | RAN5#88 (Aug-20)
MNO: Mid-20, FR1-FR1 & FR1-FR2
RAN4 completion target for NR-DC RRM (TS 38.133) for NR-DC is Feb-20 (core is completed)
Out of scope of RAN5 5G/NR WI:
  NR-DC Demodulation and CSI reporting (introduced in RAN4 under a separate Rel-16 WI (NR_perf_enh)
  FR1-FR1 (no NR-DC FR1-FR1 configurations included in TS 38.101-1)
 RAN5 5G/NR WI scope: Synchronous NR-DC for FR1-FR2,

## Slide 7
FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) Target Completion Update
RF MU/TT Priority 1 test cases (regulatory):
  Max Output Power (complete for EIRP/TRP)
  Ref Sensitivity (complete)
RF MU/TT Priority 2 test cases (regulatory):
  Transmit OFF power
  Occupied bandwidth
  Adjacent Channel Leakage Ratio
  Spurious emissions for UE co-existence
  Spectrum emission mask (complete)
  General spurious emissions
  Receiver Spurious emissions (not testable at this time)
RF MU/TT Priority 3 test cases: all other test cases
  The RAN5 targets for completing FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) (Updated at RAN5-84)

## Slide 8: Progress - Completed deliveries
SA Option 2 Phase 4 and NSA Option 3 Phase 5 were completed at RAN5#84
  For additional details of progress for different areas see R5-196272
Completed test cases:
  For details see attached document “5GS WP complete test cases v7.1” for details
  The reason for the decrease in numbers of protocol test cases is due test case optimization (removal of some test cases where the test purpose(s) are covered by another test case)

## Slide 9
General considerations & Definitions
The RF, Demod/CSI reporting and RRM test cases can be divided into the following parts
  Test definition Test case description excluding MU (FR2) and TT (FR1 and FR2) part(s) i.e. non MU/TT parts of minimum requirements, Initial conditions, Test points, Test procedure, Specific message content etc.
  MU Measurement Uncertainty
  TT Test Tolerances
  Complete FR1 test case Test definition + MU + TT
  Complete FR2 test case Test definition + MU + TT
NOTE!
  The completion targets for EN-DC FR2 RF test cases are set based on the RAN5 MU/TT targets as described on slide 7.
  Until the MU/TT becomes available it is important that the parts of test definition of the FR2 test cases that are NOT dependent on MU/TT are progressed as far as possible.
Planning CONTENT for next deliveries

## Slide 10
Planning for next deliveries:
NSA Option 3 (EN-DC) - Phase 6 content - Target RAN5#85 NOV-19
EN-DC configurations: LTE xCC + NR FR1/FR2 yCC, where x <= 4, y <=2
Test case completion targets
  Not completed RF EN-DC test cases (38.521-3), Note 1
  Demodulation and CSI reporting (38.521-4):
    Not completed LTE+NR FR1 test cases
    LTE+NR FR2 test cases where MU/TT are completed by Nov-19
  RRM (38.533):
    Not completed LTE+NR FR1 test cases
    FR2 test cases where RAN4 requirements and MU/TT completed by Nov-19
  Protocol
    Not completed protocol test cases
    CA FR1 & FR2 Band Combinations (CA with Intra-band Contiguous and Non- Contiguous)
    IMS IR.92 EN-DC test cases, Note 2
Other targets
  MU/TT for LTE+NR FR2 Demod/CSI reporting (TS 38.521-4) and RRM (TS 38.533)
  Common test environment (TS 38.508-1)
    Common procedure to establish LTE xCC + NR FR1/FR2 yCC test cases, where x <= 4, y <=2
    NR Intra-band Contiguous and Non- Contiguous CA test frequencies for protocol testing
Note 1: See slide 4 for MU/TT targets and definition of RF FR2 priority 1, 2 and 3 test cases.
Note 2: The need for EN-DC IMS test cases on top of the existing E-UTRA IMS test cases depends on if GSMA adds any additional EN-DC specific requirements in IR.92 v13.0 and/or IR.94 v14.0 for EN-DC.

## Slide 11
SC FR1+ SC FR2 + CA configurations for FR1 xCC,FR2 xCC, (FR1+FR2) xCC:, where x<=4 for FR1 and x<=8 for FR2
Test case completion targets
  RF FR1 (38.521-1):
    Not completed RF FR1 test cases for SC, UL-MIMO and CA
    RF FR1 test cases for SUL
  RF FR2 (38.521-2):
    Not completed RF FR2 priority 1 and 2 SC test cases including MU/TT for EIRP Spherical, Transmit OFF power, OBW, ACLR, General Spurious, Spurious co-existence and Rx Spurious.
    RF FR2 priority 3 SC test cases including MU/TT (TS 38.521-3), see Note 2
  RF FR1+FR2 (38.521-3):
    Not completed FR1+FR2 test cases
  Demod/CSI reporting (38.521-4), see Note 1:
    Not completed priority 1 and 2 test cases
  RRM (38.533): Note 1
    Not completed FR1 priority 1 test cases + FR1 priority 2 test cases
    FR2 test cases where RAN4 requirements and MU/TT completed by Nov-19
  Protocol test cases (38.523-1, 37.571-2):
    Not completed protocol test cases for Idle mode, Layer 2, RRC, Multilayer (Emergency services, UAC, EPS Fallback)
    NR CA FR1&FR2 intra-band contiguous and non-contiguous
    Complete FR2 power levels for multi-cell test cases
  Other targets
    Complete impacted RF/SIG work plans for synchronous NR-DC including assignment of WP TCs/Tasks
    Definition of FR2 power levels for Serving Cell, Suitable Intra-frequency Neighbour Cell, Suitable Intra-frequency Neighbour Cell and Non-Serving Cell required for Idle mode and NAS test cases.
    Standalone FR2 with E-UTRA needs to be specified.
    Generic procedures for Emergency calls set up and release in regard to establishment/release of DRBs
    Generic procedures for IMS over 5GS
    NR CA test frequencies for protocol testing and for intra-band contiguous and non-contiguous CA
Note 1: RF/Demod/RRM FR1 priority 1 test cases are test cases with only RAN5 dependencies, i.e. completed in RAN4 by March-19. RF/Demod/RRM FR1 priority 2 test cases are test cases not completed in RAN4 by March-19 (RF/Demod/RRM priorities as agreed at RAN5#82, ref: R5-192832).
Note 2: See slide 4 for MU/TT targets and definition of RF FR2 priority 1, 2 and 3 test cases.
Planned content:
SA Option 2 (SA NR) - Phase 5 - Target RAN5#85 NOV-19

## Slide 12
See slide 5 for further details
Planned content:
SA Option 5 (SA E-UTRA) - Phase 1 - Target RAN5#87 (May-20)

## Slide 13
See slide 5 for further details
Planned content:
NSA Option 4 & 7 (NE-DC & NGEN-DC) - Phase 1 - Target RAN5#87 (May-20)