## Cover sheet
3GPP TSG-RAN WG5 Meeting #90-e | [10 empty] | R5-210763
Electronic Meeting, 22nd February - 5th March 2021
Agenda Item: | 7.4.2
Source: | Huawei, Samsung
Title: | WP UE Conformance Test Aspects for Enhancements on MIMO for NR
Work item code: | NR_eMIMO-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of the UE Conformance Test Aspects for Enhancements on MIMO for NR work item is to define the UE conformance requirements corresponding to WID on enhancement on MIMO for NR, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-16. At the RAN#88 meeting in June 2020 the Rel-16 RAN5 work item for UE Conformance Test Aspects for Enhancements on MIMO for NR was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 16% (+4%) | 0 | 63 (+20)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 18.3% (+5.5%) | 0 | 47 (+10)
FR1 |  | 23.7% (+8.4%) | 0 | 39 (+5)
FR2 |  | 7% (-0%) | 0 | 10 (+5)
NSA Option 3 (EN-DC) |  | 5% | 0 | 16 (+10)
FR1 |  | 5% | 0 | 8 (+5)
FR1 + FR2 |  | 5% | 0 | 8 (+5)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FR1 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 2.8% (-0.2%) |  |  | 5% |  |  | 0% |  |  |  | 0% |  |  | 0%
Common ICS | 38.508-2 | 5% |  |  | 5% |  |  | 5%
NR RF/RRM
FR1 RF common parts | 38.521-1 | 8.3% (+0%) |  |  | 8.3%
FR1 RF Tx test cases | 38.521-1 Tx | 62.3% (+33%) | 0 | 9 | 62.3% (+33%) | 0 | 9
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2 | 0% | [5 empty] | 0%
FR2 RF Tx test cases | 38.521-2 Tx | 0% | [5 empty] | 0%
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4 | 0% | 0 | 20 | 0% | 0 | 20
RRM test cases | 38.533 | 0% | 0 | 32 (+20) | 0% | 0 | 8 (+5) | 0% | 0 | 8 (+5) |  | 0% | 0 | 8 (+5) | 0% | 0 | 8 (+5)
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 39.9% (+39.9%) |  |  | 60% (+60%) |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 31.7% (+1.7%) | 0 | 2 | 30% | 0 | 2 | 35% (+5%) | 0 | 2
Applicability Protocol test cases | 38.523-2 | 50% |  |  | 50% |  |  | 50%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-200895 | New WID on UE Conformance Test Aspects for Enhancements on MIMO for NR; Huawei, Samsung
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects for Enhancements on MIMO for NR | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_eMIMO-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for Enhancements on MIMO for NR comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [13 empty] | vs Area
WP Resp: |  | Chunying Gu, Huawei |  |  | guchunying@huawei.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 | FR1 + FR2
[15 empty] | 23.7% (+8.4%) | 7% (-0%) | 5% | 5%
[15 empty] | 99 (+9) | 50 (+8) | 23 (+8) | 23 (+8)
[15 empty] | 79.7 (+5.4) | 38.7 (+5.3) | 13.7 (+5.3) | 13.7 (+5.3)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
5GS - RAN and CN
5GS Common
TS 38.508-1: Common test environment
117 |  | 38.508-1 | 4.3 | Reference test conditions | Adding necessary test conditions for eMIMO features |  | TBD | R5-205932 |  | 1 | 2.5% | 5% | 0% |  | 10% | 0% | 0% | 0%
118 |  | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | New message and IE definition for eMIMO features |  | TBD |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
119 |  | 38.508-1 | 5 | Test environments for RF test | Necessary changes to RF test environments |  | TBD | R5-205932 |  | 1 | 2.5% | 5% | 0% |  | 10% | 0% | 0% | 0%
120 |  | 38.508-1 | 7 | Test environments for RRM tests | Necessary changes to RRM test environments |  | TBD |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
TS 38.508-2: Common ICS
1 |  | 38.508-2 | A.4 | ICS proforma tables | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | RAN5#93 (Nov-21) | R5-206414 |  | 0.2 | 5% | 5% |  |  | 5% | 5%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
2 |  | 38.521-1 | 2 | Reference | Define References made in TS |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
3 |  | 38.521-1 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively | Ericsson | RAN5#89-e (Nov-20) | R5-205557 |  | 0.1 | 100% | 100% |  |  | 100%
4 |  | 38.521-1 | 4 | General | define categories of test requirements |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
5 |  | 38.521-1 | 5 | Operating bands and Channel arrangement | define the frequency bands and channel arragement |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
6 |  | 38.521-1 | Annex A | measurement channels | define mesurement channels |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
7 |  | 38.521-1 | Annex B | Propagation conditions | Define propagation conditions |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
8 |  | 38.521-1 | Annex C | Downlink physical channels | Define downlink physical channels |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
9 |  | 38.521-1 | Annex D | Characteristics of the interfering signal | Define characteristics of the interfering signal |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
10 |  | 38.521-1 | Annex E | Global In-Channel TX-Test | Specifiy the measurement of all relevant parameters that describe the in-channel quality of the output signal of the TX under test in a single measurement process |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
11 |  | 38.521-1 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
12 |  | 38.521-1 | Annex G | Uplink Physical Channels | Define uplink physical channels |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
13 |  | 38.521-1 | Annex H | Statistical Testing |  |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
TS 38.521-1: FR1 RF test cases - Tx
14 |  |  | 6.2.2 | UE maximum output power reduction | Adding minimum requirement and additional test point for R16 DMRS | Huawei | RAN5#90-e (Feb-21) | R5-205791 R5-210782 | Ref: 38.101-1 6.2.2 Pending on RAN2/RAN4 capability alignment 38.522: No changes needed 38.905: R5-206857 | 1 | 90% | 90% |  |  | 90%
15 |  | 38.521-1 Tx | 6.2.3 | UE additional maximum output power reduction | Adding minimum requirement; Analysing whether additional test point for R16 DMRS is needed Minimum requirment for R16 DMRS is the same as for R15 DMRS. Given the UE can pass the requirements using R15 DMRS, it can be expected that UE can psss the requirements using R16 DMRS. Therefore there is no need to additionally test the R16 DMRS. | Huawei | RAN5#90-e (Feb-21) | R5-210782 | Ref: 38.101-1 6.2.3 38.522: No changes needed 38.905: R5-211809 | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
16 |  | 38.521-1 Tx | 6.4.2.5 | EVM equalizer spectrum flatness for Pi/2 BPSK | Adding minimum requirement and additional test point for R16 DMRS | Huawei | RAN5#90-e (Feb-21) | R5-211807 | Ref: 38.101-1 6.4.2.4.1 Pending on RAN2/RAN4 capability alignment 38.522: No Changes needed 38.905: R5-211810 | 1 | 90% (+90%) | 90% (+90%) |  |  | 90%
17 |  | 38.521-1 Tx | 6.5.2.2 | Spectrum Emission Mask | Adding additional test point for R16 DMRS as per MPR | Huawei | RAN5#90-e (Feb-21) | R5-206766 | Ref: 38.101-1 6.5.2.2 Pending on RAN2/RAN4 capability alignment 38.522: No changes needed 38.905: R5-206857 | 1 | 90% | 90% |  |  | 90%
18 |  | 38.521-1 Tx | 6.5.2.4.1 | NR ACLR | Adding additional test point for R16 DMRS as per MPR | Huawei | RAN5#90-e (Feb-21) | R5-206767 | Ref: 38.101-1 6.5.2.4.1 Pending on RAN2/RAN4 capability alignment 38.522: No changes needed 38.905: R5-206857 | 1 | 90% | 90% |  |  | 90%
19 |  | 38.521-1 Tx | 6.2C.4 | UE maximum output power reduction for SUL | Adding additional test point for R16 DMRS | Huawei | RAN5#90-e (Feb-21) | R5-211915 | Ref: 38.101-1 6.2C, 6.2.2 Pending on RAN2/RAN4 capability alignment 38.522: No changes needed 38.905: R5-211811 | 1 | 90% (+90%) | 90% (+90%) |  |  | 90%
20 |  | 38.521-1 Tx | 6.2C.5 | UE additional maximum output power reduction for SUL | Adding minimum requirement; Analysing whether additional test point for R16 DMRS is needed |  | RAN5#90-e (Feb-21) |  | Ref: 38.101-1 6.2C, 6.2.3 38.522: 38.905: | 1 | 0% | 0% |  |  | 0%
21 | Y | 38.521-1 Tx | 6.4C.2.5 | EVM equalizer spectrum flatness for Pi/2 BPSK for SUL | Adding test point for R16 DMRS |  | RAN5#90-e (Feb-21) | R5-211808 | Ref: 38.101-1 6.4.2.5 Pending on RAN2/RAN4 capability alignment 38.522: R5-210792 38.905: R5-210791 | 1 | 90% (+90%) | 90% (+90%) |  |  | 90%
22 |  | 38.521-1 Tx | 6.5C.2.2 | Spectrum Emission Mask for SUL | Adding additional test point for R16 DMRS as per MPR | Huawei | RAN5#90-e (Feb-21) | R5-210787 | Ref: 38.101-1 6.5.2.2 Pending on RAN2/RAN4 capability alignment 38.522: No changes needed 38.905: R5-211811 | 1 | 90% (+90%) | 90% (+90%) |  |  | 90%
23 |  | 38.521-1 Tx | 6.5C.2.4.1 | NR ACLR for SUL | Adding additional test point for R16 DMRS as per MPR | Huawei | RAN5#90-e (Feb-21) | R5-210788 | Ref: 38.101-1 6.5.2.4.1 Pending on RAN2/RAN4 capability alignment 38.522: No changes needed 38.905: R5-211811 | 1 | 90% (+90%) | 90% (+90%) |  |  | 90%
24 |  | 38.521-1 Tx | 6.2D.1 | UE maximum output power for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#90-e (Feb-21) | R5-205796 | Ref: 38.101-1 6.2D.1 38.522: No changes needed 38.905: R5-206858 | 1 | 100% | 100% |  |  | 100%
25 |  | 38.521-1 Tx | 6.2D.2 | UE maximum output power reduction for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Ericsson | RAN5#90-e (Feb-21) | R5-211133 | Ref: 38.101-1 6.2D.2 FFS:Test requirements are missing; Setting of TPMI index for ‘Mode-full power’ is TBD 38.522: No changes needed 38.905: R5-211134 | 1 | 80% (+80%) | 80% (+80%) |  |  | 80%
26 |  | 38.521-1 Tx | 6.2D.3 | UE additional maximum output power reduction for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power |  | RAN5#90-e (Feb-21) |  | Ref: 38.101-1 6.2D.3 38.522: 38.905: | 1 | 0% | 0% |  |  | 0%
27 |  | 38.521-1 Tx | 6.2D.4 | Configured transmitted power for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Ericsson | RAN5#90-e (Feb-21) |  | Ref: 38.101-1 6.2D.4 38.522: 38.905: | 1 | 0% | 0% |  |  | 0%
28 | Y | 38.521-1 Tx | 6.5D.1_1 | Occupied bandwidth for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. | Ericsson | RAN5#90-e (Feb-21) | R5-206894 | Ref: 38.101-1 6.5D.1 Test applicability is TBD Test point analysis is TBD 38.522: 38.905: | 1 | 70% | 70% |  |  | 70%
29 |  | 38.521-1 Tx | 6.5D.2_1 | Out of band emission for UL MIMO (Rel-16 onward) | New Sub-title |  | RAN5#90-e (Feb-21) |  | Sub-title | 0
30 |  | 38.521-1 Tx | 6.5D.2_1.1 | General | Measurement is changed to sum of both antenna connectors: Updating minimum requirement |  | RAN5#90-e (Feb-21) |  | Ref: 38.101-1 6.5D.2 | 0.1 | 0% | 0% |  |  | 0%
31 | Y | 38.521-1 Tx | 6.5D.2_1.2 | Spectrum Emission Mask for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power |  | RAN5#90-e (Feb-21) |  | Ref: 38.101-1 6.5D.2 38.522: 38.905: | 1 | 0% | 0% |  |  | 0%
32 | Y | 38.521-1 Tx | 6.5D.2_1.3 | Additional spectrum emission mask for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power |  | RAN5#90-e (Feb-21) |  | Ref: 38.101-1 6.5D.2 38.522: 38.905: | 1 | 0% | 0% |  |  | 0%
33 | Y | 38.521-1 Tx | 6.5D.2_1.4.1 | NR ACLR for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Ericsson | RAN5#90-e (Feb-21) |  | Ref: 38.101-1 6.5D.2 38.522: 38.905: | 1 | 0% | 0% |  |  | 0%
34 | Y | 38.521-1 Tx | 6.5D.2_1.4.2 | UTRA ACLR for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Ericsson | RAN5#90-e (Feb-21) | R5-210996 | Ref: 38.101-1 6.5D.2 FFS: Applicability of test points with UL-MIMO wi and w/o ULFPTx; Refered test case 6.2D.3 is not complete. 38.522: TBD 38.905: R5-211018 | 1 | 70% (+70%) | 70% (+70%) |  |  | 70%
35 |  | 38.521-1 Tx | 6.5D.3_1 | Spurious emissions for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement |  | RAN5#90-e (Feb-21) |  | Ref: 38.101-1 6.5D.3 38.522: 38.905: | 0.1 | 0% | 0% |  |  | 0%
36 | Y | 38.521-1 Tx | 6.5D.3_1.1 | General spurious emissions for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#90-e (Feb-21) | R5-206768 | Ref: 38.101-1 6.5D.3 Test applicability is TBD 38.522: R5-210792 38.905: R5-206769 | 1 | 90% | 90% |  |  | 90%
37 | Y | 38.521-1 Tx | 6.5D.3_1.2 | Spurious emission for UE co-existence for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#90-e (Feb-21) | R5-205799 | Ref: 38.101-1 6.5D.3 Test applicability is TBD 38.522: R5-210792 38.905: R5-206769 | 1 | 90% | 90% |  |  | 90%
38 | Y | 38.521-1 Tx | 6.5D.3_1.3 | Additional spurious emissions for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#90-e (Feb-21) | R5-205800 | Ref: 38.101-1 6.5D.3 Test applicability is TBD 38.522: R5-210792 38.905: R5-206769 | 1 | 90% | 90% |  |  | 90%
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
39 |  | 38.521-2 | 2 | Reference | Define References made in TS |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
40 |  | 38.521-2 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively | Ericsson | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
41 |  | 38.521-2 | 4 | General | define categories of test requirements |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
42 |  | 38.521-2 | 5 | Operating bands and Channel arrangement | define the frequency bands and channel arragement |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
43 |  | 38.521-2 | Annex A | measurement channels | define mesurement channels |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
44 |  | 38.521-2 | Annex B | Propagation conditions | Define propagation conditions |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
45 |  | 38.521-2 | Annex C | Downlink physical channels | Define downlink physical channels |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
46 |  | 38.521-2 | Annex D | Characteristics of the interfering signal | Define characteristics of the interfering signal |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
47 |  | 38.521-2 | Annex E | Global In-Channel TX-Test | Specifiy the measurement of all relevant parameters that describe the in-channel quality of the output signal of the TX under test in a single measurement process |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
48 |  | 38.521-2 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
49 |  | 38.521-2 | Annex G | Uplink Physical Channels | Define uplink physical channels |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
50 |  | 38.521-2 | Annex H | Statistical Testing |  |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
TS 38.521-2: FR2 RF test cases - Tx
51 |  | 38.521-2 Tx | 6.2D.1 | UE maximum output power for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#93 (Nov-21) |  | Ref: 38.101-2 6.2D.1 38.522: 38.905: | 1 | 0% | 0% |  |  |  | 0%
52 |  | 38.521-2 Tx | 6.2D.2 | UE maximum output power reduction for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#93 (Nov-21) |  | Ref: 38.101-2 6.2D.2 38.522: 38.905: | 1 | 0% | 0% |  |  |  | 0%
53 |  | 38.521-2 Tx | 6.2D.3 | UE additional maximum output power reduction for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power |  | RAN5#93 (Nov-21) |  | Ref: 38.101-2 6.2D.3 38.522: 38.905: | 1 | 0% | 0% |  |  |  | 0%
54 |  | 38.521-2 Tx | 6.2D.4 | Configured transmitted power for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Ericsson | RAN5#93 (Nov-21) |  | Ref: 38.101-2 6.2D.4 38.522: 38.905: | 1 | 0% | 0% |  |  |  | 0%
TS 38.521-4: Demod/QSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
General
55 |  | 38.521-4 | 2 | References | Define References made in TS |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
56 |  | 38.521-4 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively |  | RAN5#93 (Nov-21) |  | R4-2103827 | 0.1 | 0% | 0% |  |  | 0%
57 |  | 38.521-4 | 4 | General | define categories of test requirements |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
58 |  | 38.521-4 | 5.1.1.3 | Applicability of requirements for optional UE features | define applicability of multi-TRP test cases |  | RAN5#93 (Nov-21) |  | R4-2103826 | 0.1 | 0% | 0% |  |  | 0%
59 |  | 38.521-4 | 5.1.1.8 | Applicability of different requirements with Multi-TRP | define test cases selection rule of multi-TRP test cases |  | RAN5#93 (Nov-21) |  | R4-2103826 | 0.1 | 0% | 0% |  |  | 0%
Demodulation performance requirements (Conducted requirements) (Clause 5)
60 |  | 38.521-4 | 5.2 | PDSCH demodulation requirements | Sub-title |  | RAN5#93 (Nov-21) |  |  | 0
61 | Y | 38.521-4 | 5.2.2.1.11 | 2Rx FDD FR1 PDSCH Single-DCI based SDM scheme performance | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI | Huawei | RAN5#93 (Nov-21) |  | R4-2103828 TS 38.522 | 1 | 0% | 0% |  |  | 0%
62 | Y | 38.521-4 | 5.2.2.1.12 | 2Rx FDD FR1 PDSCH Multi-DCI based transmission scheme performance | PDSCH demodulation requirements for PDSCH from 2TRPs with Multi-DCI |  | RAN5#93 (Nov-21) |  | R4-2103986 TS 38.522 | 1 | 0% | 0% |  |  | 0%
63 | Y | 38.521-4 | 5.2.2.1.13 | 2Rx FDD FR1 PDSCH Single-DCI based FDM scheme A performance | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based FDM scheme A |  | RAN5#93 (Nov-21) |  | R4-2103827 TS 38.522 | 1 | 0% | 0% |  |  | 0%
64 | Y | 38.521-4 | 5.2.2.1.14 | 2Rx FDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based Inter-slot TDM scheme |  | RAN5#93 (Nov-21) |  | R4-2103827 TS 38.522 | 1 | 0% | 0% |  |  | 0%
65 | Y | 38.521-4 | 5.2.2.2.11 | 2Rx TDD FR1 PDSCH Single-DCI based SDM scheme performance | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI | Huawei | RAN5#93 (Nov-21) |  | R4-2103828 TS 38.522 | 1 | 0% | 0% |  |  | 0%
66 | Y | 38.521-4 | 5.2.2.2.12 | 2Rx TDD FR1 PDSCH Multi-DCI based transmission scheme performance | PDSCH demodulation requirements for PDSCH from 2TRPs with Multi-DCI |  | RAN5#93 (Nov-21) |  | R4-2103986 TS 38.522 | 1 | 0% | 0% |  |  | 0%
67 | Y | 38.521-4 | 5.2.2.2.13 | 2Rx TDD FR1 PDSCH Single-DCI based FDM scheme A performance | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based FDM scheme A |  | RAN5#93 (Nov-21) |  | R4-2103827 TS 38.522 | 1 | 0% | 0% |  |  | 0%
68 | Y | 38.521-4 | 5.2.2.2.14 | 2Rx TDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based Inter-slot TDM scheme |  | RAN5#93 (Nov-21) |  | R4-2103827 TS 38.522 | 1 | 0% | 0% |  |  | 0%
69 | Y | 38.521-4 | 5.2.3.1.11 | 4Rx FDD FR1 PDSCH Single-DCI based SDM scheme performance | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI | Huawei | RAN5#93 (Nov-21) |  | R4-2103828 TS 38.522 | 1 | 0% | 0% |  |  | 0%
70 | Y | 38.521-4 | 5.2.3.1.12 | 4Rx FDD FR1 PDSCH Multi-DCI based transmission scheme performance | PDSCH demodulation requirements for PDSCH from 2TRPs with Multi-DCI |  | RAN5#93 (Nov-21) |  | R4-2103986 TS 38.522 | 1 | 0% | 0% |  |  | 0%
71 | Y | 38.521-4 | 5.2.3.1.13 | 4Rx FDD FR1 PDSCH Single-DCI based FDM scheme A performance | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based FDM scheme A |  | RAN5#93 (Nov-21) |  | R4-2103827 TS 38.522 | 1 | 0% | 0% |  |  | 0%
72 | Y | 38.521-4 | 5.2.3.1.14 | 4Rx FDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based Inter-slot TDM scheme |  | RAN5#93 (Nov-21) |  | R4-2103827 TS 38.522 | 1 | 0% | 0% |  |  | 0%
73 | Y | 38.521-4 | 5.2.3.2.11 | 4Rx TDD FR1 PDSCH Single-DCI based SDM scheme performance | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI | Huawei | RAN5#93 (Nov-21) |  | R4-2103828 TS 38.522 | 1 | 0% | 0% |  |  | 0%
74 | Y | 38.521-4 | 5.2.3.2.12 | 4Rx TDD FR1 PDSCH Multi-DCI based transmission scheme performance | PDSCH demodulation requirements for PDSCH from 2TRPs with Multi-DCI |  | RAN5#93 (Nov-21) |  | R4-2103986 TS 38.522 | 1 | 0% | 0% |  |  | 0%
75 | Y | 38.521-4 | 5.2.3.2.13 | 4Rx TDD FR1 PDSCH Single-DCI based FDM scheme A performance | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based FDM scheme A |  | RAN5#93 (Nov-21) |  | R4-2103827 TS 38.522 | 1 | 0% | 0% |  |  | 0%
76 | Y | 38.521-4 | 5.2.3.2.14 | 4Rx TDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based Inter-slot TDM scheme |  | RAN5#93 (Nov-21) |  | R4-2103827 TS 38.522 | 1 | 0% | 0% |  |  | 0%
CSI reporting requirements (Conducted requirements) (Clause 6)
77 |  | 38.521-4 | 6.3 | Reporting of Precoding Matrix Indicator (PMI) | Sub-title |  | RAN5#93 (Nov-21) |  | R4-2103833 | 0.1 | 0% | 0% |  |  | 0%
78 | Y | 38.521-4 | 6.3.2.1.6 | 2Rx FDD FR1 Multiple PMI with 16Tx Enhanced Type II codebook for both SA and NSA | PMI reporting using enhanced Type II codebook |  | RAN5#93 (Nov-21) |  | R4-2103833 TS 38.522 | 1 | 0% | 0% |  |  | 0%
79 | Y | 38.521-4 | 6.3.2.2.6 | 2Rx TDD FR1 Multiple PMI with 16Tx Enhanced Type II codebook for both SA and NSA | PMI reporting using enhanced Type II codebook |  | RAN5#93 (Nov-21) |  | R4-2103833 TS 38.522 | 1 | 0% | 0% |  |  | 0%
80 | Y | 38.521-4 | 6.3.3.1.6 | 4Rx FDD FR1 Multiple PMI with 16Tx Enhanced Type II codebook for both SA and NSA | PMI reporting using enhanced Type II codebook |  | RAN5#93 (Nov-21) |  | R4-2103833 TS 38.522 | 1 | 0% | 0% |  |  | 0%
81 | Y | 38.521-4 | 6.3.3.2.6 | 4Rx TDD FR1 Multiple PMI with 16Tx Enhanced Type II codebook for both SA and NSA | PMI reporting using enhanced Type II codebook |  | RAN5#93 (Nov-21) |  | R4-2103833 TS 38.522 | 1 | 0% | 0% |  |  | 0%
Annex
82 |  | 38.521-4 | Annex A | measurement channels | define mesurement channels |  | RAN5#93 (Nov-21) |  | R4-2103830 | 0.1 | 0% | 0% |  |  | 0%
83 |  | 38.521-4 | Annex B | Propagation conditions | Define propagation conditions |  | RAN5#93 (Nov-21) |  | R4-2103833 | 0.1 | 0% | 0% |  |  | 0%
84 |  | 38.521-4 | Annex C | Downlink physical channels | Define downlink physical channels |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Adding applicability for test cases in 38.521-1 | Huawei | RAN5#93 (Nov-21) | R5-210792 |  | 1 | 0% | 0% |  |  | 0%
|  | 38.522 | 4.1.2 | FR2 standalone conformance test cases | Adding applicability for test cases in 38.521-2 |  |  |  |  | 0.3 | 0% | 0% |  |  |  | 0%
|  | 38.522 | 4.1.4 | Performance conformance test cases | Adding applicability for test cases in 38.521-4 |  |  |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.522 | 4.2 | RRM conformance test cases | Adding applicability for test cases in 38.533 |  |  |  |  | 0.5 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | Test cases for measurement performance(~4), Beam Failure Detection and Link Recovery (~8), Pathloss reference signal switching delay(~4) |  |  |  |  | 16 | 0% | 0% |  |  | 0% | 0%
General
85 |  | 38.533 | 2 | References | Define References made in TS |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0% | 0%
86 |  | 38.533 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0% | 0%
87 |  | 38.533 | 4 | General | define categories of test requirements |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0% | 0%
EN-DC tests within FR1 (Clause 4)
88 |  | 38.533 | 4.5 | Signaling characteristics | Sub-title |  |  |  |  | 0
89 | Y | 38.533 | 4.5.5.5 | EN-DC FR1 Scell CSI-RS-based beam failure detection and SSB-based link recovery in non-DRX | BFD and LR procedure |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  | 0%
90 | Y | 38.533 | 4.5.5.6 | EN-DC FR1 Scell CSI-RS-based beam failure detection and SSB-based link recovery in DRX | BFD and LR procedure |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  | 0%
91 |  | 38.533 | 4.6 | Measurement procedures | Sub-title |  |  |  |  | 0
92 |  | 38.533 | 4.6.7 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
93 |  |  | 4.6.7.0 | Minimum conformance requirements |  |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0.1 | 0% |  | 0% |  |  |  | 0%
94 | Y | 38.533 | 4.6.7.1 | EN-DC FR1 CSI-RS based CMR and no dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  | 0%
95 | Y | 38.533 | 4.6.7.2 | EN-DC FR1 SSB based CMR and dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  | 0%
96 | Y | 38.533 | 4.6.7.3 | EN-DC FR1 CSI-RS based CMR and dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  | 0%
97 |  | 38.533 | 4.7 | Measurement Performance requirements | Sub-title |  |  |  |  | 0
98 |  | 38.533 | 4.7.7 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
99 |  |  | 4.7.7.0 | Minimum conformance requirements |  |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0.1 | 0% |  | 0% |  |  |  | 0%
100 | Y | 38.533 | 4.7.7.1 | EN-DC FR1 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR measurement accuracy | L1-SINR measurement performance |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  | 0%
101 | Y | 38.533 | 4.7.7.2 | EN-DC FR1 SSB based CMR and dedicated IMR L1-SINR absolute measurement accuracy | L1-SINR measurement performance |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  | 0%
102 | Y | 38.533 | 4.7.7.3 | EN-DC FR1 CSI-RS based CMR and dedicated IMR L1-SINR measurement accuracy | L1-SINR measurement performance |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  | 0%
EN-DC tests including FR2 (Clause 5)
103 |  | 38.533 | 5.5 | Signaling characteristics | Sub-title |  |  |  |  | 0
104 | Y | 38.533 | 5.5.5.6 | EN-DC FR2 Scell CSI-RS-based beam failure detection and link recovery in non-DRX | BFD and LR procedure |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
105 | Y | 38.533 | 5.5.5.7 | EN-DC FR2 Scell CSI-RS-based beam failure detection and link recovery in DRX | BFD and LR procedure |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
106 |  | 38.533 | 5.6 | Measurement procedures | Sub-title |  |  |  |  | 0
107 |  | 38.533 | 5.6.5 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
108 |  |  | 5.6.5.0 | Minimum conformance requirements |  |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0.1 | 0% |  | 0% |  |  |  |  | 0%
109 | Y | 38.533 | 5.6.5.1 | EN-DC FR2 CSI-RS based CMR and no dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
110 | Y | 38.533 | 5.6.5.2 | EN-DC FR2 SSB based CMR and dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
111 | Y | 38.533 | 5.6.5.3 | EN-DC FR2 CSI-RS based CMR and dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
112 |  | 38.533 | 5.7 | Measurement Performance requirements | Sub-title |  |  |  |  | 0
113 |  | 38.533 | 5.7.6 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
114 |  |  | 5.7.6.0 | Minimum conformance requirements |  |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0.1 | 0% |  | 0% |  |  |  |  | 0%
115 | Y | 38.533 | 5.7.6.1 | EN-DC FR2 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR measurement accuracy | L1-SINR measurement performance |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
116 | Y | 38.533 | 5.7.6.2 | EN-DC FR2 SSB based CMR and dedicated IMR L1-SINR absolute measurement accuracy | L1-SINR measurement performance |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
117 | Y | 38.533 | 5.7.6.3 | EN-DC FR2 CSI-RS based CMR and dedicated IMR L1-SINR measurement accuracy | L1-SINR measurement performance |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
NR standalone in FR1 (Clause 6)
118 |  | 38.533 | 6.5 | Signalling characteristics | Sub-title |  |  |  |  | 0
119 | Y | 38.533 | 6.5.5.5 | NR SA FR1 Scell CSI-RS-based beam failure detection and SSB-based link recovery in non-DRX | BFD and LR procedure |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  | 0%
120 | Y | 38.533 | 6.5.5.6 | NR SA FR1 Scell CSI-RS-based beam failure detection and SSB-based link recovery in DRX | BFD and LR procedure |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  | 0%
121 |  | 38.533 | 6.6 | Measurement procedures | Sub-title |  |  |  |  | 0
122 |  | 38.533 | 6.6.8 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
123 |  |  | 6.6.8.0 | Minimum conformance requirements |  |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0.1 | 0% | 0% |  |  | 0%
124 | Y | 38.533 | 6.6.8.1 | NR SA FR1 CSI-RS based CMR and no dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  | 0%
125 | Y | 38.533 | 6.6.8.2 | NR SA FR1 SSB based CMR and dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  | 0%
126 | Y | 38.533 | 6.6.8.3 | NR SA FR1 CSI-RS based CMR and dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  | 0%
127 |  | 38.533 | 6.7 | Measurement Performance requirements | Sub-title |  |  |  |  | 0
128 |  | 38.533 | 6.7.9 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
129 |  |  | 6.7.9.0 | Minimum conformance requirements |  |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0.1 | 0% | 0% |  |  | 0%
130 | Y | 38.533 | 6.7.9.1 | NR SA FR1 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR measurement accuracy | L1-SINR measurement performance |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  | 0%
131 | Y | 38.533 | 6.7.9.2 | NR SA FR1 SSB based CMR and dedicated IMR L1-SINR absolute measurement accuracy | L1-SINR measurement performance |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  | 0%
132 | Y | 38.533 | 6.7.9.3 | NR SA FR1 CSI-RS based CMR and dedicated IMR L1-SINR measurement accuracy | L1-SINR measurement performance |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  | 0%
SA tests in FR2 (Clause 7)
133 |  | 38.533 | 7.5 | Signaling characteristics | Sub-title |  |  |  |  | 0
134 | Y | 38.533 | 7.5.5.6 | NR SA FR2 Scell CSI-RS-based beam failure detection and link recovery in non-DRX | BFD and LR procedure |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  |  | 0%
135 | Y | 38.533 | 7.5.5.7 | NR SA FR2 Scell CSI-RS-based beam failure detection and link recovery in DRX | BFD and LR procedure |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  |  | 0%
136 |  | 38.533 | 7.6 | Measurement procedures | Sub-title |  |  |  |  | 0
137 |  | 38.533 | 7.6.6 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
138 |  |  | 7.6.6.0 | Minimum conformance requirements |  |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0.1 | 0% | 0% |  |  |  | 0%
139 | Y | 38.533 | 7.6.6.1 | NR SA FR2 CSI-RS based CMR and no dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  |  | 0%
140 | Y | 38.533 | 7.6.6.2 | NR SA FR2 SSB based CMR and dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  |  | 0%
141 | Y | 38.533 | 7.6.6.3 | NR SA FR2 CSI-RS based CMR and dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  |  | 0%
142 |  | 38.533 | 7.7 | Measurement Performance requirements | Sub-title |  |  |  |  | 0
143 |  | 38.533 | 7.7.6 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
144 |  |  | 7.7.6.0 | Minimum conformance requirements |  |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0.1 | 0% | 0% |  |  |  | 0%
145 | Y | 38.533 | 7.7.6.1 | NR SA FR2 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR measurement accuracy | L1-SINR measurement performance |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  |  | 0%
146 | Y | 38.533 | 7.7.6.2 | NR SA FR2 SSB based CMR and dedicated IMR L1-SINR measurement accuracy | L1-SINR measurement performance |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  |  | 0%
147 | Y | 38.533 | 7.7.6.3 | NR SA FR2 CSI-RS based CMR and dedicated IMR L1-SINR measurement accuracy | L1-SINR measurement performance |  | RAN5#93 (Nov-21) |  | R4-2100938 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  |  | 0%
Annex
148 |  | 38.533 | Annex A | RRM test configurations | RRM test configurations Adding CSI-RS, CSI-IM configurations |  | TBD |  | R4-2100938 | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
149 |  | 38.533 | Annex B | Conditions for RRM requirements applicability for operating bands | Define propagation conditions |  | TBD |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
150 |  | 38.533 | Annex C | Downlink physical channels and propagation conditions | Define downlink physical channels |  | TBD |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
151 |  | 38.533 | Annex D | Deviations from standard test configuration | Define deviations from standard test configuration |  | TBD |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
152 |  | 38.533 | Annex E | Cell configuration mapping | Define cell configuration mapping |  | TBD |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
153 |  | 38.533 | Annex F | Measurement uncertainties and test tolerances | Define measurement uncertainties and test tolerances |  | TBD |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
154 |  | 38.533 | Annex H | Default message contents for RRM |  |  | TBD |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
155 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | TT analysis for RRM Test cases |  | TBD |  |  | 0.3 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
156 |  | 38.903 | Annex B | Acceptable uncertainty of test system for test cases defined in TS 38.521-2 for radiative testing | TT analysis for FR2 RF Test cases |  | TBD |  |  | 0.5 | 0% | 0% |  |  |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
157 |  | 38.905 | 4.1 | Test point analysis for FR1 test cases in TS 38.521-1 | TT analysis for FR1 RF Test cases | Huawei, Ericsson | RAN5#93 (Nov-21) | R5-206857 R5-206858 R5-206769 R5-211809 R5-211810 R5-211811 R5-210791 R5-211018 R5-211134 |  | 1 | 60% (+60%) | 60% (+60%) |  |  | 60%
158 |  | 38.905 | 4.2 | Test point analysis for FR2 test cases in TS 38.521-2 | TT analysis for FR2 RF Test cases |  | RAN5#93 (Nov-21) |  |  | 0.3 | 0% | 0% |  |  |  | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Layer 2
159 | Y | 38.523-1 | 7.1.1.3.10 | Correct Handling of UL HARQ process / Multiple CORESETPoolIndex | **** TP1: [TS 38.214:6.1] WITH: UE in RRC_CONNECTED state and is configured with PDCCH-Config that contains two different values of CORESETPoolIndex in ControlResourceSet WHEN: UE receives PDCCHs that schedule two non-overlapping in time domain PUSCHs are associated to different ControlResourceSets having different values of CORESETPoolIndex THEN: UE sends PUSCHs following the scheduling information of PDCCHs | Motorola Mobility | RAN5#90-e (Feb-21) | R5-206415 R5-210880 | 38.523-2: R5-206416 FFS how to ensure performance of overlapping PDSCH: 1. how to deal with self-interference when 2 PDSCH are transmitted on same channel 2. DMRS needs different CDM group 3. DCI needs different TCI state and scrambling ID | 1 | 65% (+5%) | 65% (+5%) |  |  | 60% | 70%
RRC
160 | Y | 38.523-1 | FFS | eMIMO / Measurement configuration control and reporting / RANK 3~4 in enhanced type II codebook | **** TP1: [TS 38.214:6.1] WITH: UE in RRC_CONNECTED state and is configured with typeII-RI-Restriction-r16 of value '1000' WHEN: The PMI reporting is triggered by DCI THEN: UE reports PMI of RANK 4 with enhanced type II codebook | Motorola Mobility | RAN5#90-e (Feb-21) |  | 38.523-2: 38.508-2: | 1 | 0% | 0% |  |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
161 |  | 38.523-2 | 4 | Recommended Test Case Applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD | R5-206416 |  | 0.2 | 50% | 50% |  |  | 50% | 50%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.