## Cover sheet
3GPP TSG-RAN WG5 Meeting #90-e | [10 empty] | R5-210876
Electronic Meeting, 22nd February - 5th March 2021
Agenda Item: | 7.4.2
Source: | Huawei, HiSilicon
Title: | WP UE Conformance Test Aspects - LTE Advanced high power TDD UE (power class 2)
Work item code: | LTE_TDD_HPUE_R15-UEConTest
Release: | Rel-15
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At the RAN#85 meeting in Newport Beach, USA a Rel-15 RAN5 work item for LTE Advanced high power TDD UE (power class 2) (LTE_TDD_HPUE_R15-UEConTest) was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 98% (+3%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE |  | 97.5% (+2.6%)
TDD |  | 97.5% (+2.6%)
FDD + TDD
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | TDD |  |  | FDD + TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx | 100% |  |  | 100%
RF Tx test cases | 36.521-1 Tx | 96.3% (+4%) |  |  | 96.3% (+4%)
RF Demod test cases | 36.521-1 Demod
Applicability RF, Demod/QSI and RRM test cases | 36.521-2
Test Point analysis receiver and transmitter test cases | 36.905 | 100% |  |  | 100%
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2 | 100% |  |  | 100%
Test suites (TTCN) | 36.523-3
5 References
[1] RP-192116 | New WID on UE Conformance Test Aspects - LTE Advanced high power TDD UE (power class 2)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP LTE Advanced high power TDD UE (power class 2) | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_TDD_HPUE_R15-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item WP LTE Advanced high power TDD UE (power class 2) for LTE comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [12 empty] | vs Area
WP Resp: |  | Zhaorui Ma, Huawei, HiSilicon |  |  | mazhaorui@huawei.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | TDD | FDD + TDD
97.5% (+2.6%)
[14 empty] | 14 (+1) | 0
[14 empty] | 38.5 (+1) | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
E-UTRA RF/RRM
TS 36.521-1: RF test cases - Common parts (general clauses, Annexes)
|  | 36.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.521-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.521-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | 1
TS 36.521-1: RF test cases - Tx
|  | 36.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 36.521-1 Tx | 6.2.2_1 | Maximum Output Power for HPUE |  |  | RAN5#86-e (Feb-20) | R5-201700, R5-203858 | TS 36.101 6.2.2, spec pending | 3 | 100% | 100% |  | 100%
|  | 36.521-1 Tx | 6.2.2A.1_3 | UE Maximum Output Power for CA and HPUE (intra-band contiguous DL CA and UL CA) |  |  |  |  | TS 36.101 6.2.2A, spec pending, No need to change | 0
2 |  | 36.521-1 Tx | 6.2.2B_1 | HPUE Maximum Output Power for UL-MIMO |  |  | RAN5#86-e (Feb-20) | R5-205977 | TS 36.101 6.2.2B, spec pending | 3 | 100% | 100% |  | 100%
3 |  | 36.521-1 Tx | 6.2.3_1 | Maximum Power Reduction (MPR) for HPUE |  |  | RAN5#86-e (Feb-20) | R5-201701, R5-203859, R5-206731 | TS 36.101 6.2.3, spec pending | 3 | 100% | 100% |  | 100%
4 |  | 36.521-1 Tx | 6.2.3A.1_3 | Maximum Power Reduction (MPR) for CA (intra-band contiguous DL CA and UL CA) for HPUE |  |  | RAN5#86-e (Feb-20) | R5-211873 | TS 36.101 6.2.3A, spec pending | 1 | 100% (+100%) | 100% (+100%) |  | 100%
5 |  | 36.521-1 Tx | 6.2.4_1 | Additional Maximum Power Reduction (A-MPR) for HPUE |  |  | RAN5#86-e (Feb-20) | R5-206732 | TS 36.101 6.2.4, spec pending | 3 | 100% | 100% |  | 100%
6 |  | 36.521-1 Tx | 6.2.5_1 | Configured UE transmitted Output Power for HPUE |  |  | RAN5#86-e (Feb-20) | R5-206733 | TS 36.101 6.2.5, spec pending | 3 | 100% | 100% |  | 100%
7 |  | 36.521-1 Tx | 6.2.5A.1_3 | Configured UE transmitted Output Power for CA and HPUE (intra-band contiguous DL CA and UL CA) for HPUE |  |  | RAN5#86-e (Feb-20) | R5-206734 | TS 36.101 6.2.5A, spec pending | 3 | 100% | 100% |  | 100%
8 |  | 36.521-1 Tx | 6.3.5_1 | Power Control for HPUE |  |  | RAN5#86-e (Feb-20) | R5-205982 | TS 36.101 6.3.5, spec pending | 3 | 100% | 100% |  | 100%
9 |  | 36.521-1 Tx | 6.6.2.3_1 | Adjacent Channel Leakage power Ratio for HPUE |  |  | RAN5#86-e (Feb-20) | R5-210875 | TS 36.101 6.6.2.3, spec pending | 1 | 100% (+100%) | 100% (+100%) |  | 100%
10 |  | 36.521-1 Tx | 6.6.2.3A.1_3 | Adjacent Channel Leakage power Ratio for CA (intra-band contiguous DL CA and UL CA) for HPUE |  |  | RAN5#86-e (Feb-20) |  | TS 36.101 6.6.2.3, spec pending | 1 | 0% | 0% |  | 0%
11 |  | 36.521-1 Tx | 6.6.3.3 | Additional spurious emissions |  |  | RAN5#86-e (Feb-20) | R5-206735 | TS 36.101 6.6.3.3, spec pending | 3 | 100% | 100% |  | 100%
TS 36.521-2: Applicability for RF, Demod/QSI reporting and RRM test cases
12 |  | 36.521-1 Rx | 4.1 | Applicability of RF conformance test cases |  |  | RAN5#86-e (Feb-20) | R5-203860 |  | 0.5 | 100% | 100% |  | 100%
TR 36.905: Test Point analysis receiver and transmitter test cases
13 |  | 36.905 | 4.1 | Test point selection in Additional Maximum Power Reduction (A-MPR) test cases | Derivation of test points for radio transmission conformance test cases to accommodate new bands |  | RAN5#86-e (Feb-20) | R5-205985 |  | 10 | 100% | 100% |  | 100%
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  |  | No need to change | 0
TS 36.523-2: Applicability for Protocol test cases
14 |  | 36.523-2 | A.4.4 | Additional information | Update of test applicability statements on the existing HPUE protocol conformance test cases to accommodate new bands |  | RAN5#86-e (Feb-20) | R5-203861 |  | 1 | 100% | 100% |  | 100%
TS 36.523-3: Protocol test suites (TTCN)
|  | 36.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  |  | No need to change | 0
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.