## Summary
Work plan summary:
IMS over 5G (TS 34.229-5)
Completion
|  |  | Overall | FR1 | FR2 | FR1+FR2
| IMS over 5G (TS 34.229-5) | SA Option 2 (SA NR) | 52.35% | 52.35% | 52.35%
NSA Option 3 (EN-DC)
SA Option 5
NSA Option 4 (NE-DC)
NSA Option 7 (NGEN-DC)
Test case statistics
|  |  | Overall number of test cases |  | Number of test cases applicable for FR1 |  | Number of test cases applicable for FR2 |  | Number of test cases applicable for FR1+FR2
|  |  | Overall | Completed | Overall | Completed | Overall | Completed | Overall | Completed
| IMS over 5G (TS 34.229-5) | SA Option 2 (SA NR) | 121 | 54 | 121 | 54 | 121 | 54
NSA Option 3 (EN-DC)
SA Option 5
NSA Option 4 (NE-DC)
NSA Option 7 (NGEN-DC)

## Protocol IMS 5GS
WP Title: | IMS over 5G (TS 34.229-5) | [10 empty] | WP item applicability | [5 empty] | End of work plan columns. Note! Do not remove this column.
RAN-CN interface options dependency
WP Scope: | This work plan section covers the IMS over 5G protocol test cases in TS 34.229-5 for SA option 2. | [10 empty] | 5GC/NR |  | 5GC/LTE | EPC/LTE | 5GC/NR master | 5GC / LTE master
WP Resp: | Hans Rohnert |  |  |  | hans.rohnert@rohde-schwarz.com
TS Resp: | Hans Rohnert |  |  |  | hans.rohnert@rohde-schwarz.com | [6 empty] | SA |  |  | NSA
WP Item ID | Is test case | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | Opt. 2 |  | Opt. 5 | Opt. 3 | Opt. 4 | Opt. 7
[11 empty] | Overall | 52.35%
Phase 1
Phase 2
Phase 3
[11 empty] | Phase 4 | 100%
Phase 5
Phase 6
[11 empty] | Phase 7 | 100%
[11 empty] | Phase 8 | 100%
[11 empty] | Phase 9 | 100%
[11 empty] | Phase 10 | 100%
[11 empty] | Phase 11 | 100%
[11 empty] | Phase 12 | 3.284%
Phase 13
Phase 14
[7 empty] | Overall #WP items: Phase 1 #WP items: Phase 2 #WP items: Phase 3 #WP items: Phase 4 #WP items: Phase 5 #WP items: Phase 6#WP items: Phase 7#WP items: Phase 8#WP items: Phase 9#WP items: Phase 10#WP items: Phase 11#WP items: Phase 12#WP items: Phase 13#WP items: Phase 14#WP items: |  |  |  |  | 141 0 0 0 19 0 0 10 7 19 14 23 49 0 0 |  | 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [11 empty] | Phase number (1,2 etc) and completion (%) per option
Generic Procedures
1 |  | 34.229-1 | A.1.1 | REGISTER | Adapt REGISTER as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
2 |  | 34.229-1 | A.1.4 | SUBSCRIBE | Adapt SUBSCRIBE as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
3 |  | 34.229-1 | A.2.1 | MO INVITE | Adapt MO INVITE as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
4 |  | 34.229-1 | A.2.4 | PRACK | Adapt PRACK as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
5 |  | 34.229-1 | A.2.5 | UPDATE | Adapt UPDATE as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
6 |  | 34.229-1 | A.2.6 | 180 RINGING | Adapt 180 RINGING as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
7 |  | 34.229-1 | A.2.8 | BYE | Adapt BYE as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
8 |  | 34.229-1 | A.2.10 | MO REFER | Adapt MO REFER as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
9 |  | 34.229-1 | A.2.12 | MT REFER | Adapt MT REFER as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
10 |  | 34.229-1 | A.3.1 | 200 OK | Adapt 200 OK as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
11 |  | 34.229-1 | A.4.3 | PUBLISH | Adapt PUBLISH as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
12 |  | 34.229-1 | A.5.1 | SUBSCRIBE for conference event | Adapt SUBSCRIBE for conference event as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
13 |  | 34.229-1 | A.6.1 | SUBSCRIBE for message summary | Adapt SUBSCRIBE for message summary as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
14 |  | 34.229-1 | A.7.3 | MESSAGE for MO SMS | Adapt MESSAGE for MO SMS as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
15 |  | 34.229-1 | A.8.2 | MESSAGE UE providing information for CS to PS SRVCC | Adapt MESSAGE UE providing information for CS to PS SRVCC | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
16 |  | 34.229-5 | A.2 | IMS Registration / 5GS | IMS Registration in 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-195233, R5-203437, R5-205115, R5-205585 |  | 0.5 | 100% | 4 | 100%
17 |  | 34.229-5 | A.4 | MTSI MO Voice Call / 5GS | MO Voice Call over 5GS | Rohde & Schwarz | Opt 2: RAN5#89 (Nov-20) | R5-195234, R5-195892, R5-202691, R5-205311, R5-210348, R5-212048, R5-213523 |  | 0.5 | 100% | 9 | 100%
18 |  | 34.229-5 | A.5 | MTSI MT Voice Call / 5GS | MT Voice Call over 5GS | Rohde & Schwarz | Opt 2: RAN5#89 (Nov-20) | R5-202692, R5-203462, R5-205312, R5-210056 |  | 0.5 | 100% | 9 | 100%
19 |  | 34.229-5 | A.3 | IMS Emergency Registration / 5GS | IMS Emergency Registration in 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-195235, R5-204480 |  | 0.5 | 100% | 4 | 100%
20 |  | 34.229-5 | A.6 | IMS Emergency Voice Call / 5GS | Emergency call over 5GS | Rohde & Schwarz | Opt 2: RAN5#91 (May-21) | R5-195237, R5-205518, R5-212388 |  | 0.5 | 100% | 11 | 100%
21 |  | 34.229-1 | C.32b | MO release of IMS call | When UE needs to release a voice call over NR | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-196034 |  | 0.5 | 100% | 4 | 100%
22 |  | 34.229-2 | A.4.10 | 5G capability | Adding 5G capability | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-195232, R5-195897 |  | 0.5 | 100% | 4 | 100%
37 |  | 34.229-5 | A.7 | MO release of IMS session | New generic procedure where UE releases the IMS session | Rohde & Schwarz | Opt 2: RAN5#87 (May-20) | R5-197746, R5-205219 |  | 0.5 | 100% | 7 | 100%
36 |  | 34.229-5 | A.8 | MT release of IMS session | New generic procedure where SS releases the IMS session | Rohde & Schwarz | Opt 2: RAN5#88 (Aug-20) | R5-203439 |  | 0.5 | 100% | 8 | 100%
75 |  | 34.229-5 | A.9 | EPS Fallback for Voice Call | New generic procedure replacing preliminary procedure in TS 34.229-1 | Rohde & Schwarz | Opt 2: RAN5#88 (Aug-20) | R5-204484, R5-205113, R5-211437 |  | 0.5 | 100% | 8 | 100%
128 |  | 34.229-5 | A.10 | PUBLISH | New generic procedure for PUBLISH | Rohde & Schwarz | Opt 2: RAN5#89 (Nov-20) | R5-205115 |  | 0.5 | 100% | 9 | 100%
129 |  | 34.229-5 | A.11 | Mobile Initiated De-Registration / 5GS | New generic procedure as 5G equivalent of Appendix C.30 of TS 34.229-1 | Rohde & Schwarz | Opt 2: RAN5#90 (Feb-21) | R5-206373, R5-210259 |  | 0.5 | 100% | 10 | 100%
130 |  | 34.229-5 | A.12 | IMS Re-Registration / 5GS | New generic procedure as 5G equivalent of Appendix C.46 of TS 34.229-1 | Rohde & Schwarz | Opt 2: RAN5#89 (Nov-20) | R5-205185 |  | 0.5 | 100% | 9 | 100%
131 |  | 34.229-5 | A.13 | Mobile Originating SMS / 5GS | New generic procedure for Mobile Originating SMS over 5GS | Keysight | Opt 2: RAN5#89 (Nov-20) | R5-206374 |  | 0.5 | 100% | 9 | 100%
132 |  | 34.229-5 | A.14 | Mobile Terminating SMS / 5GS | New generic procedure for Mobile Terminating SMS over 5GS | Keysight | Opt 2: RAN5#89 (Nov-20) | R5-206374 |  | 0.5 | 100% | 9 | 100%
138 |  | 34.229-5 | A.15 | Mobile Originating Video Call / 5GS | New generic procedure for Mobile Originating Video Call over 5GS | Qualcomm | Opt 2: RAN5#90 (Feb-21) | R5-211433, R5-211367, R5-213523 |  |  | 100% | 10 | 100%
133 |  | 34.229-1 | A.1.9 | 403 Forbidden for REGISTER | New generic procedure for 403 FORBIDDEN response for REGISTER | Rohde & Schwarz | Opt 2: RAN5#89 (Nov-20) | R5-205210 |  |  | 100% | 9 | 100%
134 |  | 34.229-1 | A.2.25 | 420 Bad Extension for INVITE | New generic procedure for 420 Bad Extension response for INVITE | ZTE | Opt 2: RAN5#89 (Nov-20) | R5-206370 |  |  | 100% | 9 | 100%
139 |  | 34.229-5 | A.16 | Mobile Terminating Video Call / 5GS | New generic procedure for Mobile Terminating Video Call over 5GS | Rohde & Schwarz | Opt 2: RAN5#91 (May-21) | R5-213524 |  |  | 100% | 11 | 100%
140 |  | 34.229-5 | A.17 | UE putting a Voice Call on hold or resume the call / 5GS | New generic procedure for holding resp resuming a call from UE side | Huawei/HiSilicon | Opt 2: RAN5#91 (May-21) | R5-213529 |  |  | 100% | 11 | 100%
141 |  | 34.229-5 | A.18 | SS putting a Voice Call on hold or resume the call / 5GS | New generic procedure for holding resp resuming a call from SS side | Huawei/HiSilicon | Opt 2: RAN5#91 (May-21) | R5-213530 |  |  | 100% | 11 | 100%
142 |  | 34.229-5 | A.19 | Conference creation / 5GS | New generic procedure for creating a conference | Huawei/HiSilicon | Opt 2: RAN5#91 (May-21) | R5-213531 |  |  | 100% | 11 | 100%
143 |  | 34.229-5 | A.20 | Inviting a user to a conference by sending REFER to focus / 5GS | New generic procedure for inviting a user to a conference via the focus | Huawei/HiSilicon | Opt 2: RAN5#91 (May-21) | R5-213532 |  |  | 100% | 11 | 100%
Test cases Option 2 - NR access to 5GC
Registration
23 | Y | 34.229-5 | 6.1 | Initial Registration / 5GS | #VALUE! | Rohde & Schwarz | Opt 2: RAN5#87 (May-20) | R5-197049, R5-197934, R5-202686, R5-203442, R5-206383 |  | 1 | 100% | 7 | 100%
24 | Y | 34.229-5 | 6.2 | Initial Registration Failures / 5GS | #VALUE! | Rohde & Schwarz | Opt 2: RAN5#87 (May-20) | R5-198899, R5-198239, R5-202687, R5-203443, R5-213534 |  | 1 | 100% | 7 | 100%
25 | Y | 34.229-5 | 6.3 | Re-Registration Scenarios / 5GS | #VALUE! | Rohde & Schwarz | Opt 2: RAN5#87 (May-20) | R5-198240, R5-202688, R5-204481, R5-210057 |  | 1 | 100% | 7 | 100%
26 | Y | 34.229-5 | 6.4 | De-Registration Scenarios / 5GS | #VALUE! | Rohde & Schwarz | Opt 2: RAN5#87 (May-20) | R5-198241, R5-202689, R5-203445, R5-210095, R5-212127 |  | 1 | 100% | 7 | 100%
27 | Y | 34.229-5 | 6.5 | Refresh for ISIM parameters / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#87 (May-20) | R5-202678, R5-203447 | (LTE 8.15) 24.229 cl 5.1.1.7, C.4 | 1 | 100% | 7 | 100%
66 | Y | 34.229-5 | 6.6 | Re-Registration after capability update / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#87 (May-20) | R5-202679, R5-203448, R5-205217 | 24.229 cl 5.1.1.4.1 | 1 | 100% | 7 | 100%
28 | Y | 34.229-5 | 6.7 | Authentication / MAC Parameter Invalid / Only two consecutive invalid challenges / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#87 (May-20) | R5-202680, R5-203452, R5-206386 | (LTE 9.1) + 24.229 cl 5.1.1.5.12 | 1 | 100% | 7 | 100%
29 | Y | 34.229-5 | 6.8 | Authentication / Security-Server missing / SQN out of range / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#87 (May-20) | R5-202681, R5-203453 | 24.229 cl 5.1.1.5.1 + (LTE 9.2) | 1 | 100% | 7 | 100%
30 | Y | 34.229-5 | 6.9 | Subscription / 503 Service Unavailable / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#87 (May-20) | R5-202682, R5-203454 | (LTE 10.1) | 1 | 100% | 7 | 100%
Call Control
32 | Y | 34.229-5 | 7.1 | MTSI MO Voice Call / 503 Service Unavailable / 5GS | #VALUE! | Qualcomm | Opt 2: RAN5#89 (Nov-20) | R5-206385, R5-210882, R5-213521, R5-213535 | (LTE 12.2) | 1 | 100% | 9 | 100%
31 | Y | 34.229-5 | 7.2 | MTSI MO Voice Call / 504 Server Time-out / 5GS | #VALUE! | Qualcomm | Opt 2: RAN5#89 (Nov-20) | R5-206384, R5-211434, R5-213535 | (LTE 12.2a) | 1 | 100% | 9 | 100%
33 |  | 34.229-5 | 7.3 | Void | #VALUE! | Huawei/HiSilicon |  | R5-206379, R5-210659 | Test Case voided by RAN5#90-e (was MTSI MO Voice Call / 421 Extension Required / 5GS) | 1
34 | Y | 34.229-5 | 7.4 | MTSI MO Voice Call with preconditions at both originating UE and terminating UE / 5GS | #VALUE! | Rohde & Schwarz | Opt 2: RAN5#89 (Nov-20) | R5-202690, R5-206382, R5-211429, R5-210343, R5-212047, R5-213535 | (LTE 12.12/12.23), NG114 cl 2.2.4, 2.4.1 / could be changed to cover both possibilities at remote UE | 1 | 100% | 9 | 100%
38 | Y | 34.229-5 | 7.5 | MTSI MO Voice Call without preconditions at both originating UE and terminating UE / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#89 (Nov-20) | R5-202683, R5-206382, R5-211429, R5-213535 | (LTE 12.12a/12.23), NG114 cl 2.2.4, 2.4.1 | 1 | 100% | 9 | 100%
35 | Y | 34.229-5 | 7.6 | MTSI MT Voice Call with preconditions at both originating UE and terminating UE / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#89 (Nov-20) | R5-202684, R5-203441, R5-203461, R5-206382, R5-211429, R5-213535 | (LTE 12.13/12.24) NG114 cl 2.2.4, 2.4.1, 24.229 cl U.3.1.4 - investigate optionality | 1 | 100% | 9 | 100%
39 | Y | 34.229-5 | 7.7 | MTSI MT Voice Call without preconditions at both originating UE and terminating UE / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#89 (Nov-20) | R5-202685, R5-203441, R5-206382, R5-212209, R5-213535 | (LTE 12.13b/12.24) NG114 cl 2.2.4, 2.4.1, 24.229 cl U.3.1.4 | 1 | 100% | 9 | 100%
63 | Y | 34.229-5 | 7.8 | MTSI MT Voice Call without preconditions at originating UE and with preconditions at terminating UE / 5GS | #VALUE! | ZTE | Opt 2: RAN5#89 (Nov-20) | R5-206375, R5-211429, R5-213535 | 24.229 cl 5.1.4.1, first bullet d). | 1 | 100% | 9 | 100%
64 | Y | 34.229-5 | 7.9 | MTSI MT Voice Call with preconditions at originating UE and without preconditions at terminating UE / 5GS | #VALUE! | ZTE | Opt 2: RAN5#89 (Nov-20) | R5-206376, R5-213535 | (LTE 12.13c) 24.229 cl 5.1.4.1, first bullet b) | 1 | 100% | 9 | 100%
45 | Y | 34.229-5 | 7.10 | MTSI MT Voice call without preconditions and without SDP offer in MT INVITE / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#89 (Nov-20) | R5-206381, R5-211436, R5-213535 | 24.229 cl U.3.1.4 | 1 | 100% | 9 | 100%
65 | Y | 34.229-5 | 7.11 | MTSI MT Voice call without preconditions at terminating UE and originating UE requiring them / 5GS | #VALUE! | ZTE | Opt 2: RAN5#89 (Nov-20) | R5-206377, R5-211435, R5-213525, R5-213535 | 24.229 cl 5.1.4.1, first bullet c) | 1 | 100% | 9 | 100%
127 | Y | 34.229-5 | 7.12 | MTSI MO Voice Call with preconditions at originating UE and without preconditions at terminating UE / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#89 (Nov-20) | R5-206380, R5-213535 | 24.229 cl 5.1.3, bullet b) | 1 | 100% | 9 | 100%
47 | Y | 34.229-5 | 7.13 | MTSI MT Voice Call with RTCP disabled / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#91 (May-21) | R5-213536 | NG114 cl 3.6.3 | 1 | 100% | 11 | 100%
40 | Y | 34.229-5 | 7.14 | MTSI MO Video call with preconditions at both originating UE and terminating UE / 5GS | #VALUE! | Qualcomm | Opt 2: RAN5#91 (May-21) | R5-211431, R5-213535, R5-213674 | (LTE 12.21), NG114 cl 2.2.4 | 1 | 100% | 11 | 100%
41 | Y | 34.229-5 | 7.15 | MTSI MO Video call without preconditions at both originating UE and terminating UE / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#91 (May-21) | R5-213537 | (LTE 12.21), NG114 cl 2.2.4 | 1 | 100% | 11 | 100%
42 | Y | 34.229-5 | 7.16 | MTSI MT Video call with preconditions at both originating UE and terminating UE / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#91 (May-21) | R5-213538 | (LTE 12.22) | 1 | 100% | 11 | 100%
43 | Y | 34.229-5 | 7.17 | MTSI MT Video call without preconditions at both originating UE and terminating UE / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#91 (May-21) | R5-213539 | (LTE 12.22) | 1 | 100% | 11 | 100%
48 | Y | 34.229-5 | 7.18 | MTSI MO Voice Call / EVS / AMR-WB / 5GS | #VALUE! | Mediatek | Opt 2: RAN5#91 (May-21) | R5-213520 | (LTE 12.25) | 1 | 100% | 11 | 100%
49 | Y | 34.229-5 | 7.19 | MTSI MT Voice Call / EVS / AMR-WB IO mode / 5GS | #VALUE! | Mediatek | Opt 2: RAN5#91 (May-21) | R5-212104 | (LTE 12.26) | 1 | 100% | 11 | 100%
50 | Y | 34.229-5 | 7.20 | MTSI MO Voice Call / add video and remove video / with preconditions at both originating UE and terminating UE / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#91 (May-21) | R5-213540 | (LTE 17.1), NG114 cl 2.2.4 | 1 | 100% | 11 | 100%
51 | Y | 34.229-5 | 7.21 | MTSI MO Voice Call / add video and remove video / without preconditions at both originating UE and terminating UE / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#91 (May-21) | R5-213541 | (LTE 17.1), NG114 cl 2.2.4, but send first re-INVITE from SS | 1 | 100% | 11 | 100%
54 | Y | 34.229-5 | 7.22 | MTSI MT Voice Call / add video and remove video / with preconditions at both originating UE and terminating UE / 5GS | #VALUE! | Qualcomm | Opt 2: RAN5#91 (May-21) | R5-213544 | (LTE 17.2 but make UE send first re-INVITE) | 1 | 100% | 11 | 100%
55 | Y | 34.229-5 | 7.23 | MTSI MT Voice Call / add video and remove video / without preconditions at both originating UE and terminating UE / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#91 (May-21) | R5-213542 | (LTE 17.2 but make UE send first re-INVITE) | 1 | 100% | 11 | 100%
56 | Y | 34.229-5 | 7.24 | Forking / UE receives two responses and one CANCEL request / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#91 (May-21) | R5-213543 | NG114 cl 2.3.7 | 1 | 100% | 11 | 100%
136 | Y | 34.229-5 | 7.25 | MTSI MT Voice call without SDP offer in INVITE / 5GS | #VALUE! | Rohde & Schwarz | Opt 2: RAN5#90 (Feb-21) | R5-210072, R5-212160, R5-213535 | NG114 cl 2.2.4 | 1 | 100% | 10 | 100%
137 | Y | 34.229-5 | 7.26 | Mobile Originating CAT / Forking Model / 5GS | #VALUE! | Huawei/HiSilicon | Opt 2: RAN5#90 (Feb-21) | R5-211439, R5-212076, R5-213535 | (LTE 20.1) | 1 | 100% | 10 | 100%
44 | Y | 34.229-5 | 7.27 | Session Timer / MO Call / UE is able to refresh the session / 5GS | #VALUE! | ZTE | Opt 2: RAN5#90 (Feb-21) | R5-211421 | (LTE 22.1), NG114 cl 2.2.8 | 1 | 100% | 10 | 100%
57 | Y | 34.229-5 | 7.28 | Session Timer / MO Call / Remote end is refresher / 5GS | #VALUE! | ZTE | Opt 2: RAN5#90 (Feb-21) | R5-211422 | (LTE 22.2) | 1 | 100% | 10 | 100%
58 | Y | 34.229-5 | 7.29 | Session Timer / MO Call / Remote end does not support Session Timer / 5GS | #VALUE! | ZTE | Opt 2: RAN5#90 (Feb-21) | R5-211423 | (LTE 22.3), NG114 cl 2.2.8 | 1 | 100% | 10 | 100%
59 | Y | 34.229-5 | 7.30 | Session Timer / MO Call / Remote end supports but does not use Session Timer / 5GS | #VALUE! | ZTE | Opt 2: RAN5#90 (Feb-21) | R5-211424 | (LTE 22.4), NG114 cl 2.2.8 | 1 | 100% | 10 | 100%
60 | Y | 34.229-5 | 7.31 | Session Timer / MT Call / Remote end supports but does not send Session-Expires / 5GS | #VALUE! | ZTE | Opt 2: RAN5#90 (Feb-21) | R5-211425, R5-213533 | (LTE 22.5), NG114 cl 2.2.8 | 1 | 100% | 10 | 100%
61 | Y | 34.229-5 | 7.32 | Session Timer / MT Call / Remote end sends Session-Expires but does not choose refresher / 5GS | #VALUE! | ZTE | Opt 2: RAN5#90 (Feb-21) | R5-211426, R5-213533 | (LTE 22.6), NG114 cl 2.2.8 | 1 | 100% | 10 | 100%
53 | Y | 34.229-5 | 7.33 | Session Timer / MT Call / Remote end chooses UE as refresher / 5GS | #VALUE! | ZTE | Opt 2: RAN5#90 (Feb-21) | R5-211427, R5-213545 | (LTE 22.7) | 1 | 100% | 10 | 100%
62 | Y | 34.229-5 | 7.34 | Session Timer / MT Call / Remote end does not support Session Timer / 5GS | #VALUE! | ZTE | Opt 2: RAN5#90 (Feb-21) | R5-211428 | (LTE 22.8) | 1 | 100% | 10 | 100%
Supplementary Services
72 | Y | 34.229-5 | 8.1 | Originating Identification Presentation / Configuration / 5GS | #VALUE! | Qualcomm | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.1), NG114 cl 2.3.12 Outstanding Editor's Notes | 1 | 50% | 12 | 50%
76 | Y | 34.229-5 | 8.2 | Originating Identification Restriction / Configuration / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.2) | 1 | 0% | 12 | 0%
77 | Y | 34.229-5 | 8.3 | Originating Identification Restriction / Signalling / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.2a), NG114 cl 2.3.6 | 1 | 0% | 12 | 0%
78 | Y | 34.229-5 | 8.4 | Terminating Identification Presentation / Configuration / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.3) | 1 | 0% | 12 | 0%
79 | Y | 34.229-5 | 8.5 | Terminating Identification Restriction / Configuration / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.4) | 1 | 0% | 12 | 0%
80 | Y | 34.229-5 | 8.6 | Terminating Identification Restriction / Signalling / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.4a), NG114 cl 2.3.7 | 1 | 0% | 12 | 0%
81 | Y | 34.229-5 | 8.7 | Communication Forwarding Unconditional / Configuration / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.5), NG114 cl 2.3.1 | 1 | 0% | 12 | 0%
82 | Y | 34.229-5 | 8.8 | Communication Forwarding Unconditional / Signalling / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | 24.604 cl A.1.1 | 1 | 0% | 12 | 0%
83 | Y | 34.229-5 | 8.9 | Communication Forwarding on Not Logged-in / Configuration / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.10), NG114 cl 2.3.1 | 1 | 0% | 12 | 0%
84 | Y | 34.229-5 | 8.10 | Communication Forwarding on Not Logged-in / Signalling / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | NG114 cl 2.3.1 | 1 | 0% | 12 | 0%
85 | Y | 34.229-5 | 8.11 | Communication Forwarding on Busy / Configuration / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.9), NG114 cl 2.3.1 | 1 | 0% | 12 | 0%
86 | Y | 34.229-5 | 8.12 | Communication Forwarding on Busy / Signalling / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | NG114 cl 2.3.1 | 1 | 0% | 12 | 0%
87 | Y | 34.229-5 | 8.13 | Communication Forwarding on Subscriber Not Reachable / Configuration / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.10a), NG114 cl 2.3.1 | 1 | 0% | 12 | 0%
88 | Y | 34.229-5 | 8.14 | Communication Forwarding on Subscriber Not Reachable / Signalling / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | NG114 cl 2.3.1 | 1 | 0% | 12 | 0%
89 | Y | 34.229-5 | 8.15 | Communication Forwarding on No Reply / Configuration / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.7) | 1 | 0% | 12 | 0%
90 | Y | 34.229-5 | 8.16 | Communication Forwarding on No Reply / Signalling / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.8), NG114 cl 2.3.1 | 1 | 0% | 12 | 0%
91 | Y | 34.229-5 | 8.17 | Barring of All Incoming Calls / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | TS 24.611 cl 4.9.1.4, NG114 cl 2.3.1, 2.3.9 | 1 | 0% | 12 | 0%
73 | Y | 34.229-5 | 8.18 | Barring of All Incoming Calls / except for a specific user / 5GS | #VALUE! | Qualcomm | Opt 2: RAN5#92 (Aug-21) | R5-204485 | (LTE 15.13) same as 8.1 | 1 | 50% | 12 | 50%
92 | Y | 34.229-5 | 8.19 | Barring of All Incoming Calls from anonymous users / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.14) | 1 | 0% | 12 | 0%
93 | Y | 34.229-5 | 8.20 | Barring of All Incoming Calls / Signalling / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | TS 24.611 cl 4.5.2.13, NG114 cl 2.3.1 | 1 | 0% | 12 | 0%
94 | Y | 34.229-5 | 8.21 | Barring of all Outgoing Calls / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | TS 24.611 cl 4.9.1.4, NG114 cl 2.3.1, 2.3.9 | 1 | 0% | 12 | 0%
95 | Y | 34.229-5 | 8.22 | Barring of Outgoing International Calls / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | TS 24.611 cl 4.9.1.4, NG114 cl 2.3.1, 2.3.9 | 1 | 0% | 12 | 0%
96 | Y | 34.229-5 | 8.23 | Barring of Outgoing International Calls / ex Home Country / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | TS 24.611 cl 4.9.1.4, NG114 cl 2.3.1, 2.3.9 | 1 | 0% | 12 | 0%
97 | Y | 34.229-5 | 8.24 | Barring of Outgoing International Calls / When Roaming / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.14b) TS 24.611 cl 4.9.1.4, NG114 cl 2.3.1, 2.3.9 | 1 | 0% | 12 | 0%
98 | Y | 34.229-5 | 8.25 | Barring of Incoming Calls / When Roaming / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.14a) TS 24.611 cl 4.9.1.4, NG114 cl 2.3.1, 2.3.9 | 1 | 0% | 12 | 0%
99 | Y | 34.229-5 | 8.26 | MO Call Hold without announcement / 5GS | #VALUE! | Huawei / HiSilicon | Opt 2: RAN5#91 (May-21) | R5-211440, R5-213526 | (LTE 15.11 but MT release), NG114 cl 2.3.1, 2.3.10 | 1 | 100% | 11 | 100%
100 | Y | 34.229-5 | 8.27 | MO Video Call Hold without announcement / 5GS | #VALUE! | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.11a), NG114 cl 2.3.1, 2.3.10 | 1 | 0% | 12 | 0%
101 | Y | 34.229-5 | 8.28 | MT Call Hold without announcement / 5GS | #VALUE! | Huawei / HiSilicon | Opt 2: RAN5#91 (May-21) | R5-211441, R5-213527, R5-213527 | (LTE 15.12 but MO release), NG114 cl 2.3.1, 2.3.10 | 1 | 100% | 11 | 100%
102 | Y | 34.229-5 | 8.29 | MT Video Call Hold without announcement / 5GS | #VALUE! | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.12a), NG114 cl 2.3.1, 2.3.10 | 1 | 0% | 12 | 0%
103 | Y | 34.229-5 | 8.30 | Subscription to the MWI event package / 5GS | #VALUE! | Huawei / HiSilicon | Opt 2: RAN5#90 (Feb-21) | R5-211442 | (LTE 15.15), NG114 cl 2.3.1, cl 2.3.4 | 1 | 100% | 10 | 100%
104 | Y | 34.229-5 | 8.31 | Creating and leaving a conference / 5GS | #VALUE! | Huawei / HiSilicon | Opt 2: RAN5#92 (Aug-21) | R5-211443 | (LTE 15.17), NG114 cl 2.3.1, 2.3.3 Generic Procedure(s) to be produced | 1 | 60% | 12 | 60%
105 | Y | 34.229-5 | 8.32 | Inviting user to conference by sending a REFER request to the conference focus / 5GS | #VALUE! | Huawei / HiSilicon | Opt 2: RAN5#92 (Aug-21) | R5-211444 | (LTE 15.19), NG114 cl 2.3.1, 2.3.3 Generic Procedure(s) to be produced | 1 | 60% | 12 | 60%
106 | Y | 34.229-5 | 8.33 | Inviting user to conference by sending a REFER request to the conference focus / Video / 5GS | #VALUE! | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.19a), NG114 cl 2.3.1, 2.3.3 | 1 | 0% | 12 | 0%
107 | Y | 34.229-5 | 8.34 | Three way session creation / 5GS | #VALUE! | Huawei / HiSilicon | Opt 2: RAN5#91 (May-21) | R5-211445, R5-213528 | (LTE 15.21a), NG114 cl 2.3.1, 2.3.3 | 1 | 100% | 11 | 100%
108 | Y | 34.229-5 | 8.35 | Three way session creation / Video / 5GS | #VALUE! | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.21c), NG114 cl 2.3.1, 2.3.3 | 1 | 0% | 12 | 0%
109 | Y | 34.229-5 | 8.36 | MO Explicit Communication Transfer / Consultative Call Transfer / 5GS | #VALUE! | Huawei / HiSilicon | Opt 2: RAN5#91 (May-21) | R5-211446, R5-213522 | (LTE 15.25), NG114 cl 2.3.1, 2.3.11 | 1 | 100% | 11 | 100%
110 | Y | 34.229-5 | 8.37 | Communication Waiting and answering the call / 5Gs | #VALUE! | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.27), NG114 cl 2.3.1, 2.3.4 | 1 | 0% | 12 | 0%
111 | Y | 34.229-5 | 8.38 | Communication Waiting and cancelling the call / 5GS | #VALUE! | Qualcomm | Opt 2: RAN5#90 (Feb-21) | R5-211447 | (LTE 15.28), NG114 cl 2.3.1, 2.3.4 | 1 | 100% | 10 | 100%
112 | Y | 34.229-5 | 8.39 | GBA authentication / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.29) | 1 | 0% | 12 | 0%
113 | Y | 34.229-5 | 8.40 | User initiated USSI / 5GS | #VALUE! | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.30) | 1 | 0% | 12 | 0%
135 | Y | 34.229-5 | 8.41 | Communication Forwarding on No Reply: MO Call initiation with preconditions | #VALUE! | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 15.8), NG114 cl 2.4.8 |  | 0% | 12 | 0%
SMS
67 | Y | 34.229-5 | 9.1 | Mobile Originating SMS / 5GS | #VALUE! | ZTE | Opt 2: RAN5#88 (Aug-20) | R5-204482, R5-206287 | (LTE 18.1) | 1 | 100% | 8 | 100%
68 | Y | 34.229-5 | 9.2 | Mobile Terminating SMS / 5GS | #VALUE! | ZTE | Opt 2: RAN5#88 (Aug-20) | R5-204483, R5-206372 | (LTE 18.2) | 1 | 100% | 8 | 100%
69 | Y | 34.229-5 | 9.3 | Mobile Originating Concatenated SMS / 5GS | #VALUE! | Qualcomm | Opt 2: RAN5#88 (Aug-20) | R5-204486, R5-205157 | (LTE 18.1a) | 1 | 100% | 8 | 100%
70 | Y | 34.229-5 | 9.4 | Mobile Terminating Concatenated SMS / 5GS | #VALUE! | Huawei, HiSilicon | Opt 2: RAN5#88 (Aug-20) | R5-204477, R5-205158 | (LTE 18.2a) | 1 | 100% | 8 | 100%
71 | Y | 34.229-5 | 9.5 | Mobile Originating SMS / RP-ERROR / 5GS | #VALUE! | Huawei, HiSilicon | Opt 2: RAN5#88 (Aug-20) | R5-204478, R5-205159, R5-210196 | (LTE 18.1b) | 1 | 100% | 8 | 100%
Emergency Calls
74 | Y | 34.229-5 | 10.1 | Emergency Call with emergency registration / Success / Location information available / 5GS | #VALUE! | Huawei, HiSilicon | Opt 2: RAN5#91 (May-21) | R5-204479, R5-211438, R5-212387 | (LTE 19.1.1). Dependency on A.6. | 1 | 100% | 11 | 100%
114 | Y | 34.229-5 | 10.2 | Emergency Call with emergency registration / Success / Location information not available / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 19.1.2) | 1 | 0% | 12 | 0%
115 | Y | 34.229-5 | 10.3 | Emergency call with emergency registration / Emergency SIP signalling and media in parallel with an other ongoing IM CN subsystem signalling and media / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 19.1.5) | 1 | 0% | 12 | 0%
116 | Y | 34.229-5 | 10.4 | Non-UE detectable emergency call / IM CN sends a 1xx response / UE geographical location information available or not / 5GS |  | Mediatek | Opt 2: RAN5#92 (Aug-21) |  | (LTE 19.3.1) | 1 | 0% | 12 | 0%
117 | Y | 34.229-5 | 10.6 | Non-UE detectable emergency call / IM CN sends 380 with an Alternative Service / Previous emergency IMS registration not expired / 5GS |  | Qualcomm | Opt 2: RAN5#92 (Aug-21) |  | (LTE 19.3.4) - note hole in that 10.5 is missing | 1 | 0% | 12 | 0%
118 | Y | 34.229-5 | 10.7 | Emergency call without emergency registration / UE does not contain an ISIM or USIM / 5GS |  | Mediatek | Opt 2: RAN5#92 (Aug-21) |  | (LTE 19.4.1) | 1 | 0% | 12 | 0%
119 | Y | 34.229-5 | 10.8 | Emergency call without emergency registration / UE contains an ISIM or USIM / UE is in state 5GMM-REGISTERED.LIMITED-SERVICE / 5GS |  | Mediatek | Opt 2: RAN5#92 (Aug-21) |  | (LTE 19.4.2) | 1 | 0% | 12 | 0%
120 | Y | 34.229-5 | 10.9 | Emergency call without emergency registration / UE credentials are not accepted / 5GS |  | Mediatek | Opt 2: RAN5#92 (Aug-21) |  | (LTE 19.4.5) | 1 | 0% | 12 | 0%
121 | Y | 34.229-5 | 10.10 | Emergency call without emergency registration / Failure of registration / Rejected by 403 (Forbidden) / 5GS |  | Mediatek | Opt 2: RAN5#92 (Aug-21) |  | (LTE 19.4.6) | 1 | 0% | 12 | 0%
122 | Y | 34.229-5 | 10.11 | New initial emergency registration after obtaining new IP address different than the IP address / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 19.5.1) | 1 | 0% | 12 | 0%
123 | Y | 34.229-5 | 10.12 | User-initiated emergency reregistration / UE has emergency related ongoing dialog / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 19.5.6) | 1 | 0% | 12 | 0%
124 | Y | 34.229-5 | 10.13 | User-initiated emergency reregistration / User initiates an emergency call / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 19.5.7) | 1 | 0% | 12 | 0%
125 | Y | 34.229-5 | 10.14 | In parallel emergency and non-emergency registrations / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 19.5.9) | 1 | 0% | 12 | 0%
126 | Y | 34.229-5 | 10.15 | Deregistration upon emergency registration expiration / 5GS |  | to be assigned | Opt 2: RAN5#92 (Aug-21) |  | (LTE 19.5.10) | 1 | 0% | 12 | 0%
Test cases Option 2 - non-3GPP access to 5GC
| Y | 34.229-5 | TBD | TBD | Placeholder for expected additionaltest cases that have not yet been included in the WP. | for later | Opt 2: RAN5#92 (Aug-21) |  | The number in the weight column represent the remaining number of test cases expected to be added. | 20 | 0% | 12 | 0%
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Y = the WP Pitem is a test case.
Note on L6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.