## Summary
Work plan summary:
Idle Mode Protocol Test Cases (TS 38.523-1, TS 38.523-2)
Completion
|  |  | Overall | FR1 | FR2 | FR1+FR2
| Idle Mode Protocol Test Cases (TS 38.523-1, TS 38.523-2) | SA Option 2 (SA NR) | 94.63% | 100% | 89.52%
NSA Option 3 (EN-DC)
SA Option 5
NSA Option 4 (NE-DC)
NSA Option 7 (NGEN-DC)
Test case statistics
|  |  | Overall number of test cases |  | Number of test cases applicable for FR1 |  | Number of test cases applicable for FR2 |  | Number of test cases applicable for FR1 and FR2
|  |  | Overall | Completed | Overall | Completed | Overall | Completed | Overall | Completed
| Idle Mode Protocol Test Cases (TS 38.523-1, TS 38.523-2) | SA Option 2 (SA NR) | 60 | 60 | 60 | 60 | 60 | 24 | 0 | 0
NSA Option 3 (EN-DC)
SA Option 5
NSA Option 4 (NE-DC)
NSA Option 7 (NGEN-DC)

## Protocol Idle Mode
WP Title: | Idle Mode Protocol Test Cases (TS 38.523-1, TS 38.523-2) | [10 empty] | WP item applicability | [10 empty] | End of work plan columns. Note! Do not remove this column.
RAN-CN interface options dependency
WP Scope: | This work plan section covers the Idle mode protocol test cases for SA option 2. | [10 empty] | 5GC/NR |  |  |  | 5GC/LTE | EPC/LTE |  |  |  | 5GC/NR master | 5GC / LTE master
WP Resp: | Yogesh Tugnawat, Qualcomm |  |  |  | yogesht@qti.qualcomm.com
TS Resp: | Stoyan Baev, Samsung |  |  |  | stoyan.baev@partner.samsung.com | [6 empty] | SA |  |  |  |  | NSA
[12 empty] | Opt.2 |  |  |  | Opt.5 | Opt.3 |  |  |  | Opt.4 | Opt.7
WP Item ID | Is test case | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | 1st Target | FR1 | FR2 | FR1+FR2 |  | 1st Target | FR1 | FR2 | FR1+FR2
[11 empty] | Overall |  | 94.63%
[13 empty] | 100% | 89.52%
Phase 1
[11 empty] | Phase 2 |  | 100% | 100%
Phase 3
[11 empty] | Phase 4 |  | 100% | 100%
[11 empty] | Phase 5 |  | 100% | 100%
[11 empty] | Phase 6 |  | 100% | 100%
[11 empty] | Phase 7 |  | 100% | 100%
[11 empty] | Phase 8 |  | 100% | 100%
Phase 9
Phase 10
[11 empty] | Phase 11 |  | 100% | 100%
[11 empty] | Phase 12 |  | 100% | 83.08%
Phase 13
Phase 14
[7 empty] | Overall #WP items: Phase 1 #WP items: Phase 2 #WP items: Phase 3 #WP items: Phase 4 #WP items: Phase 5 #WP items: Phase 6 #WP items: Phase 7 #WP items: Phase 8 #WP items: Phase 9 #WP items: Phase 10 #WP items: Phase 11 #WP items: Phase 12 #WP items: Phase 13 #WP items: Phase 14 #WP items: | [5 empty] | 60 0 5 0 4 2 3 5 4 0 0 1 36 0 0 | 66 0 5 0 4 2 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [11 empty] | Phase number (1,2 etc) and completion (%) per option
NG-RAN Only PLMN Selection
|  | 38.523-1 | 6 | Idle mode and RRC Inactive state operations | [5 empty] | 0
|  | 38.523-1 | 6.1 | NR idle mode operations | [5 empty] | 0
|  | 38.523-1 | 6.1.1 | NG-RAN Only PLMN Selection
1 | Y | 38.523-1 | 6.1.1.1 | PLMN selection of RPLMN, HPLMN/EHPLMN, UPLMN and OPLMN / Automatic mode | Editor's note: 1 **** TP: [] Editor's note: UE in Automatic network selection mode and RPLMN, HPLMN, UPLMN and OPLMN NR cells available and UE is fitted with a USIM indicating RPLMN should be selected WITH: UE is switched on or return to coverage WHEN: UE selects a cell of the RPLMN and UE attempts Registration on the selected cell THEN: **** TP2: [TS 23,122:4.4.3.1, 4.4.3.1.1 and 4.4.3.3] WITH: UE camped on an NG-RAN VPLMN cell and cells of a higher priority NG-RAN PLMN available WHEN: higher priority PLMN search timer T expires THEN: UE selects and camps on a cell of the highest priority PLMN and UE attempts Registration with mobility on the selected cell **** TP3: [TS 23,122:4.4.3.1, 4.4.3.1.1 and 4.4.3.3] WITH: UE in Automatic network selection mode and HPLMN, UPLMN and OPLMN NG-RAN cells available and UE is fitted with a USIM with Access Technology data files for each PLMN and there are no equivalent HPLMNs defined WHEN: UE is switched on or return to coverage THEN: UE selects a cell of the highest priority PLMN and UE attempts Registration with mobility on the selected cell **** TP4: [TS 23,122:4.4.3.1, 4.4.3.1.1 and 4.4.3.3] WITH: UE camped on an NG-RAN VPLMN cell and cells of a NG-RAN HPLMN available WHEN: Higher priority PLMN search timer T expires THEN: UE selects and camps on a cell of HPLMN and UE attempts Registration on the selected cell | Qualcomm | Opt 2: RAN5#92 (Aug-21) | R5-190751 R5-191663 R5-201206 R5-202593 R5-203363 |  | 1 | 95% | 12 | 100% | 90% |  |  | 1 |  |  |  | 1 | 1
2 | Y | 38.523-1 | 6.1.1.2 | PLMN selection of "Other PLMN/access technology combinations" / Automatic mode | **** TP1: [TS 23,122:4.4.3.1.1] WITH: UE in Automatic network selection mode and EHPLMN, UPLMN and OPLMN/access technology combinations cells available and UE is fitted with a USIM with Access Technology data files for each PLMN WHEN: UE is switched on or return to coverage THEN: UE selects a cell of the EHPLMN and UE attempts a Registration on the selected cell **** TP2: [TS 23,122:4.4.3.1.1] WITH: UE in Automatic network selection mode and UPLMN, OPLMN and other PLMN/access technology combinations cells available and UE is fitted with a USIM with Access Technology data files for each PLMN WHEN: UE is switched on or return to coverage THEN: UE selects a cell of the UPLMN and UE attempts a Registration on the selected cell **** TP3: [TS 23,122:4.4.3.1.1] WITH: UE in Automatic network selection mode and OPLMN and other PLMN/access technology combinations cells available and UE is fitted with a USIM with Access Technology data files for each PLMN WHEN: UE is switched on or return to coverage THEN: UE selects a cell of the OPLMN and UE attempts a Registration on the selected cell **** TP4: [TS 23,122:4.4.3.1.1] WITH: UE in Automatic network selection mode and other PLMN/access technology combinations cells not belonging to any of EHPLMN, UPLMN or OPLMN available WHEN: UE is switched on or return to coverage THEN: UE selects a cell of other PLMN/access technology combinations and UE attempts a Registration on the selected cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-190736 R5-192757 R5-201125 R5-204403 |  | 1 | 95% | 12 | 100% | 90% |  |  | 1 |  |  |  | 1 | 1
3 | Y | 38.523-1 | 6.1.1.3 | Cell reselection of ePLMN in manual mode | **** TP1: [TS 23,122:4.4.3.1.2] WITH: UE camped normally on a cell and network has downloaded a list of equivalent PLMNs during the Registration procedure WHEN: Higher ranked cell is a cell of a PLMN in the downloaded equivalent PLMN list THEN: UE reselects to the equivalent PLMN cell **** TP2: [TS 23,122:4.4.3.1.2] WITH: UE camped normally on a cell and network has downloaded a list of equivalent PLMNs during Registration procedure for mobility WHEN: Highest ranked cell is a cell of a PLMN not in the downloaded equivalent PLMN list THEN: UE does not reselect to the cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-190737 R5-192758 R5-196598 R5-200338 R5-201477 R5-211329 |  | 1 | 95% | 12 | 100% | 90% |  |  | 1 |  |  |  | 1 | 1
4 | Y | 38.523-1 | 6.1.1.4 | PLMN selection in shared network environment / Automatic mode | **** TP1: [TS 38,304:5.1.1.2; TS 23,122:4.4.3 and 4.4.3.1.1; TS 38,331:5.3.3.4; TS 24,501:5.3.1.1] WITH: The UE is in automatic network selection mode and there is a suitable cell with multiple PLMN identities among which the HPLMN but not the registered PLMN WHEN: the UE is switched on THEN: the UE attaches to the HPLMN on the shared cell **** TP2: [TS 38,304:5.1.1.2; TS 23,122:4.4.3 and 4.4.3.1.1; TS 38,331:5.3.3.4; TS 24,501:5.3.1.1] WITH: the UE in automatic network selection mode and there is a suitable cell with multiple PLMN identities among which the registered PLMN WHEN: the UE returns to coverage THEN: the UE performs a registration procedure due to mobility to the registered PLMN on the shared cell | Huawei,Hisilicon | Opt 2: RAN5#86 (Feb-20) | R5-190738 R5-192768 R5-201126 R5-203481 |  | 1 | 100% | 6 | 100% | 100% |  |  | 1 |  |  |  | 1 | 1
5 | Y | 38.523-1 | 6.1.1.5 | PLMN selection of RPLMN, HPLMN/EHPLMN, UPLMN and OPLMN / Automatic mode / User reselection | **** TP1: [TS 23,122:4.4.3.2 and 4.4.3.2.1] WITH: UE in Automatic network selection mode registered to UPLMN and RPLMN, UPLMN and OPLMN NG-RAN cells available WHEN: UE is requested to initiate reselection and registration onto an available PLMN THEN: UE reselects to the cell which belongs to higher priority OPLMN **** TP2: [TS 23,122:4.4.3.2 and 4.4.3.2.1] WITH: UE in Automatic network selection mode registered to OPLMN and only RPLMN NG-RAN cells available WHEN: UE is requested to initiate reselection and registration onto an available PLMN THEN: UE remains on the current cell which belongs to RPLMN. **** TP3: [TS 23,122:4.4.3.2 and 4.4.3.2.1] WITH: UE in Automatic network selection mode registered to OPLMN and RPLMN, UPLMN and OPLMN NG-RAN cells available WHEN: UE is requested to initiate reselection and registration onto an available PLMN THEN: UE reselects to the cell which belongs to UPLMN **** TP4: [TS 23,122:4.4.3.2 and 4.4.3.2.1] WITH: UE in Automatic network selection mode registered to UPLMN and RPLMN, UPLMN, OPLMN and HPLMN NG-RAN cells available WHEN: UE is requested to initiate reselection and registration onto an available PLMN THEN: UE reselects to the cell which belongs to HPLMN | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-190739 R5-192759 R5-201127 R5-202594 R5-203367 |  | 1 | 95% | 12 | 100% | 90% |  |  | 1 |  |  |  | 1 | 1
6 | Y | 38.523-1 | 6.1.1.6 | PLMN selection / Periodic reselection / MinimumPeriodicSearchTimer | **** TP1: [TS 23,122:4.4.3.1 and 4.4.3.3.1] WITH: UE configured with “MinimumPeriodicSearchTimer“ WHEN: UE camps on an NG-RAN VPLMN cell upon switch on and cells of a higher priority NG-RAN PLMN available THEN: the MS shall make the first attempt to access the HPLMN or an EHPLMN or higher priority PLMN after a period of at least 2 minutes **** TP2: [TS 23,122:4.4.3.1 and 4.4.3.3.1] WITH: UE configured with “MinimumPeriodicSearchTimer“ , having made first attempt to higher priority PLMN and camped on an NG-RAN VPLMN cell and cells of a higher priority NG-RAN PLMN available WHEN: the higher priority PLMN search timer T stored in the USIM or the default value for T is less than the MinimumPeriodicSearchTimer THEN: UE shall not use a value for T that is less than the MinimumPeriodicSearchTimer and selects and camps on a cell of the highest priority PLMN and attempts a location registration on the selected cell upon expiry of MinimumPeriodicSearchTimer | Qualcomm | Opt 2: RAN5#86 (Feb-20) | R5-190671 R5-191859 R5-196156 R5-200148 R5-204414 R5-210401 R5-210628 |  | 1 | 100% | 6 | 100% | 100%
7 | Y | 38.523-1 | 6.1.1.7 | PLMN selection of RPLMN or (E)HPLMN; Automatic mode | **** TP1: [TS 38,304:5.1.1.2; TS 23,122:1.2, 4.4.3.1 and 4.4.3.1.1] WITH: UE in Automatic network selection mode and RPLMN, EHPLMN and HPLMN cells available and UE is fitted with a USIM containing the EHPLMN list and the USIM indicates RPLMN or (E)HPLMN should be selected WHEN: UE is switched on THEN: UE selects a cell of the RPLMN or EHPLMN **** TP2: [TS 38,304:5.1.1.2; TS 23,122:1.2, 4.4.3.1 and 4.4.3.1.1] WITH: UE in Automatic network selection mode and RPLMN, HPLMN and VPLMN cells available and UE is fitted with a USIM not containing or containing empty EHPLMN list and the USIM indicates RPLMN or (E)HPLMN should be selected WHEN: UE is switched on THEN: UE selects a cell of the RPLMN or HPLMN | Mediatek | Opt 2: RAN5#88 (Aug-20) | R5-187686 R5-190754 R5-192750 R5-195947 R5-198880 R5-204404 R5-204414 |  | 1 | 100% | 8 | 100% | 100%
8 | Y | 38.523-1 | 6.1.1.8 | PLMN selection of RPLMN or (E)HPLMN; Manual mode | **** TP1: [TS 38,304:5.1.1.2; TS 23,122:1.2, 4.4.3.1 and 4.4.3.1.1] WITH: UE in Manual network selection mode and EHPLMN and HPLMN cells available and (E)RPLMN cell is not available and UE is fitted with a USIM containing the EHPLMN list and the UE supports the exception to manual mode selection mode WHEN: UE is switched on THEN: UE selects a cell of the highest priority EHPLMN **** TP2: [TS 38,304:5.1.1.2; TS 23,122:1.2, 4.4.3.1 and 4.4.3.1.1] WITH: UE in Manual network selection mode and HPLMN and VPLMN cells available and (E)RPLMN cell is not available and UE is fitted with a USIM not containing or containing empty EHPLMN list and the UE supports the exception to manual mode selection mode WHEN: UE is switched on THEN: UE selects a cell of the HPLMN | Mediatek | Opt 2: RAN5#88 (Aug-20) | R5-187778 R5-190755 R5-192751 R5-196353 R5-198880 R5-204414 |  | 1 | 100% | 8 | 100% | 100%
62 |  | 38.523-1 | 6.1.1.1 to 6.1.1.8 |  | Define FR2 power levels for test cases 6.1.1.1 to 6.1.1.8 | See above | Opt 2: RAN5#92 (Aug-21) | R5-187778 R5-190755 R5-192751 |  | 0.4 | 0% | 12 |  | 0%
NG-RAN Only Cell Selection & Cell Reselection
|  | 38.523-1 | 6.1.2 | NG-RAN Only Cell Selection
9 | Y | 38.523-1 | 6.1.2.1 | Cell Selection/Qrxlevmin & Cell Reselection (Intra NR) | **** TP1: [TS 38.300:9.2.1.1; TS 38,304:4.1 , 4.5 , 5.2.1, 5.2.3.1 , 5.2.3.2] WITH: UE in NR RRC_IDLE state WHEN: a cell fulfils all requirements for a suitable cell except the cell selection criteria which are not fulfilled (Srxlex<0) THEN: the UE does not consider the cell suitable and no camping on this cell can take place **** TP2: [TS 38.300:9.2.1.1; TS 38,304:4.1 , 4.5 , 5.2.1, 5.2.3.1 , 5.2.3.2] WITH: UE in NR RRC_IDLE state WHEN: a cell fulfils all requirements for a suitable cell including the cell selection criteria for a cell which are also fulfilled (Srxlev>0 AND Squal>0 THEN: the UE considers the cell suitable and camps on it **** TP3: [TS 38,304:5.2.4.6] WITH: UE in NR RRC_IDLE state WHEN: UE detects the cell ranked as the best cell THEN: UE reselects the new cell **** TP4: [TS 38,304:4.5 , 5.2.3.2 , 5.3.1] WITH: UE in NR RRC_IDLE state WHEN: a cell fulfills cell selection criteria but trackingAreaCode is not provided for that PLMN THEN: the UE considers the cell as barred and no camping on this cell can take place | Huawei,Hisilicon | Opt 2: RAN5#82 (Feb-19) | R5-190740 R5-192754 R5-197017 R5-197019 R5-199014 R5-200675 R5-202537 |  | 1 | 100% | 2 | 100% | 100%
10 | Y | 38.523-1 | 6.1.2.2 | Cell Selection / Qqualmin/Intra NR / Serving cell becomes non-suitable (Srxlev > 0, Squal < 0) | **** TP1: [TS 38,3:9.2.1.1; TS 38,304:4.1 , 4.5 , 5.2.1,5.2.3.1 , 5.2.3.2] WITH: UE in NR RRC_IDLE state WHEN: a cell fulfils all requirements for a suitable cell except the cell selection criteria which are not fulfilled (Srxlev>0 AND Squal<0) THEN: the UE does not consider the cell suitable and no camping on this cell can take place **** TP2: [TS 38,3:9.2.1.1; TS 38,304:4.1 ,4.5 , 5.2.1,5.2.3.1 , 5.2.3.2] WITH: UE in NR RRC_IDLE state WHEN: a cell fulfils all requirements for a suitable cell including the cell selection criteria for a cell which are also fulfilled (Srxlev>0 AND Squal>0) THEN: the UE considers the cell suitable and camps on it **** TP3: [TS 38,304:5.3.1 , 5.2.4.6] WITH: UE in NR RRC_IDLE state WHEN: the serving cell becomes non-suitable (Srxlev > 0 and Squal < 0)and there is a suitable neighbour cell (Srxlev > 0 and Squal > 0) THEN: UE selects the suitable neighbour cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-190741 R5-192749 R5-196217 R5-201440 R5-206318 R5-212411 |  | 1 | 95% | 12 | 100% | 90%
11 | Y | 38.523-1 | 6.1.2.3 | Cell selection / Intra NR/ Serving cell becomes non-suitable (S<0, MIB Indicated barred) | **** TP1: [TS 38,304:4.1 , 4.5 , 5.2.1, 5.2.3.1 , 5.3.1 , 5.2.4.6; TS 38,3:9.2.1.1] WITH: UE in NR RRC_IDLE state WHEN: the serving cell becomes non-suitable (S<0)and there is a suitable neighbour cell (S>0) THEN: UE selects the suitable neighbour cell **** TP2: [TS 38,304:5.2.4.6 , cl 5.3.1] WITH: UE in NR RRC_IDLE state WHEN: the serving cell becomes barred and there is a suitable neighbour cell THEN: UE selects the suitable neighbour cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-190742 R5-192756 R5-201228 |  | 1 | 95% | 12 | 100% | 90%
12 | Y | 38.523-1 | 6.1.2.4 | Cell Reselection for interband operation | **** TP1: [TS 38,304:5.2.4.1 , 52.4.2 , 5.2.4.6] WITH: UE in NR RRC_IDLE state WHEN: UE detects the cell re-selection criteria are met for the cell on the different frequency band THEN: UE reselects the new cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-190743 R5-191426 R5-201113 |  | 1 | 95% | 12 | 100% | 90%
13 | Y | 38.523-1 | 6.1.2.5 | Cell reselection for interband operation using Pcompensation / Between FDD and TDD | **** TP1: [TS 38,304:5.2.3.1 , 5.2.4.1 , 5.2.4.2 , 5.2.4.6] WITH: UE in NR RRC_IDLE state on a FDD Band WHEN: UE detects the re-selection criteria using Pcompensation is met for the cell on a TDD band THEN: UE reselects to the new cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-190744 R5-191427 R5-201114 R5-201499 R5-211377 |  | 1 | 95% | 12 | 100% | 90%
14 |  | 38.523-1 | 6.1.2.6 | Void | FFS - No test purpose details specified yet. |  |  | R5-212764 |  | 0 |  | 6
15 | Y | 38.523-1 | 6.1.2.7 | Cell reselection / Equivalent PLMN | **** TP1: [TS 23,122:4.4.3; TS 38,304:5.2.4.1] WITH: UE camped normally on a cell and network has downloaded a list of equivalent PLMNs during the Registration procedure WHEN: a suitable neighbour cell on an equivalent PLMN becomes better ranked than the suitable Serving cell THEN: UE reselects to this equivalent PLMN cell **** TP2: [TS 23,122:4.4.3; TS 38,304:5.2.4.1] WITH: UE camped normally on a cell and network has downloaded a list of equivalent PLMNs during the Registration procedure WHEN: the Serving cell becomes unsuitable due to S<0 and a suitable cell exists on an equivalent PLMN THEN: UE reselects to this equivalent PLMN cell **** TP3: [TS 23,122:4.4.3; TS 38,304:5.2.4.1] WITH: UE camped normally on a cell and network has downloaded a list of equivalent PLMNs during the Registration procedure WHEN: the UE evaluates cells for reselection THEN: UE ignores suitable cells for which the UE has no reselection priority provided | Qualcomm | Opt 2: RAN5#92 (Aug-21) | R5-190750 R5-192285 R5-201793 |  | 1 | 95% | 12 | 100% | 90%
16 | Y | 38.523-1 | 6.1.2.8 | Cell reselection / Equivalent PLMN / Single Frequency operation | **** TP1: [TS 23,122:4.4.3; TS 38,304:5.2.4.1] WITH: UE camped normally on a cell and network has downloaded a list of equivalent PLMNs during the Registration procedure WHEN: a suitable neighbour cell on an equivalent PLMN becomes better ranked than the suitable Serving cell THEN: UE reselects to this equivalent PLMN cell **** TP2: [TS 23,122:4.4.3; TS 38,304:5.2.4.1] WITH: UE camped normally on a cell and network has downloaded a list of equivalent PLMNs during the Registration procedure WHEN: the Serving cell becomes unsuitable due to S<0 and a suitable cell exists on an equivalent PLMN THEN: UE reselects to this equivalent PLMN cell | Keysight | Opt 2: RAN5#92 (Aug-21) | R5-192767 R5-196610 R5-201793 R5-211330 |  | 1 | 95% | 12 | 100% | 90%
17 | Y | 38.523-1 | 6.1.2.9 | Cell reselection using Qhyst, Qoffset and Treselection | **** TP1: [TS 38,304:5.2.4.6] WITH: UE in NR RRC_IDLE state, and the UE is not in high mobility state WHEN: Qhyst is non-zero or its value changes in system information THEN: UE reselects the highest ranked cell taking the actual Qhyst value into account **** TP2: [TS 38,304:5.2.4.6] WITH: UE in NR RRC_IDLE state, and the UE is not in high mobility WHEN: cell reselection criteria are fulfilled during a time interval Treselection THEN: UE reselects the highest ranked cell after the Treselection interval expires **** TP3: [TS 38,304:5.2.4.6] WITH: UE in NR RRC_IDLE state, and the UE is not in high mobility WHEN: Qoffset is non-zero or its value changes in system information THEN: UE reselects the highest ranked cell taking the actual Qoffset value into account | Huawei,Hisilicon | Opt 2: RAN5#82 (Feb-19) | R5-190745 R5-192760 R5-197017 R5-201209 R5-204380 R5-203810 R5-204414 R5-205365 R5-210630 |  | 1 | 100% | 2 | 100% | 100%
18 |  | 38.523-1 | 6.1.2.10 | Void | FFS - No test purpose details specified yet. | Huawei,Hisilicon |  | R5-212764 |  | 0 |  | 6
19 | Y | 38.523-1 | 6.1.2.11 | Area Specific SIBs using systemInformationAreaID | **** TP1: [TS 38,331:5.2.2.1] WITH: UE is in NR RRC_IDLE state WHEN: SIB1 does not include si-RequestConfig and si-BroadcastStatus set to notBroadcasting THEN: UE sends RRCSystemInfoRequest message and acquires the necessary SIBs **** TP2: [TS 38,331:5.2.2.1] WITH: UE in NR_RRC Idle State WHEN: UE reselects to neighbor cell with same systemInformationAreaID and SIB1 does not include si-RequestConfig and si-BroadcastStatus set to notBroadcasting THEN: UE applies system information parameters of previous cell for reselection purposes | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-198874 R5-201006 R5-202603 R5-203648 |  | 1 | 95% | 12 | 100% | 90%
20 | Y | 38.523-1 | 6.1.2.12 | Cell reselection using cell status and cell reservations / cellReservedForOtherUse | **** TP1: [TS 38,304:R2-1813084] WITH: UE camped normally in state NR RRC_IDLE WHEN: A higher ranked cell is found with cell status "true" for other use THEN: UE does not attempt to reselect to the higher ranked cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-194823 |  | 1 | 95% | 12 | 100% | 90%
21 | Y | 38.523-1 | 6.1.2.13 | Cell reselection using cell status and cell reservations / Access Identity 0, 1, 2 and 12 to 14 – cellReservedForOperatorUse | **** TP1: [TS 38,304:5.3.1] WITH: UE camped normally in state NR RRC_IDLE and UE fitted with a USIM with at least one of the following Access Identities set: 0,1,2,12,13,14 WHEN: a higher ranked cell is found "reserved" for Operator use THEN: UE does not attempt to reselect to the higher ranked cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-195244 R5-197020 R5-204416 R5-205366 |  | 1 | 95% | 12 | 100% | 90%
22 | Y | 38.523-1 | 6.1.2.14 | Cell reselection using cell status and cell reservations / Access Identity 11 or 15 - cellReservedForOperatorUse | **** TP1: [TS 38,304:5.3.1] WITH: UE camped normally in state NR RRC_IDLE operating in their HPLMN/EHPLMN and fitted with a USIM with Access Identity 11 or 15 WHEN: a higher ranked cell is found "reserved" for Operator use THEN: UE re-selects to the higher ranked cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-195245 R5-197839 R5-211173 |  | 1 | 95% | 12 | 100% | 90%
23 | Y | 38.523-1 | 6.1.2.15 | Cell reselection in shared network environment | **** TP1: [TS 23,122:4.4.3; TS 24,501:5.3.1.1; TS 38,331:5.3.3.1] WITH: the UE is in NR RRC_Idle and registered on the HPLMN WHEN: a cell of a different PLMN but shared with the HPLMN becomes highest ranked cell THEN: the UE reselects the cell shared with the HPLMN | Huawei,Hisilicon | Opt 2: RAN5#82 (Feb-19) | R5-192283 R5-197017 R5-201477 |  | 1 | 100% | 2 | 100% | 100%
24 | Y | 38.523-1 | 6.1.2.16 | Inter-frequency cell reselection (equal priority) | **** TP1: [TS 38,304:5.2.4.6] WITH: UE in NR RRC_IDLE state WHEN: UE detects both intra-frequency and equal priority inter-frequency neigbour cells and the inter-frequency cell is the highest ranked cell THEN: UE reselects the inter-frequency cell | Keysight | Opt 2: RAN5#92 (Aug-21) | R5-199028 |  | 1 | 95% | 12 | 100% | 90%
25 | Y | 38.523-1 | 6.1.2.17 | Cell reselection / Cell-specific reselection parameters provided by the network in a neighbouring cell list | **** TP1: [TS 38,304:5.2.4.6] WITH: the UE is in NR RRC_IDLE and SystemInformationBlockType3 contain a cell-specific Qoffset for a neighbour intra frequency cell WHEN: the neighbour cell has lower power than the serving cell but it is higher ranked due to the cell-specific Qoffset THEN: the UE reselects the neighbour cell with cell-specific Qoffset **** TP2: [TS 38,304:5.2.4.6] WITH: the UE is in RRC_IDLE and SystemInformationBlockType4 contain a black listed cell WHEN: a black listed inter-freq cell becomes higher ranked than the serving cell THEN: the UE remains camped on the serving cel1 | Huawei,Hisilicon | Opt 2: RAN5#82 (Feb-19) | R5-192284 R5-197017 |  | 1 | 100% | 2 | 100% | 100%
26 | Y | 38.523-1 | 6.1.2.18 | Cell reselection, Sintrasearch, Snonintrasearch | **** TP1: [TS 38,304:5.2.4.1 , 5.2.4.5 , 5.2.4.6; TS <TS#2>:FFS; TS <TS#n>:FFS] WITH: UE in NR RRC_IDLE state, and the UE is not in high mobility state WHEN: Sintrasearch is non-zero in system information THEN: UE perform measurement and reselects the highest ranked cell upon Srxlev < Sintrasearch **** TP2: [TS 38,304:5.2.4.1 , 5.2.4.5 , 5.2.4.6; TS <TS#2>:FFS; TS <TS#n>:FFS] WITH: UE in NR RRC_IDLE state, and the UE is not in high mobility state WHEN: Snonintrasearch is non-zero in system information THEN: UE perform measurement and reselects the cell which belong to the equal priority frequency cell upon Srxlev < Snonintrasearch **** TP3: [TS 38,304:5.2.4.1 , 5.2.4.5 , 5.2.4.6; TS <TS#2>:FFS; TS <TS#n>:FFS] WITH: UE in E-UTRA RRC_IDLE state, and the UE is not in high mobility state WHEN: Snonintrasearch is non-zero in system information THEN: UE perform measurement and reselects the cell which belong to the high priority frequency cell upon Srxlev > Snonintrasearch | Qualcomm | Opt 2: RAN5#92 (Aug-21) | R5-197203 R5-201115 R5-201340 R5-206312 |  | 1 | 95% | 12 | 100% | 90%
27 | Y | 38.523-1 | 6.1.2.19 | Speed-dependent cell reselection | **** TP1: [TS 38,304:5.2.4.3] WITH: UE in NR RRC_IDLE state and in high mobility state WHEN: UE detects the cell ranked as the best cell taking into account scaling factor THEN: UE reselects to the new cell **** TP2: [TS 38,304:5.2.4.3] WITH: UE in NR RRC_IDLE state and in medium mobility state WHEN: UE detects the cell ranked as the best cell taking into account scaling factor THEN: UE reselects to the new cell | Qualcomm | Opt 2: RAN5#92 (Aug-21) | R5-190672 R5-192282 R5-200622 R5-201341 R5-204405 R5-211377 |  | 1 | 95% | 12 | 100% | 90%
28 | Y | 38.523-1 | 6.1.2.20 | Inter-frequency cell reselection according to cell reselection priority provided by SIBs | **** TP1: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_IDLE state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the equal priority frequency THEN: UE reselects the cell which belongs to the equal priority frequency **** TP2: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_IDLE state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the higher priority frequency THEN: UE reselects the cell which belongs to the higher priority frequency **** TP3: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_IDLE state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the lower priority frequency THEN: UE reselects the cell which belongs to the lower priority frequency | Huawei,Hisilicon | Opt 2: RAN5#82 (Feb-19) | R5-190746 R5-192761 R5-197017 R5-201208 |  | 1 | 100% | 2 | 100% | 100%
29 | Y | 38.523-1 | 6.1.2.21 | Cell reselection, SIntra SearchQ and SnonIntraSearchQ | **** TP1: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5, 5.2.4.6 ,5.2.4.7] WITH: UE in NR RRC_IDLE state, and the UE is not in high mobility state WHEN: UE receives non-zero SIntraSearchQ in system information THEN: UE perform measurement and reselects the highest ranked cell upon Squal < SIntraSearchQ **** TP2: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5, 5.2.4.6 ,5.2.4.7] WITH: UE in NR RRC_IDLE state, and the UE is not in high mobility state WHEN: UE receives non-zero SnonIntraSearchQ in system information THEN: UE perform measurement and reselects the cell which belong to the equal priority frequency cell upon Squal < SnonIntraSearchQ **** TP3: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5, 5.2.4.6 ,5.2.4.7] WITH: UE in E-UTRA RRC_IDLE state, and the UE is not in high mobility state WHEN: UE receives non-zero SnonIntraSearchQ in system information THEN: UE perform measurement and reselects the cell which belong to the high priority frequency cell upon Squal > SnonIntraSearchQ | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-190747 R5-191430 R5-196218 R5-201112 R5-203372 R5-206313 R5-211377 |  | 1 | 95% | 12 | 100% | 90%
30 | Y | 38.523-1 | 6.1.2.22 | Inter-frequency cell reselection based on common priority information with parameters ThreshX,HighQ, ThreshX,LowQ and ThreshServing,LowQ | **** TP1: [TS 38,304:5.2.4.5 and 5.2.4.7] WITH: UE in NR RRC_IDLE state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the higher priority frequency THEN: UE reselects the cell which belongs to the higher priority frequency **** TP2: [TS 38,304:5.2.4.5 and 5.2.4.7] WITH: UE in NR RRC_IDLE state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the lower priority frequency THEN: UE reselects the cell which belongs to the lower priority frequency | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-190748 R5-191431 R5-197193 R5-201128 R5-211377 |  | 1 | 95% | 12 | 100% | 90%
69 | Y | 38.523-1 | 6.1.2.23 | Cell reselection/ MFBI | **** TP0: [TS 38,304:5.2.4.2 , 5.2.4.6; TS 38,331:5.2.2.4.2] WITH: UE is switched off WHEN: UE is switched on a MFBI cell with the SIB1 of the first frequency band indicated in freqBandIndicator is not supported by UE and the second frequency band indicated in freqBandIndicator is supported by UE THEN: the UE selects the cell **** TP1: [TS 38,304:5.2.4.2 , 5.2.4.6; TS 38,331:5.2.2.4.2] WITH: UE in NR RRC_IDLE state WHEN: an equal priority NG-RAN Intra-frequency neighbouring cell which has been included in the frequencyBandList provided by the serving cell becomes available, and, is better ranked than the serving cell during a time interval TreselectionNR, and, more than 1 second has elapsed since the UE camped on the current serving cell THEN: the UE reselects the new cell **** TP2: [TS 38,304:5.2.4.2 , 5.2.4.5; TS 38,331:5.2.2.4.2] WITH: UE in NR RRC_IDLE state WHEN: an equal priority NG-RAN Inter-frequency neighbouring cell which has been included in the frequencyBandList provided by the serving cell becomes available, and, is better ranked than the serving cell during a time interval TreselectionNR, and, more than 1 second has elapsed since the UE camped on the current serving cell THEN: the UE reselects the new cell **** TP3: [TS 38,304:5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_IDLE state WHEN: an equal priority NG-RAN Inter-band neighbouring cell which has been included in the frequencyBandList provided by the serving cell becomes available, and, is better ranked than the serving cell during a time interval TreselectionNR, and, more than 1 second has elapsed since the UE camped on the current serving cell THEN: the UE reselects the new cell **** TP<Add test case note here if needed>: [] WITH: <Add TP note here if needed> WHEN: UE is switched off THEN: FFS | CATT | Opt 2: RAN5#86 (Feb-20) | R5-197199 R5-199072 R5-201223 R5-202606 R5-203373 R5-212763 |  | 1 | 100% | 6 | 100% | 100%
63 |  | 38.523-1 | 6.1.2.1 to 6.1.2.22 |  | Define FR2 power levels for test cases 6.1.2.1 to 6.1.2.22 | See above | Opt 2: RAN5#92 (Aug-21) |  |  | 1.5 | 0% | 12 |  | 0%
Inter-RAT PLMN Selection (E-UTRAN , NG-RAN)
|  | 38.523-1 | 6.2 | Multi-mode environment (NG-RAN , E-UTRAN) | [5 empty] | 0
|  | 38.523-1 | 6.2.1 | Inter-RAT PLMN Selection
31 | Y | 38.523-1 | 6.2.1.1 | Inter-RAT PLMN Selection / Selection of correct RAT for OPLMN / Automatic mode | **** TP1: [TS 23,122:4.4.3.1 and 4.4.3.1.1] WITH: UE pre-set in Automatic network selection mode WHEN: UE is switched on and there are suitable NG-RAN and E-UTRAN cells some on the OPLMN list and some not on the OPLMN list, none of them being part of the RPLMN THEN: UE selects the highest priority OPLMN and RAT combination, attaches on the selected cell **** TP2: [TS 23,122:4.4.3.1 and 4.4.3.1.1] WITH: UE in Automatic network selection mode WHEN: UE returns to coverage and there are suitable NG-RAN and E-UTRAN cells some on the OPLMN list and some not on the OPLMN list , none of them being part of the RPLMN THEN: UE selects the highest priority OPLMN and RAT combination, attaches on the selected cell | Mediatek | Opt 2: RAN5#88 (Aug-20) | R5-190756 R5-192763 R5-198881 R5-203374 R5-204414 R5-211378 |  | 1 | 100% | 8 | 100% | 100%
32 | Y | 38.523-1 | 6.2.1.2 | Inter-RAT PLMN Selection / Selection of correct RAT for UPLMN / Automatic mode | **** TP1: [TS 23,122:4.4.3.1 and 4.4.3.1.1] WITH: UE in Automatic network selection mode and UPLMN and OPLMN cells available on NG-RAN and E-UTRAN WHEN: UE is switched on THEN: UE selects a the highest priority UPLMN and RAT combination and UE attempts to attach on the selected cell **** TP2: [TS 23,122:4.4.3.1 and 4.4.3.1.1] WITH: UE in Automatic network selection mode and UPLMN and OPLMN cells available on NG-RAN and E-UTRAN WHEN: UE returns to coverage THEN: UE selects a the highest priority VPLMN and RAT combination and UE attempts to attach on the selected cell | Mediatek | Opt 2: RAN5#87 (May-20) | R5-190785 R5-192762 R5-198882 R5-202178 R5-204414 R5-211378 R5-211022 R5-213457 |  | 1 | 100% | 7 | 100% | 100%
33 | Y | 38.523-1 | 6.2.1.3 | Inter-RAT PLMN Selection / Selection of correct PLMN and RAT in shared network environment / Automatic mode | **** TP1: [TS 23,122:4.4.3, 4.4.3.1 and 4.4.3.1.1] WITH: UE in Automatic network selection mode and shared OPLMN cells available on NG-RAN & E-UTRAN WHEN: UE is switched on THEN: UE selects a the highest priority OPLMN and RAT combination and UE attempts to register on the selected cell and PLMN **** TP2: [TS 23,122:4.4.3, 4.4.3.1 and 4.4.3.1.1] WITH: UE in Automatic network selection mode and shared OPLMN cells available on NG-RAN and E-UTRAN WHEN: UE returns to coverage THEN: UE selects a the highest priority OPLMN and RAT combination and UE attempts to attach on the selected cell and PLMN | Mediatek | Opt 2: RAN5#87 (May-20) | R5-190757 R5-192764 R5-198882 R5-202185 R5-204414 R5-211378 R5-211022 R5-213457 |  | 1 | 100% | 7 | 100% | 100%
34 | Y | 38.523-1 | 6.2.1.4 | Inter-RAT PLMN Selection / Selection of correct RAT from the OPLMN list / Manual mode | **** TP1: [TS 23,122:4.4.3.1.2] WITH: UE in Manual network selection mode and OPLMN cells available on NG-RAN and E-UTRAN WHEN: the USER selects an OPLMN THEN: UE selects a the highest priority RAT for the OPLMN and UE attempts to attach on the selected cell and when successfully registered indicates the PLMN to the user **** TP2: [TS 23,122:4.4.3.1.2] WITH: UE in Manual network selection mode and OPLMN cells available on NG-RAN and E-UTRAN WHEN: the USER selects an OPLMN and RAT combination THEN: UE attempts to attach on the selected OPLMN and RAT combination and when successfully registered indicates the PLMN to the user | Mediatek | Opt 2: RAN5#87 (May-20) | R5-190758 R5-192765 R5-198882 R5-202205 R5-203375 R5-204414 R5-205856 |  | 1 | 100% | 7 | 100% | 100%
35 | Y | 38.523-1 | 6.2.1.5 | Inter-RAT Background HPLMN Search / Search for correct RAT for HPLMN / Automatic Mode | **** TP1: [TS 23,122:4.4.3.3.1; TS 24,501:4.8.2.2] WITH: UE in Automatic network selection mode is camped on a E-UTRAN VPLMN cell and HPLMN cell available on NG-RAN WHEN: higher priority PLMN search timer T expires THEN: UE detects NR Cell and registers on to NG-RAN cell **** TP2: [TS 23,122:4.4.3.3.1; TS 24,501:4.8.2.2] WITH: With the UE having received an "interworking without N26 not supported" indication from the network WHEN: UE attempts a PDU Session Establishment procedure to transfer PDN connection from S1 mode to N1 mode THEN: UE establishes PDU sessions corresponding to all existing PDN connections, if any, by initiating the PDU session establishment procedure with request type set to "initial reques"t | Mediatek | Opt 2: RAN5#88 (Aug-20) | R5-190759 R5-192766 R5-198881 R5-204406 R5-204414 |  | 1 | 100% | 8 | 100% | 100%
64 |  | 38.523-1 | 6.2.1.1 to 6.2.1.5 |  | Define FR2 power levels for test cases 6.2.1.1 to 6.1.1.5 | See above | Opt 2: RAN5#92 (Aug-21) |  |  | 0 | 0% | 12 |  | 0%
Inter-RAT Cell Selection
|  | 38.523-1 | 6.2.2 | Inter-RAT Cell Selection | [5 empty] | 0
37 | Y | 38.523-1 | 6.2.2.1 | Inter-RAT cell selection / From NR RRC_IDLE to EUTRA_Idle / Serving cell becomes non-suitable | **** TP1: [TS 38,304:5.2.1 , 5.2.3.1 , 5.2.3.2; TS 36,304:5.2.1,5.2.3.1 , 5.2.3.2; TS <TS#n>:FFS] WITH: UE in NR RRC_IDLE state WHEN: the serving cell becomes non-suitable and there is a suitable E-UTRA neighbour cell THEN: UE selects the suitable E-UTRA neighbour cell **** TP2: [TS 38,304:4.5 , 5.3.1; TS 36,304:5.2.1,5.2.3.1 , 5.2.3.2] WITH: UE in NR RRC_IDLE state WHEN: the serving cell becomes barred and there is a suitable E-UTRA neighbour cell THEN: UE selects the suitable E-UTRA neighbour cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-201471 R5-204412 R5-204015 |  | 1 | 95% | 12 | 100% | 90%
38 | Y | 38.523-1 | 6.2.2.2 | Inter-RAT cell selection / From E-UTRA_Idle to NR RRC_IDLE / Serving cell becomes non-suitable | **** TP1: [TS 38,304:5.2.1 , 5.2.3.1 , 5.2.3.2; TS 36,304:5.2.1,5.2.3.1 , 5.2.3.2] WITH: UE in E-UTRA RRC_IDLE state WHEN: the serving cell becomes non-suitable and there is a suitable NR neighbour cell THEN: UE selects the suitable NR neighbour cell **** TP2: [TS 38,304:4.5 , 5.3.1; TS 36,304:5.2.1,5.2.3.1 , 5.2.3.2] WITH: UE in E-UTRA RRC_IDLE state WHEN: the serving cell becomes barred and there is a suitable NR neighbour cell THEN: UE selects the suitable NR neighbour cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-202602 R5-204413 R5-204018 |  | 1 | 95% | 12 | 100% | 90%
65 |  | 38.523-1 | 6.2.2.1 to 6.2.2.2 |  | Define FR2 power levels for test cases 6.2.2.1 to 6.2.2.2 | See above | Opt 2: RAN5#92 (Aug-21) |  |  | 0.2 | 0% | 12 |  | 0%
Inter-RAT Cell Reselection
|  | 38.523-1 | 6.2.3 | Inter-RAT Cell Reselection
39 | Y | 38.523-1 | 6.2.3.1 | Inter-RAT cell reselection / From E-UTRA_Idle to NR RRC_IDLE (lower priority & higher priority, Srxlev based) | **** TP1: [TS 36,304:5.2.4.1. , 5.2.4.2 and 5.2.4.5] WITH: UE in E-UTRA_Idle state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the lower priority inter-RAT NR cell THEN: UE reselects the cell which belongs to the lower priority inter-RAT NR cell **** TP2: [TS 36,304:5.2.4.1. , 5.2.4.2 and 5.2.4.5] WITH: UE in E-UTRA_Idle state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the higher priority inter-RAT NR cell THEN: UE reselects the cell which belongs to the higher priority inter-RAT NR cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-197185 R5-201171 R5-201791 R5-204417 |  | 1 | 95% | 12 | 100% | 90%
40 | Y | 38.523-1 | 6.2.3.2 | Inter-RAT cell reselection / From E-UTRA_Idle to NR RRC_IDLE (lower priority & higher priority, Squal based) | **** TP1: [TS 36,304:5.2.4.1 , 5.2.4.2 and 5.2.4.5] WITH: UE in E-UTRA RRC_IDLE state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the lower priority inter-RAT NR cell THEN: UE reselects the cell which belongs to the lower priority inter-RAT NR cell **** TP2: [TS 36,304:5.2.4.1 , 5.2.4.2 and 5.2.4.5] WITH: UE in E-UTRA_Idle state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the higher priority inter-RAT NR cell THEN: UE reselects the cell which belongs to the higher priority inter-RAT NR cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-197186 R5-197840 R5-201129 R5-204417 R5-206265 R5-210631 |  | 1 | 95% | 12 | 100% | 90%
41 | Y | 38.523-1 | 6.2.3.3 | Inter-RAT cell reselection / From NR RRC_IDLE to E-UTRA_IDLE (lower priority & higher priority, Srxlev based) | **** TP1: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_IDLE state WHEN: UE detects the cell re-selection criteria are met for the neighbour cell which belongs to the higher priority E-UTRA frequency THEN: UE reselects to the E-UTRA cell **** TP2: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_IDLE state WHEN: UE detects the cell re-selection criteria are met for the neighbour cell which belongs to the lower priority E-UTRA frequency THEN: UE reselects to the E-UTRA cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-195243 R5-202595 |  | 1 | 95% | 12 | 100% | 90%
42 | Y | 38.523-1 | 6.2.3.4 | Inter-RAT cell reselection / From NR RRC_Idle to E-UTRA_IDLE (lower priority & higher priority, Squal based) | **** TP1: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_Idle state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the lower priority inter-RAT E-UTRA cell THEN: UE reselects the cell which belongs to the lower priority inter-RAT E-UTRA cell **** TP2: [TS 38,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_Idle state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the higher priority inter-RAT E-UTRA cell THEN: UE reselects the cell which belongs to the higher priority inter-RAT E-UTRA cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-197187 R5-197841 R5-201943 R5-204417 R5-210632 R5-213455 |  | 1 | 95% | 12 | 100% | 90%
43 | Y | 38.523-1 | 6.2.3.5 | Inter-RAT cell reselection/From NR RRC_IDLE to E-UTRA_Idle according to RAT priority provided by dedicated signalling (RRCRelease) | **** TP1: [TS 38,304:5.2.4.1 , 5.2.4.5; TS 38,331:5.3.8.3 , 5.3.8.4] WITH: UE in NR RRC_IDLE state having received an RRCRelease message including cellReselectionPriorities WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the higher priority RAT THEN: UE reselects the cell which belongs to the higher priority RAT **** TP2: [TS 38,304:5.2.4.1 , 5.2.4.5; TS 38,331:5.3.8.3 , 5.3.8.4] WITH: UE in NR RRC_IDLE state having received an RRCRelease message including a cellReselectionPriorities WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the lower priority RAT THEN: UE reselects the cell which belongs to the lower priority RAT **** TP3: [TS 38,304:5.2.4.1 , 5.2.4.5; TS 38,331:5.3.8.3 , 5.3.8.4] WITH: UE in NR RRC_IDLE state having received an RRCRelease message including a cellReselectionPriorities WHEN: T320 expires THEN: UE reselects a cell by applying the cellReselectionPriority broadcast in the system information **** TP4: [TS 38,304:5.2.4.1 , 5.2.4.5; TS 38,331:5.3.8.3 , 5.3.8.4] WITH: UE in NR RRC_IDLE state and reselection priorities have been provided in dedicated signalling WHEN: T320 has not expired THEN: The UE shall ignore all the priorities provided in system information, and not perform cell reselection evaluation for NR frequencies and E-UTRA frequencies for which the UE doesn’t have a priority provided | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-195247 R5-197842 R5-201130 R5-204417 |  | 1 | 95% | 12 | 100% | 90%
44 | Y | 38.523-1 | 6.2.3.6 | Inter-RAT cell reselection / From E-UTRA_Idle to NR RRC_IDLE according to RAT priority provided by dedicated signalling (RRConnRelease) | **** TP1: [TS 36,304:5.2.4.1; TS 38,304:5.2.4.1] WITH: UE in E-UTRA RRC_Idle state having received RRCConnectionRelease including IdleModeMobilityControlInfo containing cellReselectionPriority for NR cell WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the lower priority inter-RAT NR cell based on the configured RAT priority provided by dedicated signaling THEN: UE reselects the cell which belongs to the lower priority inter-RAT NR cell **** TP2: [TS 36,304:5.2.4.1; TS 38,304:5.2.4.1] WITH: UE in NR RRC_IDLE state having inherit RAT priority provided by dedicated signaling with the remaining validity time WHEN: UE discard the inherit RAT priority upon connection establishment THEN: UE reselects a cell by applying the cellReselectionPriority broadcast in the system information | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-197188 R5-197843 R5-201131 |  | 1 | 95% | 12 | 100% | 90%
45 | Y | 38.523-1 | 6.2.3.7 | Inter-RAT cell reselection/From NR RRC_IDLE to E-UTRA RRC_IDLE, Snonintrasearch | **** TP1: [TS 38,304:5.2.4.1, 5.2.4.2, 5.2.4.5] WITH: UE in NR RRC_IDLE state, and the UE is not in high mobility state WHEN: Snonintrasearch is non-zero in system information THEN: UE perform measurement and reselects the cell which belong to the high priority E-UTRA cell even if Srxlev > Snonintrasearch | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-195249 R5-198875 |  | 1 | 95% | 12 | 100% | 90%
61 | Y | 38.523-1 | 6.2.3.8 | Inter-RAT cell reselection/From E-UTRA RRC_IDLE to NR RRC_Idle, Snonintrasearch | **** TP1: [TS 36,304:5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in E-UTRA RRC_IDLE state, and the UE is not in high mobility state WHEN: Snonintrasearch is non-zero in system information THEN: UE perform measurement and reselects to cell which belongs to the high priority NR cell even if Srxlev > Snonintrasearch | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-197189 R5-201132 |  | 1 | 95% | 12 | 100% | 90%
46 | Y | 38.523-1 | 6.2.3.9 | Void | **** TP1: [TS 38,304:5.2.4.3] WITH: UE in NR RRC_IDLE state and in high mobility state WHEN: UE detects the E-UTRA cell ranked as the best cell taking into account scaling factor THEN: UE reselects to the new cell | Huawei,Hisilicon |  | R5-197190 R5-200175 R5-201344 R5-203377 R5-204417 R5-206317 R5-211381 | TC Voided as per RAN2 LS - R5-211277, in RAN5#90 | 0 |  | 6
70 | Y | 38.523-1 | 6.2.3.10 | Inter-RAT cell reselection / From E-UTRA_Idle to NR RRC_IDLE / schedulingInfoList-v12j0 | Editor's note: <Add test case note here if needed> **** TP1: [TS 36,331:5.2.3, 5.2.3a; TS 36,304:5.2.4.1, 5.2.4.2, 5.2.4.5; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: the UE is in E-UTRA IDLE state and SystemInformationBlockType24 scheduled by optional extended field schedulingInfoList-v12j0 in SystemInformationBlockType1 is broadcasted WHEN: UE detects higher priority NR cell as candidate for reselection THEN: UE reselects the NR cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-206315 |  | 1 | 95% | 12 | 100% | 90%
71 | Y | 38.523-1 | 6.2.3.11 | Inter-RAT cell reselection / From E-UTRA_Idle to NR RRC_IDLE / schedulingInfoListExt-r12 | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: the UE is in E-UTRA IDLE state and SystemInformationBlockType24 scheduled by optional extended field schedulingInfoListExt-r12 in SystemInformationBlockType1 is broadcasted WHEN: UE detects higher priority NR cell as candidate for reselection THEN: UE reselects the NR cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-206316 |  | 1 | 95% | 12 | 100% | 90%
66 |  | 38.523-1 | 6.2.3.1 to 6.2.3.11 |  | Define FR2 power levels for test cases 6.2.3.1 to 6.2.3.9 | See above | Opt 2: RAN5#92 (Aug-21) |  |  | 0.9 | 0% | 12 |  | 0%
Steering of Roaming
|  | 38.523-1 | 6.3 | 5GS Steering of Roaming | [5 empty] | 0
|  | 38.523-1 | 6.3.1 | Steering of Roaming
47 | Y | 38.523-1 | 6.3.1.1 | Steering of UE in roaming during registration/security check successful using List Type 1 | **** TP1: [TS 23,122:Annex C.2] WITH: UE being in automatic PLMN selection mode , current VPLMN not part of “PLMNs where registration was aborted due to SOR” List and not part of "User Controlled PLMN Selector with Access Technology" list and UE's USIM configured with indication that the UE is to receive Steering of Roaming information due to initial registration in a VPLMN WHEN: SOR Transparent container indicates ACK has been requested & List Type indicates PLMN ID and Access technology list in REGISTRATION ACCEPT and security check is successful THEN: UE sends ACK in REGISTRATION COMPLETE , waits for network release of the NAS signalling connection and selects higher priority PLMN | Qualcomm | Opt 2: RAN5#85 (Nov-19) | R5-190749 R5-191661 R5-198877 R5-202596 R5-204407 R5-206314 R5-211378 R5-211379 R5-213349 |  | 1 | 100% | 5 | 100% | 100%
48 | Y | 38.523-1 | 6.3.1.2 | Steering of UE in roaming during registration/security check successful but SOR Transparent container indicates ACK has been NOT been requested | **** TP1: [TS 23,122:Annex C.2; TS 24,501:4.4.4.2 , 5.5.1.2.4] WITH: UE being in automatic PLMN selection mode , current VPLMN not part of “PLMNs where registration was aborted due to SOR” List and not part of "User Controlled PLMN Selector with Access Technology" list and UE's USIM configured with indication that the UE is to receive Steering of Roaming information due to initial registration in a VPLMN WHEN: SOR Transparent container indicates ACK has NOT been requested & List Type indicates PLMN ID and Access technology list in REGISTRATION ACCEPT and security check is successful and if the UE has a list of available and allowable PLMNs in the area and based on this list the UE determines that there is a higher priority PLMN than the currently camped chosen VPLMN THEN: the UE shall send the REGISTRATION COMPLETE message to the serving AMF without including an SOR transparent container and then either releases N1 NAS Signaling connection locally and then attempt to obtain service on a higher priority PLMN or optionally wait for network release of the NAS signalling connection and then selects higher priority PLMN | Qualcomm | Opt 2: RAN5#85 (Nov-19) | R5-195257 R5-198878 R5-202598 R5-204408 R5-211378 R5-211380 |  | 1 | 100% | 5 | 100% | 100%
49 | Y | 38.523-1 | 6.3.1.3 | Steering of UE in roaming during registration/security check unsuccessful/Automatic mode | **** TP1: [TS 23,122:Annex C.2; TS 24,501:4.4.4..2 , 5.5.1.2.4] WITH: the UE in Automatic PLMN Selection mode , VPLMN not part of “PLMNs where registration was aborted due to SOR” List and not part of "User Controlled PLMN Selector with Access Technology " & UE's USIM configured with indication that the UE is to receive Steering of Roaming information due to initial registration in a VPLMN and the PDU session for emergency services is not pending to be activated WHEN: List Type indicates PLMN ID and Access technology list in REGISTRATION ACCEPT but security check is unsuccessful THEN: UE releases N1 NAS Signaling connection locally, abort registration procedure, add PLMN to “PLMNs where registration was aborted due to SOR” and performs PLMN selection with current VPLMN considered as lowest priority **** TP2: [TS 23,122:Annex C.2] WITH: PLMN already part of “PLMNs where registration was aborted due to SOR” List WHEN: UE is switched off THEN: UE deletes PLMNs where registration was aborted due to SOR” List | ECIT | Opt 2: RAN5#84 (Aug-19) | R5-197195 R5-202599 R5-204543 R5-205368 R5-211378 |  | 1 | 100% | 4 | 100% | 100%
50 | Y | 38.523-1 | 6.3.1.4 | Steering of UE in roaming during registration/security check unsuccessful/ Manual mode | **** TP1: [TS 23,122:Annex C.2; TS 24,501:4.4.4..2 , 5.5.1.2.4] WITH: the UE in Manual PLMN Selection mode , VPLMN not part of “PLMNs where registration was aborted due to SOR” List and not part of "User Controlled PLMN Selector with Access Technology " & UE's USIM configured with indication that the UE is to receive Steering of Roaming information due to initial registration in a VPLMN and the PDU session for emergency services is not pending to be activated WHEN: List is received but Security check fails THEN: UE continues to camp on the VPLMN | ECIT | Opt 2: RAN5#84 (Aug-19) | R5-197196 R5-202597 R5-210320 R5-211378 |  | 1 | 100% | 4 | 100% | 100%
51 | Y | 38.523-1 | 6.3.1.5 | Steering of UE in roaming during registration/UE configured to receive Steering of Roaming information but does not receive Steering of Roaming from Network | **** TP1: [TS 23,122:Annex C.2] WITH: the UE in Automatic PLMN Selection mode , VPLMN not part of “PLMNs where registration was aborted due to SOR” List and not part of "User Controlled PLMN Selector with Access Technology " & UE's USIM configured with indication that the UE is to receive Steering of Roaming information due to initial registration in a VPLMN and the PDU session for emergency services is not pending to be activated WHEN: neither the list of preferred PLMN/access technology combinations nor the HPLMN indication that 'no change of the "Operator Controlled PLMN Selector with Access Technology" list stored in the UE is needed and thus no list of preferred PLMN/access technology combinations is provided' is received in the REGISTRATION ACCEPT message THEN: UE releases N1 NAS Signaling connection locally, adds PLMN to “PLMNs where registration was aborted due to SOR” and performs PLMN selection with current VPLMN considered as lowest priority | ZTE | Opt 2: RAN5#87 (May-20) | R5-202600 R5-204409 R5-205369 R5-211378 |  | 1 | 100% | 7 | 100% | 100%
52 |  | 38.523-1 | 6.3.1.6 | Void | FFS - No test purpose details specified yet. | ZTE |  | R5-212764 |  | 0 |  | 7
53 | Y | 38.523-1 | 6.3.1.7 | Steering of UE in roaming during registration/security check unsuccessful but emergency service pending to be activated | **** TP1: [TS 23,122:Annex C.2] WITH: the UE in Automatic PLMN Selection mode , VPLMN not part of “PLMNs where registration was aborted due to SOR” List and not part of "User Controlled PLMN Selector with Access Technology " & UE's USIM configured with indication that the UE is to receive Steering of Roaming information due to initial registration in a VPLMN and there is a PDU session for emergency services pending to be activated WHEN: Steering of information is received but security check is unsuccessful THEN: UE will continue with the registration procedure on the VPLMN so as to be able to establish the emergency PDU session | ZTE | Opt 2: RAN5#87 (May-20) | R5-202601 R5-204410 R5-205361 R5-210807 R5-212413 |  | 1 | 100% | 7 | 100% | 100%
54 | Y | 38.523-1 | 6.3.1.8 | Steering of UE in roaming after registration/Automatic PLMN selection mode | **** TP1: [TS 23,122:Annex C.3; TS 24,501:5.4.5.2.2 , 5.4.5.3.2 , 9.11.3.5.1] WITH: the UE in Automatic PLMN Selection mode , current chosen VPLMN not part of the "User Controlled PLMN Selector with Access Technology" list and no emergency PDU Sessions active WHEN: the AMF sends DL NAS TRANSPORT message to the served UE containing Steering of roaming information requesting ACK and the Security check fails THEN: UE shall wait until it moves to idle mode and attempt to obtain service on a higher priority PLMN as specified in subclause 4.4.3.3 by acting as if timer T that controls periodic attempts has expired, with an exception that the current PLMN is considered as lowest priority **** TP2: [TS 23,122:Annex C.3; TS 24,501:5.4.5.2.2 , 5.4.5.3.2 , 9.11.3.5.1] WITH: the UE in Automatic PLMN Selection mode , current chosen VPLMN not part of the "User Controlled PLMN Selector with Access Technology" list and no emergency PDU Sessions active WHEN: the AMF sends DL NAS TRANSPORT message to the served UE containing Steering of roaming information requesting ACK and the security check passes THEN: the UE shall replace the highest priority entries in the "Operator Controlled PLMN Selector with Access Technology" list stored in the UE with the received list of preferred PLMN/access technology combinations , sends an UL NAS TRANSPORT message to the serving AMF with a transparent container including the UE acknowledgement and wait until it moves to idle mode and then attempt to obtain service on a higher priority PLMN **** TP3: [TS 23,122:Annex C.3; TS 24,501:5.4.5.2.2 , 5.4.5.3.2 , 9.11.3.5.1] WITH: the UE in Automatic PLMN Selection mode , current chosen VPLMN not part of the "User Controlled PLMN Selector with Access Technology" list and Emergency PDU Session active WHEN: the AMF sends DL NAS TRANSPORT message to the served UE containing Steering of roaming information and the Security check passes THEN: the UE shall attempt to obtain service on higher priority PLMN after the release of the emergency PDU session and expiration of timer T | ECIT | Opt 2: RAN5#84 (Aug-19) | R5-197197 R5-202604 R5-204411 R5-211378 |  | 1 | 100% | 4 | 100% | 100%
55 | Y | 38.523-1 | 6.3.1.9 | Steering of UE in roaming after registration/Manual PLMN selection mode | **** TP1: [TS 23,122:Annex C.3; TS 24,501:5.4.5.2.2 , 5.4.5.3.2 , 9.11.3.5.1] WITH: the UE in Manual PLMN Selection mode , current chosen VPLMN not part of the "User Controlled PLMN Selector with Access Technology" list and no emergency PDU Sessions active WHEN: the AMF sends DL NAS TRANSPORT message to the served UE containing Steering of roaming information requesting ACK and the Security check passes THEN: the UE shall continue to stay in currently chosen VPLMN | ECIT | Opt 2: RAN5#84 (Aug-19) | R5-197198 R5-202605 R5-210320 R5-211378 |  | 1 | 100% | 4 | 100% | 100%
68 | Y | 38.523-1 | 6.3.1.10 | Steering of UE in roaming during mobility update registration | **** TP1: [TS 23,122:Annex C.2] WITH: UE being in automatic PLMN selection mode , current VPLMN not part of “PLMNs where registration was aborted due to SOR” List and not part of "User Controlled PLMN Selector with Access Technology" list and UE's USIM configured with indication that the UE is to receive Steering of Roaming information due to initial registration in a VPLMN WHEN: UE performs mobility update Registration Procedure to cell belonging to VPLMN and chosen VPLMN does not provide Steering of Roaming info THEN: UE continues to camp on the chosen VPLMN | ZTE | Opt 2: RAN5#91 (May-21) | R5-213456 |  | 1 | 100% | 11 | 100% | 100%
67 |  | 38.523-1 | 6.3.1.1 to 6.3.1.9 |  | Define FR2 power levels for test cases 6.3.1.1 to 6.3.1.9 | See above | Opt 2: RAN5#92 (Aug-21) |  |  | 0 | 0% | 12 |  | 0%
RRC_INACTIVE
|  | 38.523-1 | 6.4 | UE Procedures in RRC_INACTIVE state
|  | 38.523-1 | 6.4.1 | NG-RAN Only PLMN Selection in RRC_INACTIVE state
56 | Y | 38.523-1 | 6.4.1.1 | PLMN Selection/Higher priority/HPLMN in Automatic PLMN Selection Mode | **** TP1: [TS 38,304:4.1 , 4.2; TS 23,122:4.4.3.3] WITH: UE in NR RRC_INACTIVE state on an NG-RAN VPLMN cell WHEN: UE performs PLMN Selection to a PLMN that is equivalent PLMN of the registered PLMN THEN: UE remains in RRC_INACTIVE state after moving to the Equivalent PLMN cell **** TP2: [TS 38,304:4.1 , 4.2; TS 23,122:4.4.3.3] WITH: UE in NR RRC_INACTIVE state on an NG-RAN VPLMN cell and cells of a higher priority NG-RAN PLMN available WHEN: Higher priority PLMN search timer T expires THEN: UE selects the higher priority PLMN cell , moves to RRC_IDLE and attempts Registration with mobility on the selected cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-195649 R5-197838 R5-201349 R5-203382 R5-204415 R5-210062 |  | 1 | 95% | 12 | 100% | 90%
57 | Y | 38.523-1 | 6.4.1.2 | Cell reselection of ePLMN in manual mode | **** TP1: [TS 23,122:4.4.3.1.2; TS 38,304:4.1 , 4.2] WITH: UE in NR RRC_INACTIVE state on a NR cell in manual PLMN Selection mode and network has downloaded a list of equivalent PLMNs during the Registration procedure WHEN: Higher ranked cell is a cell of a PLMN in the downloaded equivalent PLMN list THEN: UE reselects to the equivalent PLMN cell and remains in NR RRC_INACTIVE state on the new cell **** TP2: [TS 23,122:4.4.3.1.2; TS 38,304:4.1 , 4.2] WITH: UE in NR RRC_INACTIVE state on a cell and network has downloaded a list of equivalent PLMNs during Registration procedure for mobility WHEN: Highest ranked cell is a cell of a PLMN not in the downloaded equivalent PLMN list THEN: UE does not reselect to the cell | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-200339 R5-201477 R5-204379 R5-211331 R5-213163 |  | 1 | 95% | 12 | 100% | 90%
|  | 38.523-1 | 6.4.2 | NG-RAN Only Cell Selection in RRC_INACTIVE State
58 | Y | 38.523-1 | 6.4.2.1 | Cell Selection/Qrxlevmin & Cell Reselection (Intra NR in RRC_INACTIVE state) | **** TP1: [TS 38.300:9.2.1.1; TS 38,304:4.1 , 4.2 , 4.5 , 5.2.1, 5.2.3.1 , 5.2.3.2] WITH: UE in NR RRC_INACTIVE state WHEN: serving cell fulfils all requirements for a suitable cell except the cell selection criteria which are not fulfilled (Srxlev<0) THEN: UE does not consider the cell as suitable , leaves NR RRC_INACTIVE state and does not remain camped on that cell **** TP2: [TS 38.300:9.2.1.1; TS 38,304:4.1 , 4.2 , 4.5 , 5.2.1, 5.2.3.1 , 5.2.3.2] WITH: UE in NR RRC_INACTIVE state WHEN: UE detects a cell ranked as the best cell THEN: UE reselects to the new cell and continues to remain in NR RRC_INACTIVE state | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-195252 R5-201133 R5-201790 R5-205600 R5-212084 |  | 1 | 95% | 12 | 100% | 90%
59 | Y | 38.523-1 | 6.4.2.2 | Inter-frequency cell reselection according to cell reselection priority provided by SIBs in RRC_INACTIVE state | **** TP1: [TS 38,304:4.1 , 4.2 , 5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_INACTIVE state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the equal priority frequency THEN: UE reselects to the cell which belongs to the equal priority frequency and remains in NR RRC_INACTIVE state **** TP2: [TS 38,304:4.1 , 4.2 , 5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_INACTIVE state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the higher priority frequency THEN: UE reselects to the cell which belongs to the higher priority frequency and remains in NR RRC_INACTIVE state **** TP3: [TS 38,304:4.1 , 4.2 , 5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_INACTIVE state WHEN: UE detects the cell re-selection criteria are met for the cell which belongs to the lower priority frequency THEN: UE reselects to the cell which belongs to the lower priority frequency and remains in NR RRC_INACTIVE state | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-195650 R5-201500 R5-203502 |  | 1 | 95% | 12 | 100% | 90%
|  | 38.523-1 | 6.4.3 | Inter-RAT Cell Reselection
60 | Y | 38.523-1 | 6.4.3.1 | Inter-RAT cell reselection From NR RRC_INACTIVE to E-UTRA RRC_IDLE (lower priority & higher priority, Srxlev based) | **** TP1: [TS 38,304:4.1 , 4.2 , 5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_INACTIVE state WHEN: UE detects the cell re-selection criteria are met for the neighbour cell which belongs to the higher priority E-UTRA frequency THEN: UE reselects to the E-UTRA cell and transitions to E-UTRA RRC_IDLE State **** TP2: [TS 38,304:4.1 , 4.2 , 5.2.4.1 , 5.2.4.2 , 5.2.4.5] WITH: UE in NR RRC_INACTIVE state WHEN: UE detects the cell re-selection criteria are met for the neighbour cell which belongs to the lower priority E-UTRA frequency THEN: UE reselects to the E-UTRA cell and transitions to E-UTRA RRC_IDLE State | Huawei,Hisilicon | Opt 2: RAN5#92 (Aug-21) | R5-197191 R5-200366 R5-203745 R5-204417 R5-210610 R5-211022 R5-212368 |  | 1 | 95% | 12 | 100% | 90%
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A7: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B7: Y = the WP Pitem is a test case.
Note on K7: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.