## Cover sheet
3GPP TSG-RAN WG5 Meeting #91-e | [10 empty] | R5-213360
Electronic Meeting, May 17th - May 28th 2021
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | Work plan for NR performance requirement enhancement
Work item code: | NR_perf_enh-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At RAN#89-e meeting Rel-16 RAN5 work item for NR performance enhancement (NR_perf_enh-Perf-UEConTest) was approved [1]. The objective of this work item is to define the UE conformance requirements on NR performance enhancement, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-16. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 18% (+4%) | 0 | 37 (+18)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 18.3% (+3.6%) | 0 | 37 (+18)
FR1 |  | 19% (+3.8%) | 0 | 35 (+18)
FR2 |  | 9.3% | 0 | 2
FR1 + FR2
NSA Option 3 (EN-DC) |  | 18.3% (+3.6%) | 0 | 37 (+18)
FR1 |  | 19% (+3.8%) | 0 | 35 (+18)
FR2 |  | 9.3% | 0 | 2
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
NR RF/RRM
RF Demod/CSI test cases | 38.521-4 | 13.5% (+3.7%) | 0 | 37 (+18) | 14.8% (+4%) | 0 | 35 (+18) | 4.5% | 0 | 2 |  |  |  | 14.8% (+4%) | 0 | 35 (+18) | 4.5% | 0 | 2
5 References
[1] RP-201941 | New WID: UE Conformance Test Aspects – NR performance requirement enhancement – Qualcomm, (Supporting companies: China Telecom, NTT Docomo, LGE, Ericsson, DISH network, Huawei, HiSilicon, CATT, ZTE, Keysight, Orange, Anritsu)
[2] R5-211289 | WP UE Conformance Test Aspects - NR performance requirement enhancement, Qualcomm
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Work plan for NR performance requirement enhancement | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [5 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_perf_enh-UEConTest
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 work item NR performance requirement enhancement comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [13 empty] | vs Area
WP Resp: |  | Vijay Balasubramanian, Qualcomm |  |  | Vijay Balasubramanian | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2
[15 empty] | 19% (+3.8%) | 9.3% |  | 19% (+3.8%) | 9.3%
[15 empty] | 36 (+14) | 9 | 0 | 36 (+14) | 9 | 0
[15 empty] | 65 (+15) | 5.5 | 0 | 65 (+15) | 5.5 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS - RAN and CN
5GS Common
TS 38.508-1: Common test environment
TBD |  | 38.508-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.508-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.508-2: Common ICS
TBD |  | 38.508-2 | <Clause> | <Title> | Add ICS as needed for the test case applicability statements for the new Demod/QSI test cases |  | TBD |  |  | TBD
NR RF/RRM
TS 38.521-4: Demod/CSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 30 | 0% | 0% | 0% |  | 0% |  |  | 0%
1 |  | 38.521-4 | 5.2 | PDSCH demodulation requirements
2 |  | 38.521-4 | 5.2.2.2.4 | 2Rx TDD FR1 PDSCH Mapping Type A and LTE-NR coexistence performance | clause title |  |  |  |  | 0
3 | Y | 38.521-4 | 5.2.2.2.4_1 | 2Rx TDD FR1 PDSCH Mapping Type A and LTE-NR coexistence performance - 4x2 MIMO with baseline receiver for both SA and NSA | new test case | Ericsson | RAN5#92 (Aug-21) | R5-206775 R5-211050 | Release applicability should be Rel15 onwards in both 38.521-4 and 38.522 | 1 | 90% | 90% | 90% |  | 90% |  |  | 90%
4 |  | 38.521-4 | 5.2A | PDSCH demodulation requirements for CA | clause title |  |  |  |  | 0
5 |  | 38.521-4 | 5.2A.1 | 1RX requirements (Void) | clause title |  |  |  |  | 0
6 |  | 38.521-4 | 5.2A.2.1 | 2RX requirements for normal PDSCH Demodulation | clause title |  |  |  |  | 0
7 | Y | 38.521-4 | 5.2A.2.1.1 | 2Rx Normal PDSCH Demodulation Performance for CA (2DL CA) | new test case | Qualcomm | RAN5#92 (Aug-21) | R5-214098 |  | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% |  |  | 60%
8 | Y | 38.521-4 | 5.2A.2.1.2 | 2Rx Normal PDSCH Demodulation Performance for CA (3DL CA) | new test case |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
9 | Y | 38.521-4 | 5.2A.2.1.3 | 2Rx Normal PDSCH Demodulation Performance for CA (4DL CA) | new test case |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
10 |  | 38.521-4 | 5.2A.2.2 | 2RX requirements for carrier aggregation with power imbalance | [5 empty] | 0
11 | Y | 38.521-4 | 5.2A.2.2.1 | 2Rx PDSCH Demodulation Performance for CA with power imbalance (2DL CA) | new test case | Qualcomm | RAN5#92 (Aug-21) | R5-213358 |  | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% |  |  | 60%
12 | Y | 38.521-4 | 5.2A.2.2.2 | 2Rx PDSCH Demodulation Performance for CA with power imbalance (3DL CA) | new test case |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
12 | Y | 38.521-4 | 5.2A.2.2.3 | 2Rx PDSCH Demodulation Performance for CA with power imbalance (4DL CA) | new test case |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
55 |  | 38.521-4 | 5.2A.3 | 4Rx requirements | clause title
13 |  | 38.521-4 | 5.2A.3.1 | 4RX requirements for normal PDSCH Demodulation | clause title
7 | Y | 38.521-4 | 5.2A.3.1.1 | 4Rx Normal PDSCH Demodulation Performance for CA (2DL CA) | new test case | Qualcomm | RAN5#92 (Aug-21) | R5-214098 |  | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% |  |  | 60%
8 | Y | 38.521-4 | 5.2A.3.1.2 | 4Rx Normal PDSCH Demodulation Performance for CA (3DL CA) | new test case |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
9 | Y | 38.521-4 | 5.2A.3.1.3 | 4Rx Normal PDSCH Demodulation Performance for CA (4DL CA) | new test case |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
17 |  | 38.521-4 | 5.2A.3.2 | 4RX requirements for carrier aggregation with power imbalance
18 | Y | 38.521-4 | 5.2A.3.2.1 | 4Rx PDSCH Demodulation Performance for CA with power imbalance (2DL CA) | new test case |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
56 |  | 38.521-4 | 5.2A.3A | 2Rx-4Rx requirements | clause title
57 |  | 38.521-4 | 5.2A.3A.1 | 2Rx-4RX requirements for normal PDSCH Demodulation | clause title
58 | Y | 38.521-4 | 5.2A.3A.1.1 | 2Rx-4Rx Normal PDSCH Demodulation Performance for CA (2DL CA) | new test case | Qualcomm | RAN5#92 (Aug-21) | R5-214098 |  | 1 | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% |  |  | 60%
59 | Y | 38.521-4 | 5.2A.3A.1.2 | 2Rx-4Rx Normal PDSCH Demodulation Performance for CA (3DL CA) | new test case |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
60 | Y | 38.521-4 | 5.2A.3A.1.3 | 2Rx-4Rx Normal PDSCH Demodulation Performance for CA (4DL CA) | new test case |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
20 |  | 38.521-4 | 5.2.3.2.4 | 4Rx TDD FR1 PDSCH Mapping Type A and LTE-NR coexistence performance | new clause title
21 | Y | 38.521-4 | 5.2.3.2.4_1 | 4Rx TDD FR1 PDSCH Mapping Type A and LTE-NR coexistence performance - 4x4 MIMO with baseline receiver for both SA and NSA | new test case | Ericsson | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
65 |  | 38.521-4 | 5.5A | Sustained downlink data rate provided by lower layers
66 |  | 38.521-4 | 5.5A.1 | CA requirements for Sustained downlink data rate provided by lower layers
67 | Y | 38.521-4 | 5.5A.1.1 | FR1 Sustained downlink data rate performance for CA | new test case |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
22 |  | 38.521-4 | 6.1 | General
23 |  | 38.521-4 | 6.2A | Reporting of Channel Quality Indicator (CQI) for CA
24 |  | 38.521-4 | 6.2A.1 | General
25 |  | 38.521-4 | 6.2A.2 | 1RX requirements (Void)
26 |  | 38.521-4 | 6.2A.3 | 2Rx requirements | clause title |  |  |  |  | 0
61 |  | 38.521-4 | 6.2A.3.1 | CQI reporting definition under AWGN conditions | clause title |  |  |  |  | 0
62 | Y | 38.521-4 | 6.2A.3.1.1 | 2Rx CQI reporting accuracy under AWGN conditions for CA (2DL CA) | new test case |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
63 | Y | 38.521-4 | 6.2A.3.1.2 | 2Rx CQI reporting accuracy under AWGN conditions for CA (3DL CA) | new test case |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
64 | Y | 38.521-4 | 6.2A.3.1.3 | 2Rx CQI reporting accuracy under AWGN conditions for CA (4DL CA) | new test case |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
27 |  | 38.521-4 | 6.3 | Reporting of Precoding Matrix Indicator (PMI)
28 |  | 38.521-4 | 6.3.1 | 1RX requirements (Void)
29 |  | 38.521-4 | 6.3.2 | 2RX requirements
30 |  | 38.521-4 | 6.3.2.1 | FDD
31 | Y | 38.521-4 | 6.3.2.1.3 | 2Rx FDD FR1 Multiple PMI with 16Tx Type1 - SinglePanel codebook for both SA and NSA | new test case | China Telecom | RAN5#92 (Aug-21) | R5-211658 | Editor's note: This clause is incomplete. - Connection figure for 16 Tx is missing | 1 | 90% | 90% | 90% |  | 90% |  |  | 90%
32 | Y | 38.521-4 | 6.3.2.1.4 | 2Rx FDD FR1 Single PMI with 32Tx Type1 - SinglePanel codebook for both SA and NSA | new test case | China Telecom | RAN5#93 (Nov-21) | R5-212067 | Connection figure for 16 Tx is missing | 1 | 90% (+90%) | 90% (+90%) | 90% (+90%) |  | 90% |  |  | 90%
72 | Y | 38.521-4 | 6.3.2.1.5 | 2Rx FDD FR1 Multiple PMI with 16Tx TypeII codebook for both SA and NSA | new test case | China Telecom | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
33 | Y | 38.521-4 | 6.3.2.2.3 | 2Rx TDD FR1 Single PMI with 16Tx Type1 - SinglePanel codebook for both SA and NSA | new test case | Ericsson | RAN5#92 (Aug-21) | R5-211813 | Editor's note: This clause is incomplete. - Connection figure for 16 Tx is missing Test Applicability release for EN-DC to be changed to Rel15 from Rel16 | 1 | 90% | 90% | 90% |  | 90% |  |  | 90%
34 | Y | 38.521-4 | 6.3.2.2.4 | 2Rx TDD FR1 Single PMI with 32Tx Type1 - SinglePanel codebook for both SA and NSA | new test case | Ericsson | RAN5#92 (Aug-21) | R5-211916 | Editor's note: This clause is incomplete. - Connection figure for 32 Tx is missing Test Applicability release for EN-DC to be changed to Rel15 from Rel16 | 1 | 90% | 90% | 90% |  | 90% |  |  | 90%
74 | Y | 38.521-4 | 6.3.2.2.5 | 2Rx TDD FR1 Multiple PMI with 16Tx TypeII codebook for both SA and NSA | new test case | China Telecom | RAN5#93 (Nov-21) |  |  | 1 | 0% (-90%) | 0% (-90%) | 0% (-90%) |  | 0% |  |  | 0%
35 | Y | 38.521-4 | 6.3.3.1.3 | 4Rx FDD FR1 Single PMI with 16Tx Type1 - SinglePanel codebook for both SA and NSA | new test case | China Telecom | RAN5#92 (Aug-21) | R5-211659 | Editor's note: This clause is incomplete. - Connection figure for 16 Tx is missing | 1 | 90% | 90% | 90% |  | 90% |  |  | 90%
36 | Y | 38.521-4 | 6.3.3.1.4 | 4Rx FDD FR1 Single PMI with 32Tx Type1 - SinglePanel codebook for both SA and NSA | new test case | China Telecom | RAN5#93 (Nov-21) | R5-212068 | Connection figure for 16 Tx is missing | 1 | 90% (+90%) | 90% (+90%) | 90% (+90%) |  | 90% |  |  | 90%
76 | Y | 38.521-4 | 6.3.3.1.5 | 4Rx FDD FR1 Multiple PMI with 16Tx TypeII codebook for both SA and NSA | new test case | China Telecom | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
37 | Y | 38.521-4 | 6.3.3.2.3 | 4Rx TDD FR1 Single PMI with 16Tx Type1 - SinglePanel codebook for both SA and NSA | new test case | Ericsson | RAN5#92 (Aug-21) | R5-211814 | Editor's note: This clause is incomplete. - Connection figure for 16 Tx is missing Test Applicability release for EN-DC to be changed to Rel15 from Rel16 | 1 | 90% | 90% | 90% |  | 90% |  |  | 90%
38 | Y | 38.521-4 | 6.3.3.2.4 | 4Rx TDD FR1 Single PMI with 32Tx Type1 - SinglePanel codebook for both SA and NSA | new test case | Ericsson | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
78 | Y | 38.521-4 | 6.3.3.2.5 | 4Rx TDD FR1 Multiple PMI with 16Tx TypeII codebook for both SA and NSA | new test case | China Telecom | RAN5#93 (Nov-21) |  |  | 1 | 0% (-90%) | 0% (-90%) | 0% (-90%) |  | 0% |  |  | 0%
39 |  | 38.521-4 | 7.1 | General
40 |  | 38.521-4 | 7.2A | PDSCH demodulation requirements for CA
41 |  | 38.521-4 | 7.2A.1 | 1RX requirements (Void)
42 |  | 38.521-4 | 7.2A.2 | 2RX requirements for normal PDSCH Demodulation for CA
43 | Y | 38.521-4 | 7.2A.2.1 | TDD CA 2RX requirements for normal PDSCH Demodulation for both SA and NSA (2DL CA) | new test case | Qualcomm | RAN5#93 (Nov-21) | R5-205920 |  | 1 | 20% | 20% | 20% |  |  | 20% |  |  | 20%
43 | Y | 38.521-4 | 7.2A.2.2 | TDD CA 2RX requirements for normal PDSCH Demodulation for both SA and NSA (3DL CA) | new test case |  | RAN5#93 (Nov-21) |  |  | 1 | 0% (-20%) | 0% (-20%) | 0% (-20%) |  |  | 0% |  |  | 0%
68 |  | 38.521-4 | 7.5A | Sustained downlink data rate provided by lower layers
69 |  | 38.521-4 | 7.5A.1 | CA requirements for Sustained downlink data rate provided by lower layers
70 | Y | 38.521-4 | 7.5A.1.1 | FR2 Sustained downlink data rate performance for CA | new test case |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
44 |  | 38.521-4 | 8.1 | General
45 |  | 38.521-4 | 8.2A | Reporting of Channel Quality Indicator (CQI) for CA
46 |  | 38.521-4 | 8.2A.1 | 1RX requirements (Void)
61 |  | 38.521-4 | 8.2A.2 | 2Rx requirements | clause title |  |  |  |  | 0
62 | Y | 38.521-4 | 8.2A.2.1.1 | 2Rx CQI reporting accuracy under AWGN conditions for CA (2DL CA) | new test case | China Telecom | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
63 | Y | 38.521-4 | 8.2A.2.1.2 | 2Rx CQI reporting accuracy under AWGN conditions for CA (3DL CA) | new test case | China Telecom | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
64 | Y | 38.521-4 | 8.2A.2.1.3 | 2Rx CQI reporting accuracy under AWGN conditions for CA (4DL CA) | new test case | China Telecom | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
48 |  | 38.521-4 | Annex A | Measurement channels |  |  | RAN5#93 (Nov-21) |  |  | 0.5 | 0% | 0% | 0% |  |  | 0% |  |  | 0%
49 |  | 38.521-4 | Annex B | Propagation conditions |  |  | RAN5#93 (Nov-21) |  |  | 0.5 | 0% | 0% | 0% |  |  | 0% |  |  | 0%
50 |  | 38.521-4 | Annex C | Downlink physical channels |  |  | RAN5#93 (Nov-21) |  |  | 0.5 | 0% | 0% | 0% |  |  | 0% |  |  | 0%
51 |  | 38.521-4 | Annex D | LTE link setup details for NSA testing |  |  | RAN5#93 (Nov-21) |  |  | 0.5 | 0% | 0% | 0% |  |  | 0% |  |  | 0%
52 |  | 38.521-4 | Annex H | Approach for finding UE direction for FR2 Demod and CSI Testing |  |  | RAN5#93 (Nov-21) |  |  | 0.5 | 0% | 0% | 0% |  |  | 0% |  |  | 0%
53 |  | 38.521-4 | Annex F | Measurement uncertainties and test tolerances |  | All companies | RAN5#93 (Nov-21) | R5-211086 |  | 0.5 | 10% | 10% | 10% |  |  | 10% |  |  | 10%
54 |  | 38.521-4 | Annex G | Statistical testing |  |  | RAN5#93 (Nov-21) |  |  | 0.5 | 0% | 0% | 0% |  |  | 0% |  |  | 0%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.521-4 |  | TBD |  |  | 0.1
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.