## Cover sheet
3GPP TSG-RAN WG5 Meeting #92-e | [10 empty] | R5-214207
Electronic Meeting, Aug 16 - 27, 2021
Agenda Item: | 7.4.2
Source: | CMCC, Ericsson
Title: | UE Conformance Test Aspects - SON and MDT support for NR
Work item code: | NR_SON_MDT-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
This work plan covers Rel-16 NR SON and MDT Signalling Test Cases
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 85% (+14%) | 20 (+12) | 47
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 85.4% (+14.4%) | 20 (+12) | 47
FR1 |  | 91.8% (+13.4%) | 37 (+7) | 47
FR2 |  | 79% (+15.4%) | 20 (+12) | 47
FR1 + FR2
NSA Option 3 (EN-DC)
FR1
FR2
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 85% (+5%) |  |  | 85% (+5%) |  |  | 85% (+5%)
Common ICS | 38.508-2 | 60% |  |  | 60% |  |  | 60%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 86.7% (+16.3%) | 20 (+12) | 47 | 94% (+15.1%) | 37 (+7) | 47 | 79.4% (+17.5%) | 20 (+12) | 47
Applicability Protocol test cases | 38.523-2 | 79% (+16%) |  |  | 85% (+16%) |  |  | 73% (+16%)
Test suites (TTCN) | 38.523-3 | 0% |  |  | 0% |  |  | 0%
5 References
[1] RP-201625 | New WID on UE Conformance Test Aspects for SON and MDT support for NR
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects - SON and MDT support for NR | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [5 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_SON_MDT-UEConTest
WP Scope: |  | UE Conformance Test Aspects for Rel-16 SON (Self-Organising Networks) and MDT (Minimization of Drive Tests) support for NR (UID-890043) | [13 empty] | vs Area
WP Resp: |  | Wenjia Dong, CMCC |  |  | dongwenjia@chinamobile.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2
[15 empty] | 91.8% (+13.4%) | 79% (+15.4%)
[15 empty] | 74 | 74 | 0 | 0 | 0 | 0
[15 empty] | 52 (+0) | 52 (+0) | 0 | 0 | 0 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4.6.3, 4.6.5 | RRC default messages | Add MDT/SON changes to default messages if needed | CMCC, ZTE | RAN5#90-e (Feb-21) | R5-211467, R5-211468, R5-213601, R5-216284, R5-214728 |  | 1 | 85% (+5%) | 85% (+5%) |  |  | 85% | 85%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | A.4.4 | Additional information | Define UE capabilities for MDT/SON features if needed | CMCC, ZTE, MediaTek Inc, HiSilicon | RAN5#90-e (Feb-21) | R5-211469, R5-213602 |  | 1 | 60% | 60% |  |  | 60% | 60%
TS 38.509: UE Positioning test mode procedures
71 |  | 38.509 | 5.6, 6.6 | Additional information | Introduction of UE Positioning test mode procedures for R16 NR SON and MDT requirements. | ZTE | RAN5#91-e (May-21) | R5-213421 |  | 1 | 100% | 100% |  |  | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
RRC
3 |  | 38.523-1 | 8.1.6 | SON and MDT support for NR | New sub-clause | CMCC | RAN5#90-e (Feb-21) |  |  | 0 | 100% | 100% |  |  | 100% | 100%
Intra NR MDT
4 |  | 38.523-1 | 8.1.6.1 | Intra NR MDT | New sub-clause | CMCC | RAN5#90-e (Feb-21) |  |  | 0 | 100% | 100% |  |  | 100% | 100%
Immediate MDT
5 |  | 38.523-1 | 8.1.6.1.1 | Immediate MDT | New sub-clause | CMCC | RAN5#90-e (Feb-21) |  |  | 0 | 50% | 50% |  |  | 100% | 0%
6 | Y | 38.523-1 | 8.1.6.1.1.1 | Immediate MDT / Measurement reporting / Location information | TP1：Entry condition for event A2 is met and detailed location information that has not been reported is available, UE sends MeasurementReport message with locationInfo included； TP2：Exit condition for event A2 is met, UE stops sending MeasurementReport message; | CMCC | RAN5#90-e (Feb-21) | R5-211477, R5-214756 |  | 1 | 50% | 50% |  |  | 100% | 0%
7 | Y | 38.523-1 | 8.1.6.1.1.2 | Immediate MDT / Measurement / Latency metrics for UL PDCP Packet Delay per DRB | TP1: UE receives RRCReconfiguration containing ReportConfigNR IE with ul-DelayValueConfig IE set to “setup”, UE sends the RRCReconfigurationComplete message; TP2: UE determines that UL PDCP SDUs per DRB, UE sends the MeasurementReport message with ul-PDCP-DelayResultList for corresponding DRB; TP3: UE receives RRCReconfiguration containing ReportConfigNR IE with ul-DelayConfig IE set to “release”, UE stops monitoring the UL PDCP Packet Delay per DRB; | CMCC | RAN5#90-e (Feb-21) | R5-211478 |  | 1 | 50% | 50% |  |  | 100% | 0%
Logged MDT
8 |  | 38.523-1 | 8.1.6.1.2 | Logged MDT | New sub-clause | ZTE | RAN5#90-e (Feb-21) |  |  | 0 | 100% | 100% |  |  | 100% | 100%
9 | Y | 38.523-1 | 8.1.6.1.2.1 | Logged MDT / RRC_IDLE / Logging and reporting / Intra-frequency measurement | TP1：logged MDT ，Measurement configuration，collection，reporting（indicator in RRCSetupComplete） TP2：the logged measurement quantities of the camped cell, the best beam index (SSB Index) as well as best beam RSRP/RSRQ is logged as well as the 'number of good beams' associated to the cells within the R value range (which is configured by network for cell reselection) of the highest ranked cell as part of the beam level measurements. TP3：UE transmits UEInformationResponse messages with absoluteTimeStamp set equal to the value configured when the logged measurement configuration was received and a relativeTimeStamp for each logged measurement indicating the elapsed time since the logged measurement configuration was received TP4：UE transmits UEInformationResponse messages with traceReference, traceRecordingSessionRef and tce-Id being set to same values as configured when the logged measurement configuration was received | ZTE | RAN5#90-e (Feb-21) | R5-211470, R5-213621, R5-216297 |  | 1 | 100% (+10%) | 100% (+10%) |  |  | 100% | 100%
10 | Y | 38.523-1 | 8.1.6.1.2.2 | Logged MDT / RRC_INACTIVE / Logging and reporting / Inter-frequency measurement | TP1：logged MDT ，Measurement configuration，collection，reporting（indicator in RRCResumeComplete） TP2：The measurement reports for neighbour cells consist of:Physical cell identity of the logged cell; Carrier frequency; RSRP and RSRQ for NR; TP3：An indicator shall be also provided in UEInformationResponse message during MDT report retrieval in case the UE has not transferred the total log in one RRC message in order to indicate the remaining data availability. | ZTE | RAN5#90-e (Feb-21) | R5-211471, R5-213622, R5-216298 |  | 1 | 100% (+10%) | 100% (+10%) |  |  | 100% | 100%
11 | Y | 38.523-1 | 8.1.6.1.2.3 | Logged MDT / RRC_IDLE / Logging and reporting / Limiting area scope | configuration of a logging area. A UE will log measurements as long as it is within the configured logging area： TP1：a list of up to 32 global cell identities TP2：a list of up to 8 Tas | ZTE | RAN5#90-e (Feb-21) | R5-211472, R5-213623, R5-216299 |  | 1 | 95% (+5%) | 95% (+5%) |  |  | 100% | 90%
12 | Y | 38.523-1 | 8.1.6.1.2.4 | logged MDT/ RRC_IDLE / Logging and reporting / periodic measurement trigger | TP1：periodic measurement trigger is supported, for which the logging interval is configurable. | ZTE | RAN5#90-e (Feb-21) | R5-210032, R5-213624, R5-216300 |  | 1 | 100% (+10%) | 100% (+10%) |  |  | 100% | 100%
13 | Y | 38.523-1 | 8.1.6.1.2.5 | logged MDT/ RRC_IDLE / Logging and reporting / event-based trigger | TP1: UE is logging serving cell idle mode measurements only when the conditions indicated by the eventL1 are met | ZTE | RAN5#90-e (Feb-21) | R5-210033, R5-213625, R5-216301 |  | 1 | 95% (+5%) | 95% (+5%) |  |  | 100% | 90%
14 | Y | 38.523-1 | 8.1.6.1.2.6 | logged MDT/ RRC_IDLE / Logging and reporting / event-based trigger / out-of-coverage | TP1: The UE will continue to log if out-of-coverage happens | ZTE | RAN5#90-e (Feb-21) | R5-210034, R5-213626, R5-216302 |  | 1 | 100% (+10%) | 100% (+10%) |  |  | 100% | 100%
15 | Y | 38.523-1 | 8.1.6.1.2.7 | Logged MDT / RRC_IDLE / Logging and reporting / Reporting at NR re-establishment | A UE configured to perform Logged MDT downlink pilot strength measurements indicates the availability of Logged MDT measurements, by means of a one bit, in NR re-establishment | ZTE | RAN5#90-e (Feb-21) | R5-211473, R5-213627, R5-216303 |  | 1 | 100% (+10%) | 100% (+10%) |  |  | 100% | 100%
16 | Y | 38.523-1 | 8.1.6.1.2.8 | Logged MDT / RRC_IDLE / Logging and reporting / Reporting at RRC reconfiguration | A UE configured to perform Logged MDT downlink pilot strength measurements indicates the availability of Logged MDT measurements, by means of a one bit, in RRC reconfiguration（intra NR handover） | ZTE | RAN5#90-e (Feb-21) | R5-211474, R5-213628, R5-216308 |  | 1 | 90% | 90% |  |  | 100% | 80%
17 | Y | 38.523-1 | 8.1.6.1.2.9 | Logged MDT / Location information | TP1：Detailed location information (e.g. GNSS location information) is included if available in the UE when the measurement was taken. If detailed location information is available the reporting shall consist of latitude and longitude. | ZTE | RAN5#90-e (Feb-21) | R5-210037, R5-213629, R5-216304 |  | 1 | 100% (+10%) | 100% (+10%) |  |  | 100% | 100%
18 | Y | 38.523-1 | 8.1.6.1.2.10 | Logged MDT / Maintaining logged measurement configuration / UE mobility | TP1：UE reselected to a cell belong to non MDT PLMN，UE does not indicate availability of Logged MDT measurements，UE suspends Logged MDT measurements； TP2：UE returns to a cell belong to MDT PLMN，UE indicate availability of Logged MDT measurements，UE resumes Logged MDT measurements | ZTE | RAN5#90-e (Feb-21) | R5-210038, R5-213630, R5-216305 |  | 1 | 95% (+5%) | 95% (+5%) |  |  | 100% | 90%
19 | Y | 38.523-1 | 8.1.6.1.2.11 | Logged MDT / Maintaining logged measurement configuration / UE state transitions | TP1：For Logged MDT measurement collection for RRC INACTIVE UEs, the actual process of logging within the UE, takes place in RRC INACTIVE state and may be continued in RRC IDLE state | ZTE | RAN5#90-e (Feb-21) | R5-210039, R5-213631, R5-216306 |  | 1 | 95% (+5%) | 95% (+5%) |  |  | 100% | 90%
20 | Y | 38.523-1 | 8.1.6.1.2.12 | Logged MDT / Release of logged MDT measurement configuration / Expire of duration timer | A release operation for logged measurement configuration in the UE is realized only by configuration replacement when the configuration is overwritten or by configuration clearance in case a duration timer stopping or expiration condition is met. | ZTE | RAN5#90-e (Feb-21) | R5-211475, R5-213632, R5-216309 |  | 1 | 90% | 90% |  |  | 100% | 80%
21 | Y | 38.523-1 | 8.1.6.1.2.13 | Logged MDT / Release of logged MDT measurement configuration / Reception of new logged measurement configuration | UE receive a new LoggedMeasurementConfiguration message, will discard the old logged measurement configuration and the stored logMeasReport | ZTE | RAN5#90-e (Feb-21) | R5-211476, R5-213633, R5-216310 |  | 1 | 90% | 90% |  |  | 100% | 80%
Radio Link Failure report
22 |  | 38.523-1 | 8.1.6.1.3 | Radio Link Failure report | New sub-clause | MediaTek | RAN5#90-e (Feb-21) |  |  | 0 | 100% | 100% |  |  | 100% | 100%
23 | Y | 38.523-1 | 8.1.6.1.3.1 | Radio Link Failure / Reporting of Intra-frequency measurements | TP1：UE in RRC_CONNECTED having performed the intra-frequency measurement and reported that the UE has radio link failure information available，UE sends the UEInformationResponse message containing the measurement result for intra-frequency neighbour cell TP2：Latest radio measurement results of the serving and neighbouring cells, including SSB/CSI-RS index and associated measurements in the serving and neighbouring cells | MediaTek | RAN5#90-e (Feb-21) | R5-211485, R5-213607, R5-216289 |  | 1 | 100% | 100% |  |  | 100% | 100%
24 | Y | 38.523-1 | 8.1.6.1.3.2 | Radio Link Failure / Reporting of Inter-frequency measurements | TP1：UE in RRC_CONNECTED having performed the inter-frequency measurement and reported that the UE has radio link failure information available，UE sends the UEInformationResponse message containing the measurement result for inter-frequency neighbour cell | MediaTek | RAN5#90-e (Feb-21) | R5-210799, R5-212106, R5-214550 |  | 1 | 100% | 100% |  |  | 100% | 100%
25 | Y | 38.523-1 | 8.1.6.1.3.3 | Radio Link Failure / Reporting at RRC connection establishment and reestablishment | TP1：UE in RRC_CONNECTED state detecting radio link failure，UE sends the RRCSetupComplete message with rlf-InfoAvailable included after receiving an RRCSetup message; TP2： UE in RRC_CONNECTED state detecting radio link failure，UE sends the RRCReestablishmentComplete message with rlf-InfoAvailable included after receiving an RRCReestablishment message; TP3：UE in RRC_CONNECTED state with the radio link failure information available，UE sends the UEInformationResponse message with rlf-Report included | MediaTek | RAN5#90-e (Feb-21) | R5-211486, R5-216290 |  | 1 | 100% | 100% |  |  | 100% | 100%
26 | Y | 38.523-1 | 8.1.6.1.3.4 | Radio Link Failure / Reporting at NR handover | TP1：UE in RRC_CONNECTED state with handover failure information available，UE receives RRCReconfiguration message includes the mobilityControlInfo，UE sends the RRCConnectionReconfigurationComplete message with rlf-InfoAvailable included TP2：UE in RRC_CONNECTED state with the handover failure information available，UE sends the UEInformationResponse message with rlf-Report included | MediaTek | RAN5#90-e (Feb-21) | R5-213608, R5-216291 |  | 1 | 100% | 100% |  |  | 100% | 100%
27 | Y | 38.523-1 | 8.1.6.1.3.5 | Radio Link Failure / Location information | TP1：UE in RRC_CONNECTED having performed the intra-frequency measurement and reported that the UE has radio link failure information with location information available，UE sends the UEInformationResponse message containing the measurement result for intra-frequency neighbour cell including locationCoordinates | MediaTek | RAN5#91-e (May-21) | R5-213609, R5-214698 |  | 1 | 100% | 100% |  |  | 100% | 100%
28 | Y | 38.523-1 | 8.1.6.1.3.6 | Radio Link Failure / RACH failure report | TP1：RACH failure report (in case, the cause for RLF is random access problem or Beam Failure Recovery failure) | MediaTek | RAN5#91-e (May-21) | R5-213610, R5-216292 |  | 1 | 100% | 100% |  |  | 100% | 100%
29 | Y | 38.523-1 | 8.1.6.1.3.7 | Radio Link Failure / Logging and reporting / Reporting at intra NR handover / PLMN list | TP1：UE performs RRC connection re-establishment procedure and intra-NR handover procedure，UE sends an RRCReconfigurationComplete message with rlf-InfoAvailable TP2：UE sends a UEInformationResponse message with rlf-Report and PLMN list | MediaTek | RAN5#91-e (May-21) | R5-213611, R5-216293 |  | 1 | 100% | 100% |  |  | 100% | 100%
Connection Establishment Failure
30 |  | 38.523-1 | 8.1.6.1.4 | Connection Establishment Failure | New sub-clause | CMCC | RAN5#90-e (Feb-21) |  |  | 0 | 100% | 100% |  |  | 100% | 100%
31 | Y | 38.523-1 | 8.1.6.1.4.1 | Connection Establishment Failure / Logging and reporting / T300 expiry | TP1：The trigger for creating a log related to a failed RRC connection establishment is for NR when timer T300 expires（RRCSetupComplete） | CMCC | RAN5#90-e (Feb-21) | R5-213603, R5-216311 |  | 1 | 50% | 50% |  |  | 100% | 0%
32 | Y | 38.523-1 | 8.1.6.1.4.2 | Connection Establishment Failure / Logging and reporting / RRC Resume | TP1: with { UE having sent an RRCResumeRequest message } ensure that { when { T319 is expired and random access procedure failed } then { UE stores the connection resume failure information } } TP2: with { UE having sent an RRCSetupComplete message with connEstFailInfoAvailable } ensure that { when { UE receives a UEInformationRequest message with connEstFailReportReq set to true } then { UE sends a UEInformationResponse message with connEstFailReport } } | CMCC | RAN5#90-e (Feb-21) | R5-213604, R5-216312 |  | 1 | 100% | 100% |  |  | 100% | 100%
33 | Y | 38.523-1 | 8.1.6.1.4.3 | Connection Establishment Failure / Logging and reporting / Reporting at intra-NR handover | TP1：UE has connection establishment failure information available，UE performs an Handover procedure（RRCReconfigurationComplete） | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-211479, R5-212115, R5-216307, R5-216312 | An initial version of the test case was added in RAN590e meeting. Keep it open for further potential revision. | 1 | 80% | 80% |  |  | 80% | 80%
34 | Y | 38.523-1 | 8.1.6.1.4.4 | Connection Establishment Failure / Logging and reporting / Reporting at RRC connection re-establishment | TP1：UE has connection establishment failure information available，UE performs an RRC Connection re-establishment procedure（RRCReestablishmentComplete） | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-211480, R5-213617, R5-215681, R5-216311 | An initial version of the test case was added in RAN590e meeting, with some "FFS" content to be filled in the future. And the FFS was filled in 91e meeting. | 1 | 95% | 95% |  |  | 100% | 90%
35 | Y | 38.523-1 | 8.1.6.1.4.5 | Connection Establishment Failure / Logging and reporting / Location Information | TP1：UE has connection establishment failure information available with location information，UE sends the UEInformationResponse message containing connEstFailReport with locationCoordinates （The latest detailed location information, if available.） | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-211481, R5-213618, R5-216313 | An initial version of the test case was added in RAN590e meeting, with some "FFS" content to be filled in the future. And the FFS was filled in 91e meeting. | 1 | 100% (+5%) | 100% (+5%) |  |  | 100% | 100%
36 | Y | 38.523-1 | 8.1.6.1.4.6 | Connection Establishment Failure / Logging and reporting / Reporting of Intra-frequency measurements | TP1：UE has connection establishment failure information available with the intra-frequency measurement result，UE sends a UEInformationResponse message containing the measurement result for intra-frequency neighbouring cell （The latest available radio measurements for any frequency or RAT） TP2：SSB index of the downlink beams of serving cell TP3：The global cell identity of the serving cell | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-211482, R5-213619, R5-216295, R5-216314 | An initial version of the test case was added in RAN590e meeting, with some "FFS" content to be filled in the future. And the FFS was filled in 91e meeting. R5-216295 prosed in RAN5#92e to correct issues. | 1 | 100% (+5%) | 100% (+5%) |  |  | 100% | 100%
37 | Y | 38.523-1 | 8.1.6.1.4.7 | Connection Establishment Failure / Logging and reporting / Reporting of Inter-frequency measurements | TP1：UE has connection establishment failure information available with the inter-frequency measurement result，UE sends a UEInformationResponse message containing the measurement result for inter-frequency neighbouring cell （The latest available radio measurements for any frequency or RAT） TP2：Time stamp, which is the elapsed time between logging and reporting the log. | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-211483, R5-213620, R5-216314 | An initial version of the test case was added in RAN590e meeting, with some "FFS" content to be filled in the future. And the FFS was filled in 91e meeting. | 1 | 90% (-5%) | 90% (-5%) |  |  | 90% | 90%
38 | Y | 38.523-1 | 8.1.6.1.4.8 | Connection Establishment Failure / Logging and reporting / RACH failure report | RACH failure report: - Tried SSB index and number of Random Access Preambles transmitted for each tried SSB in chronological order of attempts; - Contention detected as per RACH attempt; - Indication whether the selected SSB is above or below the rsrp-ThresholdSSB threshold, as per RACH attempt; - Indicator to differentiate the uplink carrier type, e.g.NUL/SUL for one RACH procedure; - TAC of the cell in which the UE performs the RA procedure; - Following frequency location related information of the RA resources used by the UE | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-211484 R5-212107 R5-212116 | An initial version of the test case was added in RAN590e meeting, with some "FFS" content to be filled in the future. | 1 | 70% | 70% |  |  | 70% | 70%
Inter-RAT MDT
66 |  | 38.523-1 | 8.1.6.2 | Inter-RAT MDT | New sub-clause | CMCC | RAN5#92 (Aug-21) |  |  | 0 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
67 | Y | 38.523-1 | 8.1.6.2.1 | Inter-RAT MDT / Immediate MDT / Periodic reporting of E-UTRAN/ Location information | with { UE in NR RRC CONNECTED state and periodic inter-RAT measurement reporting of neighbour E-UTRA cells is configured } ensure that { when { The UE receives reference signal power of E-UTRA cell where measurements are configured } then { UE sends MeasurementReport message with locationInfo included at regular intervals } } | CMCC | RAN5#92 (Aug-21) | R5-216285 |  | 1 | 90% (+90%) | 90% (+90%) |  |  | 100% | 80%
68 | Y | 38.523-1 | 8.1.6.2.2 | Inter-RAT MDT / Logged MDT / E-UTRA Inter-RAT measurement, logging and reporting | with { UE in NR RRC_IDLE state camping normally on NR cell and the UE is able to detect a E-UTRA cell } when { T330 is running } then { UE is logging serving cell idle mode measurements and E-UTRA neighbouring cell measurements } | CMCC | RAN5#92 (Aug-21) | R5-216286 |  | 1 | 90% (+90%) | 90% (+90%) |  |  | 100% | 80%
69 | Y | 38.523-1 | 8.1.6.2.3 | Inter-RAT MDT / Radio Link Failure / Reporting at E-UTRA Inter-RAT handover | TP1: with { UE selects the E-UTRA cell after detection of radio link failure in NR cell } ensure that { when { UE receives a HANDOVER FROM E-UTRA COMMAND message } then { UE transmits an RRCReconfigurationComplete message containing rlf-InfoAvailable and enters NR RRC_CONNECTED state } } TP2: with { UE in RRC_CONNECTED having reported that the UE has radio link failure information available } ensure that { when { UE receives the UEInformationRequest message containing rlf-ReportReq } then { UE sends the UEInformationResponse message containing the measurement result for E-UTRA neighbour cell } } | CMCC | RAN5#92 (Aug-21) | R5-216287 |  | 1 | 90% (+90%) | 90% (+90%) |  |  | 100% | 80%
70 | Y | 38.523-1 | 8.1.6.2.4 | Inter-RAT MDT / Connection Establishment Failure / Logging and reporting / Reporting of E-UTRA Inter-RAT handover | TP1: with {UE has connection establishment failure information available with the E-UTRA measurement result } ensure that { when {UE performs an RRC connection establishment procedure } then {UE sends an RRCSetupComplete message with connEstFailInfoAvailable } } TP2: with {UE having sent an RRCSetupComplete message with connEstFailInfoAvailable } ensure that { when {UE receives a UEInformationRequest message with connEstFailReportReq set to true } then { UE sends a UEInformationResponse message containing the measurement result for E-UTRA neighbouring cell } } | CMCC | RAN5#92 (Aug-21) | R5-216288 |  | 1 | 90% (+90%) | 90% (+90%) |  |  | 100% | 80%
Inter-System MDT
39 |  | 38.523-1 | 8.1.6.3 | Inter-System MDT | New sub-clause | CMCC | RAN5#91-e (May-21) |  |  | 0 | 100% | 100% |  |  | 100% | 100%
Inter-System MDT / Immediate MDT
40 |  | 38.523-1 | 8.1.6.3.1 | Inter-System MDT / Immediate MDT | New sub-clause | CMCC | RAN5#91-e (May-21) |  |  | 0 | 100% | 100% |  |  | 100% | 100%
41 | Y | 38.523-1 | 8.1.6.3.1.1 | Inter-System MDT / Immediate MDT / Measurement reporting / Bluetooth measurement collection | Entry condition for event is met，UE sends MeasurementReport message with Bluetooth measurement results | CMCC | RAN5#91-e (May-21) | R5-213605 |  | 1 | 50% | 50% |  |  | 100% | 0%
42 | Y | 38.523-1 | 8.1.6.3.1.2 | Inter-System MDT / Immediate MDT / Measurement reporting / WLAN measurement collection | Entry condition for event is met，UE sends MeasurementReport message with WLAN measurement results | CMCC | RAN5#91-e (May-21) | R5-213606 |  | 1 | 50% | 50% |  |  | 100% | 0%
43 | Y | 38.523-1 | 8.1.6.3.1.3 | Inter-System MDT / Immediate MDT / Measurement reporting / sensor information | If sensor information is available, | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-212494, R5-216294 | An initial version of the test case was added in RAN5#91e meeting, R5-216294 prosed in RAN5#92e to correct issues. | 1 | 100% (+20%) | 100% (+20%) |  |  | 100% | 100%
Inter-System MDT / Logged MDT
44 |  | 38.523-1 | 8.1.6.3.2 | Inter-System MDT / Logged MDT | New sub-clause |  | RAN5#91-e (May-21) |  |  | 0 | 100% | 100% |  |  | 100% | 100%
45 | Y | 38.523-1 | 8.1.6.3.2.1 | Inter-System MDT / Logged MDT / Logging and reporting / Bluetooth measurement collection | The Bluetooth measurement results consist of, per wireless network served by the Bluetooth beacon: - MAC address; - RSSI for Bluetooth. | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-212495 | An initial version of the test case was added in RAN5#91e meeting, | 1 | 80% | 80% |  |  | 80% | 80%
46 | Y | 38.523-1 | 8.1.6.3.2.2 | Inter-System MDT / Logged MDT / Logging and reporting / WLAN measurement collection | The WLAN measurement results consist of, per wireless network served by the WLAN AP: - BSSID, SSID and HESSID; - RSSI for WLAN; - RTT. | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-213612 | An initial version of the test case was added in RAN5#91e meeting, | 1 | 80% | 80% |  |  | 80% | 80%
47 | Y | 38.523-1 | 8.1.6.3.2.3 | Inter-System MDT / Logged MDT / Logging and reporting / sensor information | TP1：sensor information (i.e. uncompensated barometric pressure measurement, UE speed and UE orientation) can be included, if available in the UE when the measurement was taken. | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-213613 | An initial version of the test case was added in RAN5#91e meeting, | 1 | 80% | 80% |  |  | 80% | 80%
Inter-System MDT / Radio Link Failure
48 |  | 38.523-1 | 8.1.6.3.3 | Inter-System MDT / Radio Link Failure | New sub-clause |  | RAN5#91-e (May-21) |  |  | 0 | 100% | 100% |  |  | 100% | 100%
49 | Y | 38.523-1 | 8.1.6.3.3.1 | Inter-System MDT / Radio Link Failure / Logging and reporting / Bluetooth measurement collection | WLAN and Bluetooth measurement results, if were configured prior RLF and are available for reporting; | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-213614 | An initial version of the test case was added in RAN5#91e meeting, | 1 | 80% | 80% |  |  | 80% | 80%
50 | Y | 38.523-1 | 8.1.6.3.3.2 | Inter-System MDT / Radio Link Failure / Logging and reporting / WLAN measurement collection |  | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-213615 | An initial version of the test case was added in RAN5#91e meeting, | 1 | 80% | 80% |  |  | 80% | 80%
51 | Y | 38.523-1 | 8.1.6.3.3.3 | Inter-System MDT / Radio Link Failure / Logging and reporting / sensor information | If sensor information is available, | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-213616 | An initial version of the test case was added in RAN5#91e meeting, | 1 | 80% | 80% |  |  | 80% | 80%
Inter-System MDT / Connection Establishment Failure
52 |  | 38.523-1 | 8.1.6.3.4 | Inter-System MDT / Connection Establishment Failure | New sub-clause |  | RAN5#92 (Aug-21) |  |  | 0 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
53 | Y | 38.523-1 | 8.1.6.3.4.1 | Inter-System MDT / Connection Establishment Failure / Logging and reporting / Bluetooth measurement collection | The latest Bluetooth measurement results, if available. | Huawei, Hisilicon | RAN5#92 (Aug-21) | R5-216296 | An initial version of the test case was added in RAN5#92e meeting, | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
54 | Y | 38.523-1 | 8.1.6.3.4.2 | Inter-System MDT / Connection Establishment Failure / Logging and reporting / WLAN measurement collection | The latest WLAN measurement results, if available; | Huawei, Hisilicon | RAN5#92 (Aug-21) | R5-214829 | An initial version of the test case was added in RAN5#92e meeting, | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
55 | Y | 38.523-1 | 8.1.6.3.4.3 | Inter-System MDT / Connection Establishment Failure / Logging and reporting / sensor information | If sensor information is available, | Huawei, Hisilicon | RAN5#92 (Aug-21) | R5-214830 | An initial version of the test case was added in RAN5#92e meeting, | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
SON: UE RACH reporting
72 |  | 38.523-1 | [8.1.6.5] | SON / RACH reporting | New sub-clause |  | RAN5#93 (Nov-21) |  |  | 0 | 0% | 0% |  |  | 0% | 0%
73 | Y | 38.523-1 | [8.1.6.5.1] | SON / RACH logging and reporting | RACH logging and reporting: configuring and looging TBD what RACH reporting purposes feasible to be covered. Aim is to include the differnent type of report items in one test case. Existing types as per 38.331 RA-Report-r16 IE are: accessRelated, beamFailureRecovery, reconfigurationWithSync, ulUnSynchronized, schedulingRequestFailure, noPUCCHResourceAvailable, requestForOtherSI. | Ericsson | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
56 |  | 38.523-2 | <Clause> | <Title> | Add new ICS for MDT and SON capabilities |  | RAN5#90-e (Feb-21) |  |  | 0.1 | 50% | 50% |  |  | 50% | 50%
57 |  | 38.523-2 | 4.1 | Introduction the applicability statement for new test cases for NR Immediate MDT | Add test case applicability for 8.1.6.1.1 Immediate MDT test cases 8. | CMCC | RAN5#90-e (Feb-21) | R5-211487 |  | 0.1 | 50% | 50% |  |  | 100% | 0%
58 |  | 38.523-2 | 4.1 | Adding applicability for new logged MDT test cases | Add test case applicability statements for 8.1.6.1.2 Logged MDT test cases | ZTE | RAN5#90-e (Feb-21) | R5-211488 |  | 0.1 | 90% | 90% |  |  | 100% | 80%
59 |  | 38.523-2 | 4.1 | Adding applicability for new MDT test cases | Addition of applicability for new MDT TC 8.1.6.1.3.x | MediaTek | RAN5#90-e (Feb-21) | R5-210801 |  | 0.1 | 100% (+60%) | 100% (+60%) |  |  | 100% | 100%
60 |  | 38.523-2 | 4.1 | Correction to NR TC applicability for MDT | Add test case applicability statements for Connection Establishment Failure test cases. | CMCC, Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-211489 R5-212040 R5-213636 | R5-213636 is the revision of CEF test cases in RAN5#91e meeting. | 0.1 | 100% | 100% |  |  | 100% | 100%
61 |  | 38.523-2 | 4.1 | Applicability statement for new test cases for Inter-System Immediate MDT | Add test case applicability statements for 8.1.6.3.1.x Inter-System MDT / Immediate MDT test cases. | CMCC, Huawei, Hisilicon | RAN5#91-e (May-21) | R5-212041 R5-213635 | R5-213635 is for the applicability of 8.1.6.3.1.3., 8.1.6.3.2.1/2/3 and 8.1.6.3.3.1/2/3. | 0.1 | 100% | 100% |  |  | 100% | 100%
62 |  | 38.523-2 | 4.1 | Applicability for NR MDT inter-system TCs | Add test case applicability statements for 8.1.6.3.2.x Inter-System MDT / Logged MDT test cases. | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-213635 | R5-213635 is for the applicability of 8.1.6.3.1.3., 8.1.6.3.2.1/2/3 and 8.1.6.3.3.1/2/3. | 0.1 | 100% | 100% |  |  | 100% | 100%
63 |  | 38.523-2 | 4.1 | Applicability for NR MDT inter-system TCs | Add test case applicability statements for 8.1.6.3.3.x Inter-System MDT / Radio Link Failure test cases. | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-213635 | R5-213635 is for the applicability of 8.1.6.3.1.3., 8.1.6.3.2.1/2/3 and 8.1.6.3.3.1/2/3. | 0.1 | 100% | 100% |  |  | 100% | 100%
64 |  | 38.523-2 | 4.1 | Applicability for NR MDT inter-system TCs | Add test case applicability statements for 8.1.6.3.4.x Inter-System MDT / Connection Establishment Failure test cases. | Huawei, Hisilicon | RAN5#92 (Aug-21) | R5-214831 | R5-214831 is for the applicability of 8.1.6.3.4.1/2/3 | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
65 |  | 38.523-2 | <Clause> | <Title> | Add test case applicability statements for SON UE RACH reporting test cases. | Ericsson | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
TBD |  | 38.523-3 | FFS | TTCN test model updates | Placeholder: FFS if needed |  | TBD |  |  | 1 | 0% | 0% |  |  | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.