## Cover sheet
3GPP TSG-RAN WG5 Meeting #92-e | [8 empty] | R5-214539
Electronic meeting, 16th - 27th Aug 2021
Agenda Item: | 7.4.2
Source: | China Telecom
Title: | WP UE Conformance Test Aspects for add support of NR DL 256QAM for FR2 RAN5#91e
Work item code: | NR_DL256QAM_FR2-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
Until RAN#89e, the core part of Rel-16 WI ‘Add support of NR DL 256QAM for FR2’ is 100% completed, and the performance part is 50% completed and is targeting March 2021. The corresponding UE conformance specifications are now required to be implemented in 3GPP RAN WG5. The objective of this work item is to define the UE conformance requirements corresponding to WID on Add support of NR DL 256QAM for FR2. This work item will cover RF and Demod conformance test specifications for FR2 DL 256QAM.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 82% (+38%) | 0 | 3
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR2) |  | 81.8% (+38%) | 0 | 3
FR2 |  | 81.8% (+38%) | 0 | 3
NSA Option 3 (EN-DC) |  | 81.8% (+38%) | 0 | 3
FR2 |  | 81.8% (+38%) | 0 | 3
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR2 |  |  |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  |  | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
NR RF/RRM
FR2 RF common parts | 38.521-2 | 100% |  |  | 100% |  |  |  |  | 100%
FR2 RF Rx test cases | 38.521-2 Rx | 70% | 0 | 1 | 70% | 0 | 1 |  |  | 70% | 0 | 1
RF Demod/QSI test cases | 38.521-4 | 87.5% (+57.9%) | 0 | 2 | 87.5% (+57.9%) | 0 | 2 |  |  | 87.5% (+57.9%) | 0 | 2
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 90% (+90%) |  |  | 90% (+90%) |  |  |  |  | 90% (+90%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0% |  |  |  |  | 0%
5 References
[1] RP-202371 | New WID on UE Conformance Test Aspects - Add support of NR DL 256QAM for frequency range 2 (FR2), China Telecom, RAN#90-e
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance Test Aspects for add support of NR DL 256QAM for FR2 | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_DL256QAM_FR2-UEConTest
WP Scope: |  | The objective of this work item is to define the UE conformance requirements corresponding to WID on Add support of NR DL 256QAM for FR2. This work item will cover RF and Demod conformance test specifications for FR2 DL 256QAM.
WP Resp: |  | Wu Jingzhou |  |  | wujingzhou@chinatelecom.cn | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR2 | FR2
[15 empty] | 81.8% (+38%) | 81.8% (+38%)
[15 empty] | 10 | 10
[15 empty] | 3.7 | 3.7
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
NR RF/RRM
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
1 |  | 38.521-2 | A.3.3.5 | FRC for receiver requirements for 256QAM | Add FRC for FR2 256QAM receiver requierments defined in TS38.101-2 | Nokia | RAN5#92 (Aug-21) | R5-211919 |  | 0.1 | 100% | 100% | 100% |  | 100% | 100%
TS 38.521-2: FR2 RF test cases - Rx
2 | Y | 38.521-2 Rx | 7.4 | Maximum input level | Add test requirement of maximum input level for 256QAM in the existing test case. | Nokia | RAN5#92 (Aug-21) | R5-211919 R5-214011 | Test configuration details for DL 256QAM are TBD. Relaxation of DL power for 256 QAM is FFS. | 1 | 70% | 70% | 70% |  | 70% | 70%
TS 38.521-4: Demod/QSI reporting test cases - Common parts (applicability, Annexes)
3 |  | 38.521-4 | Annexes |  | 1. Add simplified TDLD30 channel model in clause B.2.1, which is defined for PDSCH demodulation for 256QAM. 2. Add new FRC in clause A.3.2.2.5 for the new TC defined for FR2 256QAM PDSCH demodulation in clause 7.2.2.2.1. 3. Add new RMC in clause A.4 for the the new TC for CQI reporting test with CQI Table2 under fading condition. | China Telecom | RAN5#92 (Aug-21) | R5-212064 R5-214533 |  | 0.1 | 100% (+30%) | 100% (+30%) | 100% (+30%) |  | 100% | 100%
4 |  | 38.521-4 | 7.1.1.3 | Applicability of requirements for optional UEfeatures | Applicability rules for section 7 PDSCH normal and SDR test cases. | China Telecom | RAN5#92 (Aug-21) | R5-212063 |  | 0.1 | 100% (+30%) | 100% (+30%) | 100% (+30%) |  | 100% | 100%
5 |  | 38.521-4 | 8.1.1.3 | Applicability of requirements for optional UEfeatures | Applicability rules for section 8 CQI reporting test cases. | China Telecom | RAN5#92 (Aug-21) | R5-212063 |  | 0.1 | 100% (+30%) | 100% (+30%) | 100% (+30%) |  | 100% | 100%
TS 38.521-4: Demod/QSI reporting test cases
6 | Y | 38.521-4 | 7.2.2.2.1_3 | 2Rx TDD FR2 PDSCH mapping Type A performance - 2x2 MIMO with 256QAM for SA and NSA (Rel-16 and forward) | New test case for PDSCH demodulation for 256QAM. | China Telecom | RAN5#92 (Aug-21) | R5-216076 | The test applicability dur to maximum achievable SNR is TBD. | 1 | 90% (+90%) | 90% (+90%) | 90% (+90%) |  | 90% | 90%
7 |  | 38.521-4 | 7.5 | Sustained downlink data rate provided by lower layers | Specify the test procedure for UE supporting DL FR2 256QAM on the selected band(s). |  | RAN5#92 (Aug-21) |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0%
8 | Y | 38.521-4 | 8.2.2.2.2.1_1 | 2Rx TDD FR2 aperiodic CQI reporting under fading performance for both SA and NSA – 256QAM (Rel-16 and forward) | New test case for CQI reporting test with CQI Table2 under fading condition. | Huawei, HiSilicon | RAN5#92 (Aug-21) | R5-214012 R5-215950 | The test applicability dur to maximum achievable SNR is TBD. | 1 | 90% (+40%) | 90% (+40%) | 90% (+40%) |  | 90% | 90%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
9 |  | 38.522 | 4.1.4 | Performance conformance test cases | Add applicability statements for the new test case introduced in 38.521-4. | All companies | RAN5#92 (Aug-21) | R5-214534 R5-216077 |  | 0.1 | 90% (+90%) | 90% (+90%) | 90% (+90%) |  | 90% | 90%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TR 38.905: Test Point analysis receiver and transmitter test cases
10 |  | 38.905 | 4.2.1 | Test point analysis for FR2 | Adding TP analysis for test cases in 38.521-1 | All companies | RAN5#92 (Aug-21) |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.