## Cover sheet
3GPP TSG-RAN WG5 Meeting #92-e | [10 empty] | R5-214579
Electronic Meeting, 16th Aug - 27th Aug 2021
Agenda Item: | 7.4.2
Source: | CATT, CMCC
Title: | WP UE Conformance Test Aspects - B1C Signal in A-BDS Positioning System Support for LTE and NR
Work item code: | B1C_BDS_pos_UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At the RAN#89-e meeting a Rel-16 RAN5 work item for B1C Signal in BDS Positioning System Support for LTE and NR (B1C_BDSpos_UEConTest) was approved [1]. The purpose of this present document is to provide a work plan for the RAN5 work item for this. The work plan is updated after each RAN5 meeting to give the status of this work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+29%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 100% (+30%)
FR1 |  | 100% (+30%)
FR2 |  | 100% (+30%)
FR1 + FR2
NSA Option 3 (EN-DC) |  | 100% (+30%)
FR1 |  | 100% (+30%)
FR2 |  | 100% (+30%)
FR1 + FR2
LTE |  | 100% (+27.1%)
FDD |  | 100% (+27.1%)
TDD |  | 100% (+27.1%)
FDD + TDD
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC) | [8 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FDD |  |  | TDD |  |  | FDD + TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1 | 100% |  |  | 100% |  |  | 100% | [5 empty] | 100% |  |  | 100% | [5 empty] | 100% |  |  | 100%
UE Positioning Protocol test cases | 37.571-2 | 100% | [20 empty] | 100% |  |  | 100%
Applicability and ICS UE Positioning test cases | 37.571-3 | 100% |  |  | 100% |  |  | 100% | [5 empty] | 100% |  |  | 100% | [5 empty] | 100% |  |  | 100%
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5 | 100% (+60%) |  |  | 100% (+60%) |  |  | 100% (+60%) | [5 empty] | 100% (+60%) |  |  | 100% (+60%) | [5 empty] | 100% (+60%) |  |  | 100% (+60%)
5 References
[1] RP-201777 | New WI Proposal: UE Conformance Test Aspects - B1C Signal in BDS Positioning System Support for LTE and NR – CATT, CMCC (Supporting companies: CATT, Spirent Communications, ZTE, Rohde & Schwarz, MediaTek Inc., Huawei, HiSilicon, CMCC, China Unicom, China Telecom, CAICT)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects - B1C Signal in A-BDS Positioning System Support for LTE and NR | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [8 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | B1C_BDS_pos_UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE B1C Signal in A-BDS Positioning System Support for LTE and NR comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [14 empty] | vs Area
WP Resp: |  | Huiying Zhang, CATT |  |  | zhanghuiying@catt.cn | [5 empty] | WP item completion |  |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC) |  |  | LTE
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) | LTE |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2 | FDD | TDD | FDD + TDD
[14 empty] | Overall |  | 100% (+30%) | 100% (+30%) |  | 100% (+30%) | 100% (+30%) |  | 100% (+27.1%) | 100% (+27.1%)
[14 empty] | Number of WP items |  | 7 (+1) | 7 (+1) | 0 | 7 (+1) | 7 (+1) | 0 | 9 (+1) | 9 (+1) | 0
[14 empty] | Sum weight of WP items |  | 2.9 (+1) | 2.9 (+1) | 0 | 2.9 (+1) | 2.9 (+1) | 0 | 3.1 (+1) | 3.1 (+1) | 0
[14 empty] | Contribution by work plan analysis |  | 5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
UE Positioning
TS 37.571-1: UE Positioning -Performance
|  | 37.571-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 37.571-1 | 2, 3 | Introduction of BDS B1C Signal test contents | Adding reference of B1C ICD and symbol of B1C | CATT | RAN5#89-e (Nov-20) | R5-206774 |  | 0.2 | 100% | 100% | 100% | 100% |  | 100% | 100% |  | 100% | 100% |  | 100% | 100%
2 |  | 37.571-1 | 4 | Introduction of BDS B1C Signal test conditions | 1. Adding BDS B1C parameters in GNSS multi-path conditions 2. Adding BDS B1C into multiple satellite signals supported by UE | CATT | RAN5#89-e (Nov-20) | R5-206774 |  | 0.2 | 100% | 100% | 100% | 100% |  | 100% | 100% |  | 100% | 100% |  | 100% | 100%
3 |  | 37.571-1 | 7 | Introduction of BDS B1C minimum performance requirements in E-UTRA | Adding note for BDS B1C in E-UTRA A-GNSS minimum performance requirements | CATT | RAN5#89-e (Nov-20) | R5-206774 |  | 0.2 | 100% | 100% | 100% | 100% |  | 100% | 100% |  | 100% | 100% |  | 100% | 100%
4 |  | 37.571-1 | 13 | Introduction of BDS B1C minimum performance requirements in NR | Adding note for BDS B1C in NR A-GNSS minimum performance requirements | CATT | RAN5#89-e (Nov-20) | R5-206774 |  | 0.2 | 100% | 100% | 100% | 100% |  | 100% | 100% |  | 100% | 100% |  | 100% | 100%
TS 37.571-2: UE Positioning -Protocol
|  | 37.571-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
5 |  | 37.571-2 | 5 | Addition of BDS B1C into default conditions for E-UTRAN | Updating GNSS Auxiliary Information in Table 5.4.1.1-1 | CATT | RAN5#89-e (Nov-20) | R5-206424 |  | 0.1 | 100% |  |  | 100% | [7 empty] | 100% | 100%
6 |  | 37.571-2 | 7 | Addition of BDS B1C into protocol conformance test cases for E-UTRAN | Adding pc_BDS_B1C in MultiFreqAGNSS condition | CATT | RAN5#89-e (Nov-20) | R5-206424 |  | 0.1 | 100% |  |  | 100% | [7 empty] | 100% | 100%
TS 37.571-3: Applicability and ICS UE Positioning test cases
7 |  | 37.571-3 | <Clause> | Addition of BDS B1C testing contents in TS 37.571-3 | Adding test case applicabilities for BDS B1C testing | CATT | RAN5#89-e (Nov-20) | R5-206425 |  | 0.1 | 100% | 100% | 100% | 100% |  | 100% | 100% |  | 100% | 100% |  | 100% | 100%
TS 37.571-4: UE Positioning test suites (TTCN)
|  | 37.571-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 37.571-4 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 37.571-5: UE Positioning test scenarios and assistance data
|  | 37.571-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
8 |  | 37.571-5 | 4,6 | Addition of test scenarios for BDS B1C minimum performance and signalling tests | Adding assistance data definitions and values for BDS B1C | Spirent Communications, CATT, CAICT | RAN5#93 (Nov-21) | R5-211340 R5-211812 R5-215711 R5-216006 |  | 1 | 100% (+60%) | 100% (+60%) | 100% (+60%) | 100% (+60%) |  | 100% | 100% |  | 100% | 100% |  | 100% | 100%
9 |  | 37.571-5 | Annex B | Addition of BDS B1C data files |  | Spirent Communications, CATT, CAICT | RAN5#92 (Aug-21) | R5-215711 R5-216006 |  | 1 | 100% (+100%) | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100% |  | 100% | 100% |  | 100% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.