## Cover sheet
3GPP TSG RAN WG5 Meeting #92-e | [8 empty] | R5-215486
Electronic Meeting, August 16 - 27, 2021
Agenda Item: | 7.4.2
Source: | T-Mobile USA, CMCC
Title: | WP B41 n41 PC1.5
Work item code: | LTE_NR_B41_Bn41_PC29dBm-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to the parent WID (LTE_NR_B41_Bn41_PC29dBm, RAN4), analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-16. Specific updates will be to MPR, A-MPR, ACLR, A-SEM and A-Spurious. This includes enabling single component carrier UL operation (no CA) for NR n41 UE Power Class 1.5 (29 dBm) to be utilized for LTE-NR Dual Connectivity, and NR 2x2 non-coherent UL MIMO and NR 29 dBm operation with transparent transmit diversity.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 58% (+58%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 74.8% (+74.8%)
74.8% (+74.8%)
NSA Option 3 (EN-DC) |  | 5% (+5%)
5% (+5%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  |  | Completion | Number of new completed test cases | Number of new test cases
LTE
5GS
NR RF/RRM
FR1 RF Tx test cases | 38.521-1 Tx | 78.3% (+78.3%) |  |  | 78.3% (+78.3%)
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx | 0% | [7 empty] | 0%
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0%
5 References
[1] RP-211443 | New WID - UE Conformance Test Aspects - 29 dBm UE Power Class for LTE Band 41and NR Band n41
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects - 29 dBm UE Power Class for LTE Band 41and NR Band n41 | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_NR_B41_Bn41_PC29dBm-UEConTest
WP Scope: |  | The objective of this work item is to define the UE conformance requirements corresponding to the parent WID, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-16. Specific updates will be to MPR, A-MPR, ACLR, A-SEM and A-Spurious. This includes enabling single component carrier UL operation (no CA) for NR n41 UE Power Class 1.5 (29 dBm) to be utilized for LTE-NR Dual Connectivity, and NR 2x2 non-coherent UL MIMO and NR 29 dBm operation with transparent transmit diversity.
WP Resp: |  | Scott Probasco |  |  | scott.probasco@t-mobile.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
[15 empty] | 74.8% (+74.8%) | 5% (+5%)
[15 empty] | 26 (+26) | 8 (+8)
[15 empty] | 4.9 (+4.9) | 1.6 (+1.6)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
5GS
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.521-1 Tx | 6.2.1.3 | MOP Minimum conformance requirements | add the power class and toleranxe values for the band, including descriptive text after the table | T-Mobile US | RAN5#92 (Aug-21) |  | R5-216000 | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
2 |  | 38.521-1 Tx | 6.2.1.4.2 | MOP test procedure | update the test procedure | T-Mobile US | RAN5#92 (Aug-21) |  | R5-216000 | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
3 |  | 38.521-1 Tx | 6.2.1.4.3 | MOP message contents | update the message contents, if needed | T-Mobile US | RAN5#92 (Aug-21) |  | R5-216000 | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
4 |  | 38.521-1 Tx | 6.2.1.5 | MOP test requirement | add the test requirement for PC1.5 | T-Mobile US | RAN5#92 (Aug-21) |  | R5-216000 | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
5 |  | 38.521-1 Tx | 6.2.2.3 | MPR Minimum conformance requirements | add the MPR for dual TX |  | RAN5#92 (Aug-21) |  | already done | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
6 |  | 38.521-1 Tx | 6.2.2.4.1 | MPR initial conditions | test configuration table for PC 1.5 | T-Mobile US | RAN5#92 (Aug-21) |  | R5-216001 | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
7 |  | 38.521-1 Tx | 6.2.2.4.2 | MPR test procedure | update test procedure for PC 1.5 | T-Mobile US | RAN5#92 (Aug-21) |  | R5-216001 | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
8 |  | 38.521-1 Tx | 6.2.2.4.2 | MPR message contents | update the message contents | T-Mobile US | RAN5#92 (Aug-21) |  | R5-216001 | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
9 |  | 38.521-1 Tx | 6.2.2.4.2 | MPR test requirements | update the test requirements for PC1.5 | T-Mobile US | RAN5#92 (Aug-21) |  | R5-216001 | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
10 |  | 38.521-1 Tx | 6.2.3.3.2 | A-MPR minimum conformance requirements for NS_04 | add the A-MPR for dual TX | T-Mobile US | RAN5#92 (Aug-21) |  | R5-216002 | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
11 |  | 38.521-1 Tx | 6.2.3.4.1 | A-MPR test configuration for NS_04 PC1.5 | test configuration table for PC 1.5 | T-Mobile US | RAN5#92 (Aug-21) |  | R5-216002 | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
12 |  | 38.521-1 Tx | 6.2.3.4.2 | A-MPR test procedure | update the test procedure | T-Mobile US | RAN5#92 (Aug-21) |  | R5-216002 | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
13 |  | 38.521-1 Tx | 6.2.3.4.3.4 | A-MPR message contents | update message contents exceptions for network signalling value "NS_04" | T-Mobile US | RAN5#92 (Aug-21) |  | R5-216002 | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
14 |  | 38.521-1 Tx | 6.2.3.5 | A-MPR test requirements | update test requirements for network signalling value "NS_04" PC1.5 | T-Mobile US | RAN5#92 (Aug-21) |  |  | 0.2 | 0% | 0% |  |  | 0%
15 |  | 38.521-1 Tx | 6.2.4.3 | Configured Tx Power Minimum conformance requirements | add the configured tx power requirements | CMCC | RAN5#92 (Aug-21) |  | R5-214476 | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
16 |  | 38.521-1 Tx | 6.2.4.4.3 | Configured Tx Power message contents | update message contents, if needed | CMCC | RAN5#92 (Aug-21) |  |  | 0.2 | 0% | 0% |  |  | 0%
17 |  | 38.521-1 Tx | 6.2.4.5 | Configured Tx Power; Test Requirements | update test requirements | CMCC | RAN5#92 (Aug-21) |  |  | 0.2 | 0% | 0% |  |  | 0%
18 |  | 38.521-1 Tx | 6.2D.1.3 | MOP for UL MIMO | add the minimum conformance requirements | CMCC | RAN5#92 (Aug-21) |  | R5-214477 | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
19 |  | 38.521-1 Tx | 6.2D.1.5 | MOP for UL MIMO | add the test requirements | CMCC | RAN5#92 (Aug-21) |  | R5-215999 | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
20 |  | 38.521-1 Tx | 6.5.2.4.1.3 | NR ACLR minimum conformance requirements | minimum conformance requirement | CMCC | RAN5#92 (Aug-21) |  | already done | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
21 |  | 38.521-1 Tx | 6.5.2.4.1.4.2 | NR ACLR test procedure | update test procedure for PC 1.5 | CMCC | RAN5#92 (Aug-21) |  |  | 0.2 | 0% | 0% |  |  | 0%
22 |  | 38.521-1 Tx | 6.5.2.4.1.4.3 | NR ACLR message contents | update message contents for PC 1.5 | CMCC | RAN5#92 (Aug-21) |  |  | 0.2 | 0% | 0% |  |  | 0%
23 |  | 38.521-1 Tx | 6.5.2.4.1.5 | NR ACLR test requirement | update test requirement for PC1.5 | CMCC | RAN5#92 (Aug-21) |  | R5-214479 | 0.2 | 100% (+100%) | 100% (+100%) |  |  | 100%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Tx
|  | 38.521-3 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
24 |  | 38.521-3 Tx | 6.2B.1.1.3 | MOP for Intra-Band Contiguous EN-DC | Minimum conformance requirements |  | RAN5#93 (Nov-21) |  |  | 0.2 | 0% |  | 0% |  |  | 0%
25 |  | 38.521-3 Tx | 6.2B.1.2.3 | MOP for Intra-Band Non-Contiguous EN-DC | Minimum conformance requirements |  | RAN5#93 (Nov-21) |  |  | 0.2 | 0% |  | 0% |  |  | 0%
26 |  | 38.521-3 Tx | 6.2B.3.1.3 | A-MPR for Intra-band contiguous EN-DC | Minimum conformance requirements |  | RAN5#93 (Nov-21) |  |  | 0.2 | 0% |  | 0% |  |  | 0%
27 |  | 38.521-3 Tx | 6.2B.3.1.3.2.1 | A-MPR for Intra-band contiguous EN-DC | A-MPRIM3 for NS_04 to meet -13 dBm |  | RAN5#93 (Nov-21) |  |  | 0.2 | 0% |  | 0% |  |  | 0%
28 |  | 38.521-3 Tx | 6.2B.3.1.3.2.2 | A-MPR for Intra-band contiguous EN-DC | A-MPR for NS_04 to meet -25 dBm |  | RAN5#93 (Nov-21) |  |  | 0.2 | 0% |  | 0% |  |  | 0%
29 |  | 38.521-3 Tx | 6.2B.3.2.3.1 | A-MPR minimum conformance requirements | A-MPR minimum conformance requirements for NS_04 |  | RAN5#93 (Nov-21) |  |  | 0.2 | 0% |  | 0% |  |  | 0%
30 |  | 38.521-3 Tx | 6.2B.4.1.0.1.1 | Configured Output Power for EN-DC | Minimum Conformance Requirements Intra-band contiguous EN-DC |  | RAN5#93 (Nov-21) |  |  | 0.2 | 0% |  | 0% |  |  | 0%
31 |  | 38.521-3 Tx | N.1 | Indication of modified MPR behaviour | update definitions of the bits in the field modifiedMPRbehavior |  | RAN5#93 (Nov-21) |  |  | 0.2 | 0% |  | 0% |  |  | 0%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
32 |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
33 |  | 38.522 | 4 | Test case conditions and selection criteria | set the conditions and selection criteria |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
34 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Add test case applicability statements for the updated test cases introduced for 38.521-1 & 38.521-3. |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.