## Cover sheet
3GPP TSG-RAN WG5 Meeting #92-e | [10 empty] | R5-216355
Electronic Meeting, Aug 16 - 27, 2021
Agenda Item: | 7.4.2
Source: | Rapporteurs (CMCC, Nokia)
Title: | WP - UE Conformance Test Aspects for Support of NR Industrial Internet of Things (IoT)
Work item code: | NR_IioT-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At the RAN#88-e meeting a Rel-16 RAN5 work item for Support of NR Industrial Internet of Things (NR_IIOT-UEConTest) was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item. Section 2 gives an overview of the work item status; WP Sheet lists the planned IIOT for NR test scenarios and the detailed status.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 95% (+18%) | 4 (+4) | 6 (-1)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 95.2% (+24%) | 4 (+4) | 5
FR1 |  | 95.2% (+24%) | 4 (+4) | 5
FR2 |  | 95.2% (+24%) | 4 (+4) | 5
LTE |  | 95.2% (+0%) | 0 | 1 (-6)
FDD |  | 95.2% (+0%) | 0 | 1 (-1)
TDD |  | 95.2% (+0%) | 0 | 1 (-1)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FDD |  |  | TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
LTE RAN and CN protocols
Protocol test cases | 36.523-1 | 95% (+0%) | 0 | 1 (-1) | [7 empty] | 95% | 0 | 1 (-1) | 95% | 0 | 1 (-1)
Applicability Protocol test cases | 36.523-2 | 95% (+0%) | [9 empty] | 95% |  |  | 95%
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1 | 85% (+5%) |  |  | 85% (+5%) |  |  | 85% (+5%)
Common ICS | 38.508-2 | 85% (+5%) |  |  | 85% (+5%) |  |  | 85% (+5%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 99% (+30%) | 4 (+4) | 5 | 99% (+30%) | 4 (+4) | 5 | 99% (+30%) | 4 (+4) | 5
Applicability Protocol test cases | 38.523-2 | 70% (+10%) |  |  | 70% (+10%) |  |  | 70% (+10%)
Test suites (TTCN) | 38.523-3
3. References
[1] RP-200757 | New WI Proposal: UE Conformance Test Aspects – Support of NR Industrial Internet of Things (IoT) – CMCC, Nokia (Supporting companies: Huawei, Hisilicon, ZTE, Orange, Qualcomm, Ericsson, Bureau Veritas, Dish Network, Motorola Mobility, NTT Docomo, R&S, KTL, Vodafone, Anritsu)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance Test Aspects for Support of NR Industrial Internet of Things (IoT) | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_IioT-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for Support of NR Industrial Internet of Things (IoT) comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [13 empty] | vs Area
WP Resp: |  | Dan Song, CMCC |  |  | songdan@chinamobile.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | LTE
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | LTE |  | FR1 | FR2 | FDD | TDD
[15 empty] | 95.2% (+24%) | 95.2% (+24%) | 95.2% (+0%) | 95.2% (+0%)
[15 empty] | 8 | 8 | 2 | 2
[15 empty] | 6.3 | 6.3 | 1.2 (-1) | 1.2 (-1)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
10 |  | 36.508 | 4, 7 | General and RRM Test Environment | Introduction of General and RRM Test Environment for Rel-16 HST in LTE | CMCC | RAN5#93 (Nov-21) |  |  | 0.2
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Layer 2
11 | Y | 36.523-1 | 7.3.6.2 | Ethernet header compression and decompression / Correct functionality of ethernet header compression and decompression | TS 36.323 cl5.14.2/3/4/5/6.1/6.2 Verifying UE can perform EHC in LTE correctly. | Nokia | RAN5#89-e (Nov-20) | R5-206401 | Kangas Matti <matti.kangas@nokia.com> Keep it open for detailed technical review and potential revision 36.523-2: R5-206402 | 1 | 95% |  | 95% (+0%) |  |  |  | 95% | 95%
TS 36.523-2: Applicability for Protocol test cases
12 |  | 36.523-2 | 4, A.4.4 | Recommended Test Case Applicability, ICS Proforma | Add test case applicability statements for the new test cases introduced in 38.523-1 | Nokia | RAN5#89-e (Nov-20) | R5-206402 | Kangas Matti <matti.kangas@nokia.com> Keep it open for detailed technical review and potential revision | 0.2 | 95% |  | 95% (+0%) |  |  |  | 95% | 95%
TS 36.523-3: Protocol test suites (TTCN)
|  | 36.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4, 6 | General and Signaling Test Environment for IIOT testing | Introduction of General and Signaling Test Environment for IIOT testing | Huawei, Ericsson | RAN5#90-e (Feb-21) | R5-206394, R5-216256 | Liu Bing (Leo)<leo.liubing@huawei.com> Keep it open for potential missing content that needs to be added | 0.5 | 85% (+5%) | 85% (+5%) |  |  | 85% | 85%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.508-2 | <Clause> | Introduction of common implementation conformance statements for Rel-16 NR-IIOT |  | Huawei, Ericsson, CMCC | RAN5#90-e (Feb-21) | R5-206395, R5-216257, R5-216258, | Liu Bing (Leo)<leo.liubing@huawei.com> Keep it open for potential missing content that needs to be added | 0.3 | 85% (+5%) | 85% (+5%) |  |  | 85% | 85%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Layer 2
4 | Y | 38.523-1 | 7.1.1.3.11 | Collision handling based on Logical channel prioritization | TS 38.321 cl 5.4.1/cl 5.4.2.1 1. Verifying UE can handle conlission between dynamic grant and configured grant with different priority. 2. Verifying UE can autonomously retransmit deprioritized configured UL grant | Huawei | RAN5#90-e (Feb-21) | R5-211313 | Liu Bing (Leo)<leo.liubing@huawei.com> An initial version of the test case text was provided through R5-211313 in RAN5#90e meeting. Keep it open for detailed technical review and potential revisions. | 1 | 100% (+20%) | 100% (+20%) |  |  | 100% | 100%
TBD |  | 38.523-1 | TBD | Reception of system time reference | TS 38.300 cl 16.8; TS 38.331 cl 6.3.2 Verifying UE can correctly receive the system time reference Test command might be needed. | Huawei | RAN5#90-e (Feb-21) |  | Liu Bing (Leo)<leo.liubing@huawei.com> Might not be testable | TBD
6 | Y | 38.523-1 | 7.1.1.6.4 | Correct handling of DL assignment / Multi Semi-persistent configuration | TS 38.321 cl 5.3.1/cl 5.8.1; TS 38.300 cl 10.2 1. Verifying UE can perform reception on 2 SPS configuration, and handling HARQ process ID with harq-procID-offset. 2. Verifying the activation/deactivation of multi SPS configuration | Huawei | RAN5#90-e (Feb-21) | R5-206396, R5-211454 | Liu Bing (Leo)<leo.liubing@huawei.com> Some technical revision was made by R5-211454 in RAN5#90e meeting. Keep it open for further potential revisions. | 1 | 100% (+10%) | 100% (+10%) |  |  | 100% | 100%
7 | Y | 38.523-1 | 7.1.1.6.5 | Correct handling of UL grant / Multi configured uplink grants | TS 38.321 cl 5.4.1/cl 5.8.2; TS 38.300 cl 10.3 1. Verifying UE can perform transmission on 2 configured uplink grants, and handling HARQ process ID with harq-procID-offset. 2. Verifying the activation/deactivation of multi configured uplink grants | CMCC | RAN5#90-e (Feb-21) | R5-214208 | Dong Wenjia<dongwenjia@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
3 | Y | 38.523-1 | 7.1.3.5.6 | PDCP Duplication / 3 RLC entities | TS 38.321 cl 5.10/cl 6.1.3.11/cl 6.1.3.32; TS 38.323 cl 5.2.1/cl 5.11.1/cl 5.11.2; TS 38.331 cl 5.3.5.6.4 Verifying PDCP can be duplicated on more than 2 RLC entities. Similar TPs with Rel-15. Need 3 serving cells configured | CMCC | RAN5#90-e (Feb-21) | R5-206397 | Dong Wenjia<dongwenjia@chinamobile.com> 38.523-2: R5-206399 | 1 | 100% (+20%) | 100% (+20%) |  |  | 100% | 100%
8 | Y | 38.523-1 | 7.1.3.5.7 | Ethernet header compression and decompression / Correct functionality of ethernet header compression and decompression | TS 38.323 cl 5.12.2/cl 5.12.3/cl 5.12.4/cl 5.12.5/cl 5.12.6.1/cl 5.12.6.2 Verifying UE can perform EHC correctly. | Nokia | RAN5#90-e (Feb-21) | R5-206398 | Kangas Matti <matti.kangas@nokia.com> Keep it open for detailed technical review and potential revision 38.523-2: R5-206400 | 1 | 95% (+1.3%) | 95% (+0%) |  |  | 95% | 95%
TS 38.523-2: Applicability for Protocol test cases
9 |  | 38.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | RAN5#90-e (Feb-21) | R5-206399, R5-206400, R5-211455, R5-213407, R5-214209 |  | 0.5 | 70% (+10%) | 70% (+10%) |  |  | 70% | 70%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.