## Slide 1: RAN5 5G NR STATUS, DELIVERY phases and targets (Aug-21)
3GPP TSG-RAN5#92-e R5-214240
Electronic Meeting, 16 – 27 Aug 2021

## Slide 2: Introduction & CONTENT
The purpose of this document is to give high level status of RAN5 completed 5GS test cases and the targets for the next RAN5 Rel-15 5GS work item delivery phase.
Content
Progress since previous report
FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) targets
Planning for next delivery
  SA NR (SA Option 2)
  EN-DC (NSA Option 3)
  NE-DC (NSA Option 4)

## Slide 3: Progress SINCE PREVIOUS REPORT
RAN5 accepted a proposal @RAN5_92-e to include NE-DC into the RAN5 5G/NR work item scope.
Status vs connectivity option:
  SA NR (SA Option 2): 89% completed
  EN-DC (NSA Option 3): 94% completed
  NE-DC (NSA Option 4): To be reported post RAN5#93-e meeting (Nov-21)
Current target completion is RAN5#93-e (Nov-21).
More time may be needed to complete FR2 and NE-DC test cases,
For further details including list of completed test cases see RAN5 workplan in R5-214237

## Slide 4
FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) Target Completion Update (R5-214432)

## Slide 5
All FR2 test cases may not be feasible to complete by RAN5#93-e.
RF/Performance/RRM test cases:
  FR1
    RF: Complete remaining one (1) FR1 test cases (TS 38.521-1).
  FR2 & FR1+FR2:
    RF: Complete remaining 178 FR2 test cases (TS 38.521-2).
    RF performance: Complete remaining one (1) FR2 test case (TS 38.521-4).
      Conclude test tolerance analysis considering SNR testability issue pending for FR2 Demod and CSI test cases.
    RRM: Complete remaining 48 FR2 and 3 FR1+FR2 test cases (TS 38.533).
RAN Protocol test cases (TS 38.523-1):
  Layer 2: Complete remaining one (1) FR1+FR2 test case.
  Idle mode: Complete remaining 36 FR2 test cases.
  RRC: Complete remaining one (1) FR1, 49 FR2 and 9 FR1+FR2 test cases.
  Multilayer/Services: Complete remaining 6 FR2 test cases.
IMS Protocol test cases (TS 34.229-5):
  Complete remaining 39 IMS test cases (FR1 and FR2).
Plan for next delivery:
SA NR (SA Option 2) - Phase 13 - Target RAN5#93-e NOV-21

## Slide 6
Plan for next deliverY:
EN-DC (NSA Option 3) - Phase 14 content - Target RAN5#93-e NOV-21
All FR2 test cases may not be feasible to complete by RAN5#93-e.
RF/Performance/RRM test cases
  FR1:
    RF: Complete remaining 22 FR1 (anchor-agnostic) test cases (TS 38.521-3).
  FR2 & FR1+FR2:
    RF: Complete remaining 55 FR2 test cases (TS 38.521-3).
      Progress depending on progress of associated NR SA FR2 test cases.
    RF performance:
      Conclude test tolerance analysis considering SNR testability issue pending for FR2 Demod and CSI test cases (TS 38.521-4).
    RRM: Complete remaining 39 FR2 and one (1) FR1+FR2 test cases (TS 38.533).
RAN Protocol test cases (TS 38.523-1):
  RRC: Complete remaining 4 FR1, 8 FR2 and 4 FR1+FR2 test cases.

## Slide 7
Plan for next deliverY:
NE-DC (NSA Option 4) - Phase 1 content - Target RAN5#93-e NOV-21
Scope: Inter-band two band NE-DC configurations with 1CC FR1 NR and 1CC E-UTRA.
Complete work plans for NE-DC
  Test Environment (TS 38.508-1, TS 36.508) – Identify Connectivity procedures, ASN.1, Preambles etc. to enable test case creation for impacted areas
  Protocol (TS 38.523-1) – Scope and define Test Purpose of new tests cases in L2 and RRC WPs
  Currently no RRM test cases planned as no normative test cases defined in TS 38.133
Complete test cases identified in current work plans
  Introduce Implementation Conformance Statements (ICS) for NE-DC in TS 38.508-2 for RF and protocol and in TS 37.571-3 for positioning.
  RF (TS 38.521-3): ~33 FR1 and ~33 FR2 test cases
  RF performance (TS 38.521-4):
    One (1) SDR test case
    Enable applicability of existing test cases to both EN-DC and NE-DC
  Positioning:
    Enable applicability for existing RAT and RAT-independent minimum performance test cases (TS 37.571-1) and protocol test cases (TS 37.571-2) to both EN-DC and NE-DC
  Protocol:
    Layer 2: ~79 FR1, ~70 FR2 and ~1 FR1+FR2 test cases
    RRC: ~40+ test cases
NE-DC test cases may not be feasible to complete by RAN5#93-e.