## Guideline
| 3GPP RAN5#92-e |  |  | R5-214472
Electronic Meeting, Aug 16 – 27, 2021
| Agenda Item: |  | 4.2.1
| Source: |  | CMCC, Bureau Veritas, Ericsson
| Title: |  | Checklist - NR CA; NR-DC and EN-DC configurations for RAN5#92-e
| Document for: |  | Endorsement
Guideline and Check List for NR CA, NR DC and EN-DC configurations
The purpose of this document is to provide a check list for actions needed to introduced a NR CA, NR DC or EN-DC configuration into 3GPP RAN5 test specifications for 5G / NR. The document also calculates the overall completion status per TS that is to be included in the overall work plan. This document applies to 3GPP RAN5 test specifications release 15 and forward. How to use it: - Use applicable work sheet to identify what need to be added to 3GPP RAN5 TSs to introduce the configuration (You can remove the nont-applicable work sheets). - Initially all action items are set to 0% in the status column. - For NOT applicable action items clear the cell in the status column (delete the 0% value). - For Applicable action items indicate use the drop down box in the status column to indicate current completion (values of 0% to 100% in steps of 10%). - The overall completion per TS/Area is shown at the top of each worksheet (columns I to R). On request You need to provide the overall completion values for the configuration in the format for inclusion in the overall work plan for NR CA, NR DC and EN-DC configurations.
If You have questions please contact:
Danni Song, CMCC |  | songdan@chinamobile.com
Leif Mattisson, Ericsson |  | leif.mattisson@ericsson.com

## NR CA
Configuration: | <CA_.....> | [5 empty] | Completion per TS/TR
TS/TR | Check item | Clause / Test case | Applicable configurations | Action | Status | Comments | 38.508-1 | 38.508-2 | 38.523-1 | 38.521-1 | 38.521-2 | 38.521-3 | 38.521-4 | 38.533 | 38.903 | 38.905
Action for TS 38.508-1 - Common test environment | [6 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0%
38.508-1 | 1 | FR1: 4.3.1.1.3, 4.3.1.1.5 FR2: 4.3.1.2.3, 4.3.1.2.4 | Configurations including any intra-band contiguous CCs or any intra-band non-contiguous CCs. | Check if existing test frequencies can be re-used or if new test frequencies need to be specified in any of the clasues in column C. | 0% |  | For import of status to Rel-15 work plan (copy and past as values)
38.508-1 | 2 | FR1: 4.3.1.1.2 FR2: 4.3.1.2.2 FR1+FR2: 4.3.1.3.1 | Inter-band configurations | Add the CA configuration to the relevant table in one of the clauses in column C. | 0% |  | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-x: Chapter 5 | 38.521-x: Tx test cases | 38.521-x: Rx test cases | 38.521-4: RF perfromance test cases | 38.523-3: Update of the test case execution guidelines | 38.533: RRM test cases | 38.903: MU and TT | 38.905: Test point analysis
38.508-1 | 3 | 4.6.3 | Radio resource control information elements | Updating message contents | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% |  | 0%
38.508-1 | 4 | 6.2.3 | Intra-band contiguous or intra-band non-contiguous configurations with 2CC | Add test frequencies for protocol testing (protocol testing limited to 2CC CA configurations) | 0% |  | For import of status to Rel-16 and Rel-17 work plans (copy and past as values)
Action for TS 38.508-2 - Implementation Conformance Statements | [6 empty] | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-x: Common Clause | 38.521-x: Tx test cases / 38.522: Test case applicability | 38.521-x: Rx test cases / 38.522 Test case applicability | 38.521-4: RF perfromance test cases / 38.522: Test case applicability | 38.533: RRM test cases / 38:.522 Test case applicability | 38.903: MU and TT | 38.905: Test point analysis
38.508-2 | 1 | FR1: A.4.3.2A.2.1 FR2: A.4.3.2A.2.2 | NR CA Intra-band contiguous | Add NR CA configurations for Intra-band contiguous CA | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0%
38.508-2 | 2 | FR1: A.4.3.2A.3.1 FR2: A.4.3.2A.3.2 | NR CA Intra-band non-contiguous | Add configurations for NR Intra-band non-contiguous CA | 0%
38.508-2 | 3 | FR1: A.4.3.2A.4.1 | NR Inter-band CA | Add CA configurations for NR Inter-band CA | 0%
Action for TS 38.523-1 - Protocol
38.523-1 | 1 |  |  |  | 0%
38.523-1 | 2 |  |  |  | 0%
38.523-1 | ... |  |  |  | 0%
Action for TS 38.521-1 - RF Tx and Rx FR1 (including associated actions for TR 38.903 MU/TT and TR 38.905 Test Points analysis)
38.521-1 | 1 | 3.2 Symbols |  | Add new symbols needed for R16 CADC band combos. | 0%
38.521-1 | 2 | 5.2A.1 Intra-band CA | Configurations including any intra-band contiguous CCs or any intra-band non-contiguous CCs. | Add the intra-band CA operating bands to the relevant table in column C. | 0%
38.521-1 | 3 | 5.2A.2 Inter-band CA | Inter-band configurations | Add the inter-band CA operating bands to the relevant table in column C. | 0%
38.521-1 | 4 | 5.5A.1 Configurations for intra-band contiguous CA | Configurations for intra-band contiguous CCs | Add the configurations for intra-band contiguous CA to the relevant table in column C. | 0%
38.521-1 | 5 | 5.5A.2 Configurations for intra-band non-contiguous CA | Configurations for intra-band non-contiguous CCs | Add the configurations for intra-band non-contiguous CA to the relevant table in column C. | 0%
38.521-1 | 6 | 5.5A.3 Configurations for inter-band CA | Configurations for inter-band CCs | Add the configurations for inter-band CA to the relevant table in column C. | 0%
38.521-1 | 7 | 6.2A.1.0.3 UE maximum output power for Inter-band CA | Configurations including any inter-band UL CA CCs. | Add the UE maximum output power for inter-band UL CA to Table 6.2A.1.0.3-1. | 0%
38.521-1 | 8 | 6.2A.1.0.4 UE maximum output power for Intra-band contiguous CA | Configurations including any Intra-band contiguous UL CA CCs. | Add the UE maximum output power for Intra-band contiguous UL CA to Table 6.2A.1.0.4-1. | 0%
38.521-1 | 9 | 6.2A.1.1 UE maximum output power for CA (2UL CA) | Test requirement for any Inter-band/Intra-band non-contiguous 2UL CA. | Add the test requirements for Inter-band/Intra-band non-contiguous 2UL CA to Table 6.2A.1.1.5-1.
38.521-1 | 10 | 6.2A.3.1 UE additional maximum output power reduction for CA (2 UL CA) | Initial Conditions/Test Requirements for inter-band CA (2 UL CA). | Add the Initial Conditions for inter-band CA (2 UL CA) to Table 6.2A.3.1.4.1-1; Add tables for inter-band CA (2 UL CA) in Section 6.2A.3.1.5 Test requirement. | 0%
38.521-1 | 11 | 6.2A.4.0.2 ΔTIB,c for CA | Inter-band configurations | Add ΔTIB,c for inter-band CA to the relevant table in column C. | 0%
38.521-1 | 12 | 6.5A.3.2 Spurious emission for UE co-existence | Configurations including any inter-band UL CA CCs. | 1) Add the minimum conformance requirements/initial condition/test requirements for inter-band UL CA to the relevant table in column C. 2) Add TPAnalysis for NR CA band combos to TR 38.905 | 0%
38.521-1 | 13 | 7.3A.0.3 ΔRIB,c for CA | Inter-band configurations | Add ΔRIB,c for inter-band CA to the relevant table in column C. | 0%
38.521-1 | 14 | 7.3A.0.4 Reference sensitivity exceptions due to UL harmonic interference for CA | Inter-band configurations | Add Reference sensitivity exceptions, Uplink configuration and MSD for inter-band CA to the relevant table in column C. | 0%
38.521-1 | 15 | 7.3A.0.5 Reference sensitivity exceptions due to intermodulation interference due to 2UL CA | Inter-band configurations | Add Reference sensitivity and Uplink/Downlink configurations for inter-band CA to the relevant table in column C. | 0%
38.521-1 | 16 | 7.3A.1~4 Reference sensitivity power level for 2DL~5DL CA | Configurations including any intra-band contiguous CCs or any intra-band non-contiguous CCs or any inter-band UL CA CCs with applicable number of DL CCs. | 1) Add test configuration and test requirements for any exceptional requirements. 2) Add TP Analysis for the NR CA band combos to TR 38.905 | 0%
38.521-1 | ... |  |  |  | 0%
Action for TS 38.521-2 - RF Tx and Rx FR2 (including associated actions for TR 38.903 MU/TT and TR 38.905 Test Points analysis)
38.521-2 | 1 | 5.2A.1 Intra-band CA | Configurations including any intra-band contiguous CCs or any intra-band non-contiguous CCs. | Add the intra-band CA operating bands to the relevant table in column C. | 0%
38.521-2 | 2 | 5.5A.1 Configurations for intra-band contiguous CA | Configurations for intra-band contiguous CCs | Add the configurations for intra-band contiguous CA to the relevant table in column C. | 0%
38.521-2 | 3 | 5.5A.2 Configurations for intra-band non-contiguous CA | Configurations for intra-band non-contiguous CCs | Add the configurations for intra-band non-contiguous CA to the relevant table in column C. | 0%
38.521-2 | 4 | 6.2A.1 UE maximum output power for CA | Configurations including any intra-band contiguous UL CA CCs. | Add the UE maximum output power for intra-band contiguous UL CA to the relevant table in column C. | 0%
38.521-2 | 5 | 6.5A.3.2 Spurious emission for UE co-existence | Configurations including any intra-band contiguous UL CA CCs. | 1) Add the minimum conformance requirements/initial condition/test requirements for intra-band contiguous UL CA to the relevant table in column C. 2) Add TP Analysis for the NR CA band combos to TR 38.905 | 0%
38.521-2 | 6 | 7.3A.2 Reference sensitivity power level for CA | Intra-band contiguous and Intra-band non-contiguous configurations | No need to change. | 0%
38.521-2 | ... |  |  |  | 0%
Action for TS 38.521-3 - RF Tx and Rx FR1 + FR2 (including associated actions for TR 38.903 MU/TT and TR 38.905 Test Points analysis)
38.521-3 | 1 |  |  |  | 0%
38.521-3 | 2 |  |  |  | 0%
38.521-3 | ... |  |  |  | 0%
Action for TS 38.521-4 - Demodulation / CSI reporting (including associated actions for TR 38.903 MU/TT)
38.521-4 | 1 |  |  |  | 0%
38.521-4 | 2 |  |  |  | 0%
38.521-4 | ... |  |  |  | 0%
Action for TS 38.533 - RRM (including associated actions for TR 38.903 MU/TT)
38.533 | 1 |  |  |  | 0%
38.533 | 2 |  |  |  | 0%
38.533 | ... |  |  |  | 0%
Note on B2: Check item number within the TS, 1,2,3 etc.
Note on C2: Impacted clause in the TS: or list of clauses if the applicable configurations and action is the same.
Note on D2: The type of configuration(s) the action applies to, could be “All” if all are impacted.
Note on E2: Action on the responsible for the configuration to check/update etc.
Note on F2: Status of the analysis: Check: The action need to be checked (not started yet) Not Applicable: Item not applicable for the configuration Ongoing: Action on-going Completed: Action completed

## NR DC
Configuration: | <DC_.....> | [5 empty] | Completion per TS/TR
TS/TR | Check item | Clause / Test case | Applicable configurations | Action | Status | Comments | 38.508-1 | 38.508-2 | 38.523-1 | 38.521-1 | 38.521-2 | 38.521-3 | 38.521-4 | 38.533 | 38.903 | 38.905
Action for TS 38.508-1 - Common test environment | [6 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
38.508-1 | 1 | FR1: 4.3.1.1.5 FR2: 4.3.1.2 FR1+FR2: 4.3.1.3.2 | All | Add the DA configuration to the relevant table in one of the clauses in column C. | 0% |  | For import of status to Rel-15 work plan (copy and past as values)
38.508-1 | 2 |  |  |  | 0% |  | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-x: Chapter 5 | 38.521-x: Tx test cases | 38.521-x: Rx test cases | 38.521-4: RF perfromance test cases | 38.523-3: Update of the test case execution guidelines | 38.533: RRM test cases | 38.903: MU and TT | 38.905: Test point analysis
38.508-1 | ... |  |  |  | 0% |  | 0% | 0% |  |  |  | 0% |  | 0%
Action for TS 38.508-2 - Implementation Conformance Statements | [6 empty] | For import of status to Rel-16 and Rel-17 work plans (copy and past as values)
38.508-2 | 1 |  |  |  | 0% |  | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-x: Common Clause | 38.521-x: Tx test cases / 38.522: Test case applicability | 38.521-x: Rx test cases / 38.522 Test case applicability | 38.521-4: RF perfromance test cases / 38.522: Test case applicability | 38.533: RRM test cases / 38:.522 Test case applicability | 38.903: MU and TT | 38.905: Test point analysis
38.508-2 | 2 |  |  |  | 0% |  | 0% | 0% |  |  |  | 0% | 0%
38.508-2 | ... |  |  |  | 0%
Action for TS 38.523-1 - Protocol
38.523-1 | 1 |  |  |  | 0%
38.523-1 | 2 |  |  |  | 0%
38.523-1 | ... |  |  |  | 0%
Action for TS 38.521-1 - RF Tx and Rx FR1 (including associated actions for TR 38.903 MU/TT and TR 38.905 Test Points analysis)
38.521-1 | 1 |  |  |  | 0%
38.521-1 | 2 |  |  |  | 0%
38.521-1 | ... |  |  |  | 0%
Action for TS 38.521-2 - RF Tx and Rx FR2 (including associated actions for TR 38.903 MU/TT and TR 38.905 Test Points analysis)
38.521-2 | 1 |  |  |  | 0%
38.521-2 | 2 |  |  |  | 0%
38.521-2 | ... |  |  |  | 0%
Action for TS 38.521-3 - RF Tx and Rx FR1 + FR2 (including associated actions for TR 38.903 MU/TT and TR 38.905 Test Points analysis)
38.521-3 | 1 |  |  |  | 0%
38.521-3 | 2 |  |  |  | 0%
38.521-3 | ... |  |  |  | 0%
Action for TS 38.521-4 - Demodulation / CSI reporting (including associated actions for TR 38.903 MU/TT)
38.521-4 | 1 |  |  |  | 0%
38.521-4 | 2 |  |  |  | 0%
38.521-4 | ... |  |  |  | 0%
Action for TS 38.533 - RRM (including associated actions for TR 38.903 MU/TT)
38.533 | 1 |  |  |  | 0%
38.533 | 2 |  |  |  | 0%
38.533 | ... |  |  |  | 0%
Note on B2: Check item number within the TS, 1,2,3 etc.
Note on C2: Impacted clause in the TS: or list of clauses if the applicable configurations and action is the same.
Note on D2: The type of configuration(s) the action applies to, could be “All” if all are impacted.
Note on E2: Action on the responsible for the configuration to check/update etc.
Note on F2: Status of the analysis: Check: The action need to be checked (not started yet) Not Applicable: Item not applicable for the configuration Ongoing: Action on-going Completed: Action completed

## EN-DC
Configuration: | <DC_.....> | [5 empty] | Completion per TS/TR
TS/TR | Check item | Clause / Test case | Applicable configurations | Action | Status | Comments | 38.508-1 | 38.508-2 | 38.523-1 | 38.521-1 | 38.521-2 | 38.521-3 | 38.521-4 | 38.533 | 38.903 | 38.905
Action for TS 38.508-1 - Common test environment | [6 empty] | 0% | 0% |  |  |  | 0% |  |  |  | 0%
38.508-1 | 1 | FR1: 4.3.1.4.2, 4.3.1.4.3 | Configurations including any intra-band EN-DC contiguous CCs or any intra-band EN-DC non-contiguous CCs | Check if existing test frequencies can be re-used or if new test frequencies need to be specified in any of the clasues in column C. | 0% |  | For import of status to Rel-15 work plan (copy and past as values to the WP)
38.508-1 | 2 | FR1: 4.3.1.4.1 FR2: 4.3.1.5.1 FR1+FR2: 4.3.1.6 | Inter-band configurations | Add the CA configuration to the relevant table in one of the clauses in column C. | 0% |  | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-x: Chapter 5 | 38.521-x: Tx test cases | 38.521-x: Rx test cases | 38.521-4: RF perfromance test cases | 38.523-3: Update of the test case execution guidelines | 38.533: RRM test cases | 38.903: MU and TT | 38.905: Test point analysis
38.508-1 | 3 | 6.2.3 | Intra-band contiguous or intra-band non-contiguous configurations with 2CC | Add test frequencies for EN-DC band combinations protocol testing (protocol testing limited to 2 bands) | 0% |  | 0% | 0% | 0% | 0% | 0% |  |  |  |  | 0%
Action for TS 38.508-2 - Implementation Conformance Statements | [6 empty] | For import of status to Rel-16 and Rel-17 work plans (copy and past as values to the WP)
38.508-2 | 1 | FR1: A.4.3.2B.2.1 | EN-DC Intra-band contiguous | Add EN-DC Intra-band contiguous configurations | 0% |  | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-x: Common Clause | 38.521-x: Tx test cases / 38.522: Test case applicability | 38.521-x: Rx test cases / 38.522 Test case applicability | 38.521-4: RF perfromance test cases / 38.522: Test case applicability | 38.533: RRM test cases / 38:.522 Test case applicability | 38.903: MU and TT | 38.905: Test point analysis
38.508-2 | 2 | FR1: A.4.3.2B.2.2 | EN-DC Intra-band non-contiguous | Add EN-DC Intra-band non-contiguous configurations | 0% |  | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
38.508-2 | 3 | FR1: A.4.3.2B.2.3.1~A.4.3.2B.2.3.5 FR2: A.4.3.2B.2.3.6~A.4.3.2B.2.3.10 FR1+FR2: A.4.3.2B.2.3.7~A.4.3.2B.2.3.10 | EN-DC Inter-band | Add EN-DC Inter-band configurations | 0%
Action for TS 38.523-1 - Protocol
38.523-1 | 1
38.523-1 | 2
38.523-1 | ...
Action for TS 38.521-3 - RF Tx and Rx EN-DC FR1, FR2 and FR1 + FR2 (including associated actions for TR 38.903 MU/TT and TR 38.905 Test Points analysis)
38.521-3 | 1 | 5.5B.2 Intra-band contiguous EN-DC | Intra-band contiguous EN-DC configurations within FR1 | Add band combinations for intra-band contiguous EN-DC to the relevant table in Column C | 0%
38.521-3 | 2 | 5.5B.3 Intra-band non-contiguous EN-DC | Intra-band non-contiguous EN-DC configurations within FR1 | Add band combinations for intra-band non-contiguous EN-DC to the relevant table in Column C | 0%
38.521-3 | 3 | 5.5B.4 Inter-band EN-DC within FR1 | Inter-band configurations within FR1 | Add inter-band EN-DC configurations within FR1 to the relevant table in column C. | 0%
38.521-3 | 4 | 5.5B.5 Inter-band EN-DC including FR2 | Inter-band configurations including FR2 | Add inter-band EN-DC configurations including FR2 to the relevant table in column C. | 0%
38.521-3 | 5 | 5.5B.6 Inter-band EN-DC including FR1 and FR2 | Inter-band configurations including FR1 and FR2 | Add inter-band EN-DC configurations including FR1 and FR2 to the relevant table in column C. | 0%
38.521-3 | 6 | 6.2B.1.1 UE Maximum Output Power for Intra-Band Contiguous EN-DC | Intra-band contiguous EN-DC configurations within FR1 | 1) Update MOP for intra band contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements of Column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 7 | 6.2B.1.2 UE Maximum Output Power for Intra-Band Non-Contiguous EN-DC | Intra-band non contiguous EN-DC configurations within FR1 | 1) Update MOP for intra band non contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements of Column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 8 | 6.2B.1.3 UE Maximum Output Power for Inter-Band EN-DC within FR1 | Inter-band configurations within FR1 | 1) Update maximum output power for inter-band EN-DC within FR1 to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 9 | 6.2B.1.4 UE Maximum Output Power for Inter-Band EN-DC including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update maximum output power for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirementsof column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 10 | 6.2B.1.4_1 UE Maximum Output Power for Inter-Band EN-DC including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update maximum output power for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 11 | 6.2B.2.4 UE Maximum Output power reduction for inter-band EN-DC including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update maximum output power reduction for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 12 | 6.2B.2.4_1 UE Maximum Output power reduction for inter-band EN-DC including (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update the maximum output power reduction for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 13 | 6.2B.3.1 UE Additional Maximum Output Power reduction for Intra-band contiguous EN-DC | Intra-band contiguous EN-DC configurations within FR1 | 1) Update A-MPR for intra band contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements of Column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 14 | 6.2B.3.2 UE Additional Maximum Output Power reduction for Intra-Band Non-Contiguous EN-DC | Intra-band non-contiguous EN-DC configurations within FR1 | 1) Update A-MPR for intra band non-contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements of Column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 15 | 6.2B.3.4 UE Additional Maximum Output power reduction for inter-band EN-DC including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update additional maximum output power reduction for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 16 | 6.2B.3.4_1 UE Additional Maximum Output power reduction for inter-band EN-DC including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1)Update additional maximum output power reduction for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 17 | 6.2B.4.1.0.2.3 Inter-band EN-DC within FR1 | Inter-band configurations within FR1 | Update ΔTIB,c for inter-band EN-DC within FR1 to the relevant table in column C. | 0%
38.521-3 | 18 | 6.2B.4.1.0.2.4 Inter-band EN-DC including FR2 | Inter-band configurations including FR2 | Update ΔTIB,c for inter-band EN-DC including FR2 to the relevant table in column C. | 0%
38.521-3 | 19 | 6.2B.4.1.0.2.5 Inter-band EN-DC including both FR1 and FR2 | Inter-band configurations including both FR1 and FR2 | Update ΔTIB,c for inter-band EN-DC including both FR1 and FR2 to the relevant table in column C. | 0%
38.521-3 | 20 | 6.2B.4.2.3 Inter-band EN-DC within FR1 | Inter-band configurations within FR1 | Add ΔTIB,c for inter-band EN-DC within FR1 to the relevant table in column C. | 0% | updated to correct table.
38.521-3 | 21 | 6.2B.4.2.4 Inter-band EN-DC including FR2 | Inter-band configurations including FR2 | Add ΔTIB,c for inter-band EN-DC including FR2 to the relevant table in column C. | 0% | updated to correct table.
38.521-3 | 22 | 6.2B.4.2.5 Inter-band EN-DC including both FR1 and FR2 | Inter-band configurations including both FR1 and FR2 | Add ΔTIB,c for inter-band EN-DC including both FR1 and FR2 to the relevant table in column C. | 0% | updated to correct table.
38.521-3 | 23 | 6.3B.1.4 Minimum output power for inter-band EN-DC including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update Minimum output power for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 24 | 6.3B.1.4_1 Minimum output power for inter-band EN-DC including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update Minimum output power for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 25 | 6.3B.2.4 Transmit OFF Power for inter-band EN-DC including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update Transmit OFF Power for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 26 | 6.3B.2.4_1 Transmit OFF Power for inter-band EN-DC including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update Transmit OFF Power for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 27 | 6.3B.3.4 Tx ON/OFF time mask for inter-band EN-DC including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update Tx ON/OFF time mask for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 28 | 6.3B.3.4_1 Tx ON/OFF time mask for inter-band EN-DC including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update Tx ON/OFF time mask for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 29 | 6.3B.4.4 PRACH Time Mask for inter-band EN-DC including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update PRACH Time Mask for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 30 | 6.3B.4.4_1 PRACH Time Mask for inter-band EN-DC including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update PRACH Time Mask for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 31 | 6.4B.1.5 Frequency Error for inter-band EN-DC including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update Frequency Error for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 32 | 6.4B.1.5_1 Frequency Error for inter-band EN-DC including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update Frequency Error for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 33 | 6.4B.2.4.1 Error Vector Magnitude for inter-band EN-DC including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update Error Vector Magnitude for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 34 | 6.4B.2.4.1_1 Error Vector Magnitude for inter-band EN-DC including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update Error Vector Magnitude for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 35 | 6.4B.2.4.2 Carrier Leakage for inter-band EN-DC including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update Carrier Leakage for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 36 | 6.4B.2.4.2_1 Carrier Leakage for inter-band EN-DC including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update Carrier Leakage for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 37 | 6.4B.2.4.3 In-band Emissions for inter-band EN-DC including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update In-band Emissions for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 38 | 6.4B.2.4.3_1 In-band Emissions for inter-band EN-DC including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update In-band Emissions for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 39 | 6.4B.2.4.4 EVM Equalizer Flatness for inter-band EN-DC including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update EVM Equalizer Flatness for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 40 | 6.4B.2.4.4_1 EVM Equalizer Flatness for inter-band EN-DC including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update EVM Equalizer Flatness for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 41 | 6.5B.1.4 Occupied bandwidth for inter-band EN-DC including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update Occupied bandwidth for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 42 | 6.5B.1.4_1 Occupied bandwidth for inter-band EN-DC including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update Occupied bandwidth for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 43 | 6.5B.2.4.1 Spectrum emissions mask for Inter-band EN-DC including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update Spectrum emissions mask for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 44 | 6.5B.2.4.1_1 Spectrum emissions mask for Inter-band EN-DC including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update Spectrum emissions mask for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 45 | 6.5B.2.4.2 Additional Spectrum emissions mask for Inter-band EN-DC including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update Additional Spectrum emissions mask for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 46 | 6.5B.2.4.2_1 Additional Spectrum emissions mask for Inter-band EN-DC including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update Additional Spectrum emissions mask for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 47 | 6.5B.2.4.3 Adjacent channel leakage ratio for Inter-band EN-DC including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update Adjacent channel leakage ratio for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 48 | 6.5B.2.4.3_1 Adjacent channel leakage ratio for Inter-band EN-DC including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update Adjacent channel leakage ratio for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 49 | 6.5B.3.1.2 Spurious emission band UE co-existence for intra-band contiguous EN-DC | Intra-band contiguous EN-DC configurations within FR1 | 1) Update Spurious Emission band UE co-existence for intra band contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements of Column C 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 50 | 6.5B.3.2.2 Spurious emission band UE co-existence for intra-band non-contiguous EN-DC | Intra-band non-contiguous EN-DC configurations within FR1 | 1) Update Spurious Emission band UE co-existence for intra band non-contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements of Column C 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 50A | 6.5B.3.3.1 General Spurious Emissions for Inter-band EN-DC within FR1 | Intra-band contiguous EN-DC configurations within FR1 | 1) Update General Spurious Emissions for inter-band EN-DC within FR1 to minimum conformance requirements/initial condition/test requirements of Column C 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 51 | 6.5B.3.3.2 Spurious emission band UE co-existence for Inter-band within FR1 | Inter-band configurations within FR1 | 1) Update Spurious Emission band UE co-existence for Inter-band within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements of Column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 52 | 6.5B.3.4.1 General Spurious Emissions for Inter-band including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update General Spurious Emissions for inter-band EN-DC including FR2 (2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 53 | 6.5B.3.4.1_1 General Spurious Emissions for Inter-band including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update General Spurious Emissions for inter-band EN-DC including FR2 (>2 CCs) to the relevant table in minimum conformance requirements/initial condition/test requirements of column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 54 | 6.5B.3.4.2 Spurious emission band UE co-existence for Inter-band including FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update Spurious Emission band UE co-existence for Inter-band including FR2 (2 CCs) to minimum conformance requirements/initial condition/test requirements of Column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 55 | 6.5B.3.4.2_1 Spurious emission band UE co-existence for Inter-band including FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update Spurious Emission band UE co-existence for Inter-band including FR2 (>2 CCs) to minimum conformance requirements/initial condition/test requirements of Column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 56 | 6.5B.4.4 Transmit Intermodulation for inter-band EN-DC within FR2 (2 CCs) | Inter-band configurations including FR2 (2 CCs) | 1) Update Transmit Intermodulation for inter-band EN-DC within FR2 (2 CCs) to minimum conformance requirements/initial condition/test requirements of Column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 57 | 6.5B.4.4_1 Transmit Intermodulation for inter-band EN-DC within FR2 (>2 CCs) | Inter-band configurations including FR2 (>2 CCs) | 1) Update Transmit Intermodulation for inter-band EN-DC within FR2 (>2 CCs) to minimum conformance requirements/initial condition/test requirements of Column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 58 | 7.3B.2.0.3 Inter-band EN-DC within FR1 | Inter-band configurations within FR1 | 1) Add Reference sensitivity exceptions for EN-DC within FR1 to the relevant table in column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 59 | [7.3B.2.0.4 Inter-band EN-DC including FR2] | Inter-band configurations including FR2 | 1) Add Reference sensitivity exceptions for EN-DC including FR2 to the relevant table in column C. 2) Add TP Analysis for the EN-DC band combos to TR 38.905 | 0%
38.521-3 | 60 | 7.3B.2.3 Reference sensitivity for Inter-band EN-DC within FR1 | Inter-band configurations within FR1 | Update initial condition/test requirements for inter-band EN-DC within FR1 in column C | 0%
38.521-3 | 61 | 7.3B.2.4 Reference sensitivity for Inter-band EN-DC including FR2 | Inter-band configurations including FR2 | Update initial condition/test requirements for inter-band EN-DC including FR2 in column C | 0%
38.521-3 | 62 | 7.3B.3.3 ΔRIB,c for Inter-band EN-DC within FR1 | Inter-band configurations within FR1 | Add ΔRIB,c for inter-band EN-DC within FR1 to the relevant table in column C. | 0%
38.521-3 | 63 | 7.3B.3.4 Reference sensitivity for ΔRIB,c Inter-band EN-DC including FR2 | Inter-band configurations including FR2 | Add ΔRIB,c for inter-band EN-DC including FR2 to the relevant table in column C. | 0%
38.521-3 | ...
Action for TS 38.521-4 - Demodulation / CSI reporting (including associated actions for TR 38.903 MU/TT)
38.521-4 | 1
38.521-4 | 2
38.521-4 | ...
Action for TS 38.533 - RRM (including associated actions for TR 38.903 MU/TT)
38.533 | 1
38.533 | 2
38.533 | ...
Note on B2: Check item number within the TS, 1,2,3 etc.
Note on C2: Impacted clause in the TS: or list of clauses if the applicable configurations and action is the same.
Note on D2: The type of configuration(s) the action applies to, could be “All” if all are impacted.
Note on E2: Action on the responsible for the configuration to check/update etc.
Note on F2: Status of the analysis: Check: The action need to be checked (not started yet) Not Applicable: Item not applicable for the configuration Ongoing: Action on-going Completed: Action completed