## Cover sheet
3GPP TSG-RAN5 Meeting #92-e | [8 empty] | R5-214546
Electronic Meeting, 16 – 27 August 2021
Agenda Item: | 7.4.2
Source: | China Telecom
Title: | WP for NR_PC2_CA_R17_2BDL_2BUL-UEConTest after RAN5#92e
Work item code: | NR_PC2_CA_R17_2BDL_2BUL-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to define the UE conformance test cases correspond to the defined test requirements in WI ‘High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2)’. The scope of this WI includes all PC2 NR inter-band CA for 2 bands DL with 2 bands UL and PC1.5 and PC2 NR Inter-band CA for 2 bands DL with 1 band UL band combination configurations with the agreed baseline P-MPR based SAR solution defined in the RAN4 WID on High power UE (power class 2) for NR inter-band Carrier Aggregation with 2 bands downlink and 2 bands uplink, identified in clause 2.2.Only completed PC2 CA configurations in RAN4 are allowed to be introduced in RAN5.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 15% (+15%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 15.2% (+15.2%)
FR1 |  | 15.2% (+15.2%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2 | 0% |  |  | 0%
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx | 30.4% (+30.4%) |  |  | 30.4% (+30.4%)
FR1 RF Rx test cases | 38.521-1 Rx | 0% |  |  | 0%
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0%
5 References
[1] RP-211140 | New WID on UE Conformance – High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP for NR_PC2_CA_R17_2BDL_2BUL-UEConTest after RAN5#92e | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_PC2_CA_R17_2BDL_2BUL-UEConTest
WP Scope: |  | The objective of this work item is to define the UE conformance test cases correspond to the defined test requirements in WI ‘High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2)’. The scope of this WI includes all PC2 NR inter-band CA for 2 bands DL with 2 bands UL and PC1.5 and PC2 NR Inter-band CA for 2 bands DL with 1 band UL band combination configurations with the agreed baseline P-MPR based SAR solution defined in the RAN4 WID on High power UE (power class 2) for NR inter-band Carrier Aggregation with 2 bands downlink and 2 bands uplink, identified in clause 2.2.Only completed PC2 CA configurations in RAN4 are allowed to be introduced in RAN5.
WP Resp: |  | Wu Jingzhou |  |  | wujingzhou@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp:
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
15.2% (+15.2%)
127 (+127)
64.9 (+64.9)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS NR RF
PC2 band combinations (2 bands UL and 2 bands DL)
UL CA Config: CA_n1A-n78A Interested Operator: China Telecom
[9 empty] | NOTE: The introduction of PC2 for UL CA Config CA_n1A-n78A will be finished in NR_SAR_PC2_interB_SUL_2BUL-UEConTest WI as the example band combination. | 0
UL CA Config: CA_n2A-n77A Interested Operator: Verizon
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
1 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
2 |  | 38.521-1 Rx | 7.3A | Reference sensitivity for CA | Introduce conformance requirements, test case description, test requirements for the test case for Reference sensitivity exceptions due to intermodulation interference |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
UL CA Config: CA_n3A-n41A Interested Operator: CMCC
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability | CMCC | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
3 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. | CMCC | RAN5#94 (Feb-22) | R5-215986 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
4 |  | 38.521-1 Rx | 7.3A | Reference sensitivity for CA | Introduce conformance requirements, test case description, test requirements for the test case for Reference sensitivity exceptions due to intermodulation interference due to 2UL CA | CMCC | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
UL CA Config: CA_n5A-n77A Interested Operator: Verizon
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
5 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
6 |  | 38.521-1 Rx | 7.3A | Reference sensitivity for CA | Introduce conformance requirements, test case description, test requirements for the test case for Reference sensitivity exceptions due to intermodulation interference due to 2UL CA |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
7 |  | 38.521-1 Rx | 7.6A.3 | Out-of-band blocking for CA | Introduce conformance requirements, test case description, test requirements for the test case for Out-of-band blocking for Inter-band CA |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
UL CA Config: CA_n25A-n77A Interested Operator:
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
8 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
9 |  | 38.521-1 Rx | 7.3A | Reference sensitivity for CA | Introduce conformance requirements, test case description, test requirements for the test case for Reference sensitivity exceptions due to intermodulation interference due to 2UL CA |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
UL CA Config: CA_n28A-n41A Interested Operator: CMCC
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability | CMCC | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
10 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. | CMCC | RAN5#94 (Feb-22) | R5-215988 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
UL CA Config: CA_n28A-n79A Interested Operator: CMCC
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability | CMCC | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
11 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. | CMCC | RAN5#94 (Feb-22) | R5-215987 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
UL CA Config: CA_n40A-n41A Interested Operator: CMCC
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability | CMCC | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
12 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. | CMCC | RAN5#94 (Feb-22) | R5-215989 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
UL CA Config: CA_n41A-n77A Interested Operator:
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
13 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
UL CA Config: CA_n41A-n79A Interested Operator: CMCC
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability | CMCC | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
14 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements for PC2 MOP test. | CMCC | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test cases. | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
UL CA Config: CA_n66A-n77A Interested Operator: Verizon
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
15 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
16 |  | 38.521-1 Rx | 7.3A | Reference sensitivity for CA | Introduce conformance requirements, test case description, test requirements for the test case for Reference sensitivity exceptions due to intermodulation interference due to 2UL CA |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
UL CA Config: CA_n71A-n77A Interested Operator:
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
17 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
18 |  | 38.521-1 Rx | 7.3A | Reference sensitivity for CA | Introduce conformance requirements, test case description, test requirements for the test case for Reference sensitivity exceptions due to intermodulation interference due to 2UL CA |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
PC2 band combinations (1 band UL and 2 bands DL)
DL CA Config: CA_n1A-n78A UL band: n78 Interested Operator: China Telecom
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability | China Telecom | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
19 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. | China Telecom | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria | China Telecom | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. | China Telecom | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
DL CA Config: CA_n2A-n77A CA_n2A-n77(2A) UL band: n77 Interested Operator: Verizon
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
20 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
21 |  | 38.521-1 Rx | 7.3A | Reference sensitivity for CA | Introduce conformance requirements, test case description, test requirements for the test case for Reference sensitivity exceptions due to due to UL harmonic for UL n77 and DL n2 |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
DL CA Config: CA_n3A-n41A UL band: n41 Interested Operator: CMCC
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability | CMCC | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
22 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. | CMCC | RAN5#94 (Feb-22) | R5-215990 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
23 |  | 38.521-1 Rx | 7.3A | Reference sensitivity for CA | Introduce conformance requirements, test case description, test requirements for the test case for Reference sensitivity exceptions due to cross band isolation for CA | CMCC | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
DL CA Config: CA_n5A-n77A, CA_n5A-n77(2A) UL band: n77 Interested Operator: Verizon
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
24 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
DL CA Config: CA_n25A-n77A UL Band: n77 Interested Operator: T-Mobile USA
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
25 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
26 |  | 38.521-1 Rx | 7.3A | Reference sensitivity for CA | Introduce conformance requirements, test case description, test requirements for the test case for Reference sensitivity exceptions due to due to UL harmonic for UL n77 and DL n25 |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
DL CA Config: CA_n28A-n41A UL Band: n41 Interested Operator: CMCC
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability | CMCC | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
27 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. | CMCC | RAN5#94 (Feb-22) | R5-215992 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
DL CA Config: CA_n28A-n79A UL Band: n79 Interested Operator: CMCC
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability | CMCC | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
28 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. | CMCC | RAN5#94 (Feb-22) | R5-215991 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
DL CA Config: CA_n40A-n41A UL Band: n41 Interested Operator: CMCC
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability | CMCC | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
29 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. | CMCC | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
DL CA Config: CA_n41A-n77A UL Band: n41 n77 Interested Operator: T-Mobile USA
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
30 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
31 |  | 38.521-1 Rx | 7.3A | Reference sensitivity for CA | Introduce conformance requirements, test case description, test requirements for the test case for Reference sensitivity exceptions due to cross band isolation for CA |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
DL CA Config: CA_n41A-n79A UL Band: n41 n79 Interested Operator: CMCC
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability | CMCC | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
32 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. | CMCC | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
33 |  | 38.521-1 Rx | 7.3A | Reference sensitivity for CA | Introduce conformance requirements, test case description, test requirements for the test case for Reference sensitivity exceptions due to cross band isolation for CA | CMCC | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. | CMCC | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
DL CA Config: CA_n66A_n77A CA_n66A-n77(2A) UL Band: n77 Interested Operator: Verizon
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
34 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
DL CA Config: CA_n71A-n77A UL Band: n77 Interested Operator: T-Mobile USA
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
35 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements. |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.