## Summary
Work plan summary:
NR-based access to unlicensed spectrum - (TS 38.521-1)
|  |  | Overall | FR1 | FR2 | FR1+FR2
| NR Transmitter and Receiver Test Cases for NR-U – SA Range 1 (TS 38.521-1) | SA Option 2 (SA NR) | 10% | 10%
NSA Option 3 (EN-DC)
SA Option 5
NSA Option 4 (NE-DC)
NSA Option 7 (NGEN-DC)
|  | Area | SA Option 2 (SA NR) test case statistics
|  |  | Overall number of test cases |  | Number of FR independent test cases |  | Number of FR1 test cases |  | Number of FR2 test cases |  | Number of FR1+FR2 test cases
|  | Area | Overall | Completed | Overall | Completed | Overall | Completed | Overall | Completed | Overall | Completed
| NR Transmitter and Receiver Test Cases for NR-U – SA Range 1 (TS 38.521-1) | SA Option 2 (SA NR) | 32 | 0 |  |  | 32 | 0
NSA Option 3 (EN-DC)
SA Option 5
NSA Option 4 (NE-DC)
NSA Option 7 (NGEN-DC)

## RF Tx Rx Range 1
WP Title: | NR-based access to unlicensed spectrum - (TS 38.521-1) | [11 empty] | WP item applicability
RAN-CN interface options dependency
WP Scope: | This part of the work plan covers NR transmitter and receiver test cases for NR based access to unlicensed spectrum for range 1 (sub-6 GHz) | [11 empty] | 5GC/NR |  | 5GC/LTE | EPC/LTE | 5GC/NR master | 5GC / LTE master
WP Resp: | Vijay Balasubramanian, Qualcomm |  |  |  | vijayb@qti.qualcomm.com
TS Resp: | <TS responsible if a new TS is involved> | [11 empty] | SA |  |  | NSA
WP Item ID | Is test case | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. |  | Opt. 2 |  | Opt. 5 | Opt. 3 | Opt. 4 | Opt. 7
[11 empty] | Overall |  | 8.984%
[11 empty] | Phase 1 |  | 26.15%
[11 empty] | Phase 2 |  | 0%
[11 empty] | Phase 3 |  | 0%
[11 empty] | Phase 4 |  | 0%
[11 empty] | Phase 5 |  | 0%
[11 empty] | Phase 6 |  | 68.57%
[11 empty] | Phase 7 |  | 0%
[11 empty] | Phase 8 |  | 1.667%
Phase 9
Phase 10
Phase 11
Phase 12
[7 empty] | Overall #WP items: Phase 1 #WP items: Phase 2 #WP items: Phase 3 #WP items: Phase 4 #WP items: Phase 5 #WP items: Phase 6 #WP items: Phase 7 #WP items: Phase 8 #WP items: Phase 9 #WP items: Phase 10 #WP items: Phase 11 #WP items: Phase 12 #WP items: | [5 empty] | 53 13 15 8 6 1 3 1 6 0 0 0 0 |  | 0 0 0 0 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
TS 38.508-2: Common ICS
60 |  | 38.508-2 | 4 |  | Introduction of common implementation conformance statements for Rel-16 NR-U | Ericsson | RAN5#93 (Nov-21) | R5-214334 |  | 0.5 | 60% |  | 6 | 60% | 1 | 1 | 1 | 1
General
1 |  | 38.521-1 | 4 | General | define categories of test requirements for NR-U |  | RAN5#93 (Nov-21) | R5-215984 |  | 0.1 | 90% |  | 6 | 90% | 1 | 1 | 1 | 1
2 |  | 38.521-1 | 5 | Operating bands and Channel arrangement | define the frequency bands and channel arragement for NR-U |  | RAN5#93 (Nov-21) | R5-215984 |  | 0.1 | 90% |  | 6 | 90% | 1 | 1 | 1 | 1
Transmitter characteristics (Clause 6)
3 |  | 38.521-1 | 6.1 | General | TS38.101-1 cl 6,1, provide general info for chapter 6. |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% |  | 3 | 0% | 1 | 1 | 1 | 1
Transmit power for shared spectrum channel access (Clause 6.2F)
4 | Y | 38.521-1 | 6.2F.1 | UE maximum output power |  | Ericsson | RAN5#93 (Nov-21) | R5-215983 | No test points are defined since there is no configuration satisfying MPR=0dB requirements in RAN4. Testing with 1.5dB MPR has been covered in [6.2F.2]. - MU and TT for >6GHz (band n96). - RMC in Annex A | 1 | 60% |  | 1 | 60% | 1 | 1 | 1 | 1
6 | Y | 38.521-1 | 6.2F.2 | UE maximum output power reduction |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 2 | 0% | 1 | 1 | 1 | 1
8 | Y | 38.521-1 | 6.2F.3 | UE additional maximum output power reduction |  | Ericsson | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 2 | 0% | 1 | 1 | 1 | 1
10 | Y | 38.521-1 | 6.2F.4 | Configured transmitted power |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 2 | 0% | 1 | 1 | 1 | 1
Output power dynamics for shared spectrum channel access (Clause 6.3F)
11 | Y | 38.521-1 | 6.3F.1 | Minimum output power |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 1 | 0% | 1 | 1 | 1 | 1
12 | Y | 38.521-1 | 6.3F.2 | Transmit OFF power |  | Ericsson | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 1 | 0% | 1 | 1 | 1 | 1
13 | Y | 38.521-1 | 6.3F.3 | Transmit ON/OFF time mask |  | Ericsson | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 3 | 0% | 1 | 1 | 1 | 1
14 |  | 38.521-1 | 6.3F.4 | Power control | [10 empty] | 1 | 1 | 1 | 1
15 | Y | 38.521-1 | 6.3F.4.2 | Absolute power tolerance |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 3 | 0% | 1 | 1 | 1 | 1
16 | Y | 38.521-1 | 6.3F.4.3 | Relative power tolerance |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 1 | 0% | 1 | 1 | 1 | 1
17 | Y | 38.521-1 | 6.3F.4.4 | Aggregate power tolerance |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 1 | 0% | 1 | 1 | 1 | 1
Transmit signal quality for shared spectrum channel access (Clause 6.4F)
18 | Y | 38.521-1 | 6.4F.1 | Frequency Error |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 2 | 0% | 1 | 1 | 1 | 1
19 | Y | 38.521-1 | 6.4F.2.1 | Error Vector Magnitude |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 3 | 0% | 1 | 1 | 1 | 1
21 | Y | 38.521-1 | 6.4F.2.3 | In-band emissions |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 2 | 0% | 1 | 1 | 1 | 1
22 | Y | 38.521-1 | 6.4F.2.4 | EVM equalizer spectrum flatness |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 2 | 0% | 1 | 1 | 1 | 1
Output RF spectrum emissions for shared spectrum channel access (Clause 6.5F)
23 | Y | 38.521-1 | 6.5F.1 | Occupied bandwidth |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 1 | 0% | 1 | 1 | 1 | 1
24 |  | 38.521-1 | 6.5F.2.1 | Out of band Emission | [5 empty] | 0.1 | 0% |  | 2 | 0%
25 | Y | 38.521-1 | 6.5F.2.2 | Spectrum emission mask for operation with shared spectrum channel access |  | Qualcomm | RAN5#93 (Nov-21) | R5-215564 | Test config table is FFS TP analysis is TBD Message content is TBD | 1 | 60% |  | 1 | 60% | 1 | 1 | 1 | 1
26 | Y | 38.521-1 | 6.5F.2.3 | Additional spectrum emission mask |  | Ericsson | RAN5#93 (Nov-21) |  | No requirements yet in 38.101-1 but will come | 1 | 0% |  | 4 | 0% |  | 1 | 1 | 1
27 | Y | 38.521-1 | 6.5F.2.4.1 | Shared spectrum channel access ACLR |  | Qualcomm | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 1 | 0% |  | 1 | 1 | 1
28 | Y | 38.521-1 | 6.5F.2.4.2 | Additional requirements for network signaled value "NS_29" |  | Ericsson | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 2 | 0% |  | 1 | 1 | 1
Spurious emissions(Clause 6.5F.3)
29 | Y | 38.521-1 | 6.5F.3.1 | General spurious emissions |  | Qualcomm | RAN5#93 (Nov-21) | R5-215985 | Test configuration table is FFS TP analysis is TBD Test state and generic procedure are TBD in 38.508-1 | 1 | 60% |  | 1 | 60% | 1 | 1 | 1 | 1
30 |  | 38.521-1 | 6.5F.3.2 | Spurious emissions for UE co-existence |  | Qualcomm | RAN5#93 (Nov-21) | R5-215985 | not applicable | 1 | 100% |  | 1 | 100% | 1 | 1 | 1 | 1
31 |  | 38.521-1 | 6.5F.3.3 | Additional spurious emissions | [5 empty] | 1 | 0% |  | 4 | 0% | 1 | 1 | 1 | 1
32 | Y | 38.521-1 | 6.5F.3.3.1 | Requirements for network signaled value "NS_28" |  | Ericsson | RAN5#93 (Nov-21) |  | Combine all NS values into one test case, 6.5F.3.3 Additional spurious emissions. | 1 | 0% |  | 2 | 0% |  | 1 | 1 | 1
33 | Y | 38.521-1 | 6.5F.3.3.2 | Requirements for network signaled value "NS_29" |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 2 | 0% |  | 1 | 1 | 1
34 | Y | 38.521-1 | 6.5F.3.3.3 | Requirements for network signaled value "NS_30" |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 2 | 0% |  | 1 | 1 | 1
35 | Y | 38.521-1 | 6.5F.3.3.4 | Requirements for network signaled value "NS_31" |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 2 | 0% |  | 1 | 1 | 1
36 | Y | 38.521-1 | 6.5F.3.3.5 | Requirements for network signaled value "NS_53" or "NS_54" |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 2 | 0% |  | 1 | 1 | 1
37 | Y | 38.521-1 | 6.5F.4 | Transmit intermodulation |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 2 | 0% | 1 | 1 | 1 | 1
Receiver characteristics(Clause 7)
38 |  | 38.521-1 | 7.1 | General |  |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% |  | 3 | 0% | 1 | 1 | 1 | 1
39 |  | 38.521-1 | 7.2 | Diversity characteristics |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 3 | 0% | 1 | 1 | 1 | 1
Reference sensitivity for shared spectrum channel access (Clause 7.3F)
40 |  | 38.521-1 | 7.3.1 | General |  |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% |  | 4 | 0% | 1 | 1 | 1 | 1
41 | Y | 38.521-1 | 7.3F.2 | Reference sensitivity power level for shared spectrum channel access |  | Qualcomm | RAN5#93 (Nov-21) | R5-215562 | Test Configuration Table is FFS Message content for NS_53 is FFS TP analysis is TBD TT for 5.925GHz < f ≤ 7.125GHz is TBD | 1 | 60% |  | 1 | 60% | 1 | 1 | 1 | 1
42 | Y | 38.521-1 | 7.3F.3 | ΔRIB,c |  | Qualcomm | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 1 | 0% | 1 | 1 | 1 | 1
Maximum input level for shared spectrum channel access (Clause 7.4F)
43 | Y | 38.521-1 | 7.4F | Maximum input level |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 1 | 0% | 1 | 1 | 1 | 1
Adjacent channel selectivity for shared spectrum channel access (Clause 7.5F)
44 | Y | 38.521-1 | 7.5F | Adjacent channel selectivity | TS38.101-1 cl 7.5 |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 4 | 0% | 1 | 1 | 1 | 1
Blocking charateristics for shared spectrum channel access (Clause 7.6F)
45 |  | 38.521-1 | 7.6F.1 | General |  |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% |  | 4 | 0% | 1 | 1 | 1 | 1
46 | Y | 38.521-1 | 7.6F.2.1 | Inband blocking |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 3 | 0% | 1 | 1 | 1 | 1
48 |  | 38.521-1 | 7.6F.3 | Out of band blocking |  |  | RAN5#93 (Nov-21) |  |  | 0 | 0% |  | 2 | 0% | 1 | 1 | 1 | 1
Spurious response for shared spectrum channel access (Clause 7.7F)
Intermodulation characteristic for shared spectrum channel access (Clause 7.8F)
50 |  | 38.521-1 | 7.8F.1 | General |  |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% |  | 4 | 0% | 1 | 1 | 1 | 1
51 | Y | 38.521-1 | 7.8F.2 | Wide band Intermodulation |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 3 | 0% | 1 | 1 | 1 | 1
Annex
52 |  | 38.521-1 | Annex A | measurement channels | define mesurement channels |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 8 | 0% | 1 | 1 | 1 | 1
53 |  | 38.521-1 | Annex B | Propagation conditions | Define propagation conditions |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 5 | 0% | 1 | 1 | 1 | 1
54 |  | 38.521-1 | Annex C | Downlink physical channels | Define downlink physical channels |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 8 | 0% | 1 | 1 | 1 | 1
55 |  | 38.521-1 | Annex D | Characteristics of the interfering signal | Define characteristics of the interfering signal |  |  |  |  | 1 | 0% | 1 | 8 | 0% | 1 | 1 | 1 | 1
56 |  | 38.521-1 | Annex E | Global In-Channel TX-Test | Specifiy the measurement of all relevant parameters that describe the in-channel quality of the output signal of the TX under test in a single measurement process |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 7 | 0%
57 |  | 38.521-1 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 8 | 0% | 1 | 1 | 1 | 1
58 |  | 38.521-1 | Annex G | Uplink Physical Channels | Define uplink physical channels |  | RAN5#93 (Nov-21) | R5-215893 |  | 1 | 10% |  | 8 | 10%
59 |  | 38.521-1 | Annex H | Statistical Testing |  |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 8 | 0%
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Y = the WP Pitem is a test case.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.