## Cover sheet
3GPP TSG-RAN WG5 Meeting #93-e | [10 empty] | R5-217404
Electronic Meeting, 08th - 19th Nov 2021
Agenda Item: | 7.4.2
Source: | Huawei, Samsung
Title: | WP UE Conformance Test Aspects for Enhancements on MIMO for NR
Work item code: | NR_eMIMO-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of the UE Conformance Test Aspects for Enhancements on MIMO for NR work item is to define the UE conformance requirements corresponding to WID on enhancement on MIMO for NR, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-16. At the RAN#88 meeting in June 2020 the Rel-16 RAN5 work item for UE Conformance Test Aspects for Enhancements on MIMO for NR was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 47% (+12%) | 13 (+4) | 64
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 43.2% (+8.5%) | 13 (+4) | 48
FR1 |  | 59.6% (+12.6%) | 13 (+4) | 38
FR2 |  | 9.7% | 0 | 11
NSA Option 3 (EN-DC) |  | 56.6% (+19%) | 8 | 37
FR1 |  | 76% (+26.9%) | 8 | 29
FR2 |  | 10% | 0 | 9
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 12.1% (+3.2%) |  |  | 18% (+4%) |  |  | 0% |  |  |  | 16% (+6%) |  |  | 0%
Common ICS | 38.508-2 | 63.9% (+13.9%) |  |  | 70% (+20%) |  |  | 50% |  |  |  | 70% (+20%) |  |  | 50%
NR RF/RRM
FR1 RF common parts | 38.521-1 | 8.3% |  |  | 8.3%
FR1 RF Tx test cases | 38.521-1 Tx | 78.8% (+4.2%) | 5 (+4) | 9 | 78.8% (+4.2%) | 5 (+4) | 9
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2 | 0% | [5 empty] | 0%
FR2 RF Tx test cases | 38.521-2 Tx | 21.6% | 0 | 2 |  |  |  | 21.6% | 0 | 2
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4 | 92.6% (+18.7%) | 8 | 20 | 92.3% (+18.8%) | 8 | 20 |  |  |  |  | 93.4% (+18.3%) | 8 | 20
RRM test cases | 38.533 | 24.6% (+24.6%) | 0 | 32 | 21% (+21%) | 0 | 8 | 0% | 0 | 8 |  | 77.3% (+77.3%) | 0 | 8 | 0% | 0 | 8
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 22.8% (+6.5%) |  |  | 28% (+8%) |  |  | 0% |  |  |  | 46.7% (+13.3%) |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 41.4% (+0.1%) |  |  | 60% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 31.5% (-0%) | 0 | 1 | 30% | 0 | 1 | 35% | 0 | 1 |  | 30% | 0 | 1 | 35% | 0 | 1
Applicability Protocol test cases | 38.523-2 | 50% |  |  | 50% |  |  | 50% |  |  |  | 50% |  |  | 50%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-200895 | New WID on UE Conformance Test Aspects for Enhancements on MIMO for NR; Huawei, Samsung
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects for Enhancements on MIMO for NR | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_eMIMO-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for Enhancements on MIMO for NR comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [13 empty] | vs Area
WP Resp: |  | Chunying Gu, Huawei |  |  | guchunying@huawei.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 | FR2
[15 empty] | 59.6% (+12.6%) | 9.7% | 76% (+26.9%) | 10%
[15 empty] | 118 (+1) | 53 | 70 | 28
[15 empty] | 83.4 (+0.1) | 40.8 | 41.1 | 17.1
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
5GS - RAN and CN
5GS Common
TS 38.508-1: Common test environment
117 |  | 38.508-1 | 4.3 | Reference test conditions | Adding necessary test conditions for eMIMO features | Huawei | TBD | R5-205932 |  | 1 | 2.5% | 5% | 0% |  | 10% | 0% | 0% | 0%
118 |  | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | New message and IE definition for eMIMO features |  | TBD |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
119 |  | 38.508-1 | 5 | Test environments for RF test | Necessary changes to RF test environments | Huawei | TBD | R5-205932 R5-217366 |  | 1 | 15% (+12.5%) | 15% (+10%) | 15% (+15%) |  | 30% | 0% | 30% | 0%
120 |  | 38.508-1 | 7 | Test environments for RRM tests | Necessary changes to RRM test environments |  | TBD |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
195 |  | 38.508-1 | Annex A | Connection Diagrams | Connection Diagrams | Huawei | TBD | R5-216070 |  | 1 | 25% | 25% | 25% |  | 50% | 0% | 50% | 0%
TS 38.508-2: Common ICS
1 |  | 38.508-2 | A.4 | ICS proforma tables | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | Lenovo, Motorola Mobility, Huawei, HiSilicon, Bureau Veritas, Ericsson | RAN5#93 (Nov-21) | R5-206414 R5-212938 R5-215095 R5-215933 R5-215184 R5-218307 |  | 0.2 | 60% (+10%) | 60% (+10%) | 60% (+10%) |  | 70% | 50% | 70% | 50%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
2 |  | 38.521-1 | 2 | Reference | Define References made in TS |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
3 |  | 38.521-1 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively | Ericsson | RAN5#89-e (Nov-20) | R5-205557 |  | 0.1 | 100% | 100% |  |  | 100%
4 |  | 38.521-1 | 4 | General | define categories of test requirements |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
5 |  | 38.521-1 | 5 | Operating bands and Channel arrangement | define the frequency bands and channel arragement |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
6 |  | 38.521-1 | Annex A | measurement channels | define mesurement channels |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
7 |  | 38.521-1 | Annex B | Propagation conditions | Define propagation conditions |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
8 |  | 38.521-1 | Annex C | Downlink physical channels | Define downlink physical channels |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
9 |  | 38.521-1 | Annex D | Characteristics of the interfering signal | Define characteristics of the interfering signal |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
10 |  | 38.521-1 | Annex E | Global In-Channel TX-Test | Specifiy the measurement of all relevant parameters that describe the in-channel quality of the output signal of the TX under test in a single measurement process |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
11 |  | 38.521-1 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
12 |  | 38.521-1 | Annex G | Uplink Physical Channels | Define uplink physical channels |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
13 |  | 38.521-1 | Annex H | Statistical Testing |  |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0%
TS 38.521-1: FR1 RF test cases - Tx
14 |  |  | 6.2.2 | UE maximum output power reduction | Adding minimum requirement and additional test point for R16 DMRS | Huawei | RAN5#91-e (May-21) | R5-205791, R5-210782 R5-216141 R5-217215 | Ref: 38.101-1 6.2.2 38.522: No changes needed 38.905: R5-206857, R5-216142 | 1 | 100% | 100% |  |  | 100%
15 |  | 38.521-1 Tx | 6.2.3 | UE additional maximum output power reduction | Adding minimum requirement; Analysing whether additional test point for R16 DMRS is needed Minimum requirment for R16 DMRS is the same as for R15 DMRS. Given the UE can pass the requirements using R15 DMRS, it can be expected that UE can psss the requirements using R16 DMRS. Therefore there is no need to additionally test the R16 DMRS. | Huawei | RAN5#90-e (Feb-21) | R5-210782 R5-217216 | Ref: 38.101-1 6.2.3 38.522: No changes needed 38.905: R5-211809 | 1 | 100% | 100% |  |  | 100%
16 |  | 38.521-1 Tx | 6.4.2.5 | EVM equalizer spectrum flatness for Pi/2 BPSK | Adding minimum requirement and additional test point for R16 DMRS | Huawei | RAN5#91-e (May-21) | R5-211807 R5-216141 | Ref: 38.101-1 6.4.2.4.1 38.522: R5-215935 38.905: R5-211810 , R5-216142 | 1 | 100% | 100% |  |  | 100%
17 |  | 38.521-1 Tx | 6.5.2.2 | Spectrum Emission Mask | Adding additional test point for R16 DMRS as per MPR | Huawei | RAN5#91-e (May-21) | R5-206766 R5-216141 | Ref: 38.101-1 6.5.2.2 38.522: No changes needed 38.905: R5-206857, R5-216142 | 1 | 100% | 100% |  |  | 100%
18 |  | 38.521-1 Tx | 6.5.2.4.1 | NR ACLR | Adding additional test point for R16 DMRS as per MPR | Huawei | RAN5#91-e (May-21) | R5-206767 R5-216141 R5-217215 | Ref: 38.101-1 6.5.2.4.1 Pending on RAN2/RAN4 capability alignment 38.522: No changes needed 38.905: R5-206857, R5-216142 | 1 | 100% | 100% |  |  | 100%
19 |  | 38.521-1 Tx | 6.2C.4 | UE maximum output power reduction for SUL | Adding additional test point for R16 DMRS | Huawei | RAN5#91-e (May-21) | R5-211915 R5-217215 | Ref: 38.101-1 6.2C, 6.2.2 Pending on RAN2/RAN4 capability alignment 38.522: No changes needed 38.905: R5-211811 | 1 | 100% (+10%) | 100% (+10%) |  |  | 100%
20 |  | 38.521-1 Tx | 6.2C.5 | UE additional maximum output power reduction for SUL | Adding minimum requirement; Analysing whether additional test point for R16 DMRS is needed |  | RAN5#91-e (May-21) |  | Ref: 38.101-1 6.2C, 6.2.3 No changes needed | 1 | 100% | 100% |  |  | 100%
21 | Y | 38.521-1 Tx | 6.4C.2.5 | EVM equalizer spectrum flatness for Pi/2 BPSK for SUL | Adding test point for R16 DMRS |  | RAN5#91-e (May-21) | R5-211808 R5-216141 | Ref: 38.101-1 6.4.2.5 38.522: R5-210792, R5-215935 38.905: R5-210791, R5-216142 | 1 | 100% | 100% |  |  | 100%
22 |  | 38.521-1 Tx | 6.5C.2.2 | Spectrum Emission Mask for SUL | Adding additional test point for R16 DMRS as per MPR | Huawei | RAN5#91-e (May-21) | R5-210787 R5-217215 | Ref: 38.101-1 6.5.2.2 Pending on RAN2/RAN4 capability alignment 38.522: No changes needed 38.905: R5-211811 | 1 | 100% (+10%) | 100% (+10%) |  |  | 100%
23 |  | 38.521-1 Tx | 6.5C.2.4.1 | NR ACLR for SUL | Adding additional test point for R16 DMRS as per MPR | Huawei | RAN5#91-e (May-21) | R5-210788 R5-217215 | Ref: 38.101-1 6.5.2.4.1 Pending on RAN2/RAN4 capability alignment 38.522: No changes needed 38.905: R5-211811 | 1 | 100% (+10%) | 100% (+10%) |  |  | 100%
24 |  | 38.521-1 Tx | 6.2D.1 | UE maximum output power for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#90-e (Feb-21) | R5-205796 | Ref: 38.101-1 6.2D.1 38.522: No changes needed 38.905: R5-206858 | 1 | 100% | 100% |  |  | 100%
25 |  | 38.521-1 Tx | 6.2D.2 | UE maximum output power reduction for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Ericsson | RAN5#91-e (May-21) | R5-211133 R5-215185 | Ref: 38.101-1 6.2D.2 FFS:Test requirements for PC2 are missing 38.522: No changes needed 38.905: R5-211134 | 1 | 100% | 100% |  |  | 100%
26 |  | 38.521-1 Tx | 6.2D.3 | UE additional maximum output power reduction for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Apple | RAN5#91-e (May-21) |  | Ref: 38.101-1 6.2D.3 38.522: 38.905: | 1 | 0% | 0% |  |  | 0%
27 |  | 38.521-1 Tx | 6.2D.4 | Configured transmitted power for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Ericsson | RAN5#91-e (May-21) | R5-214007 | Ref: 38.101-1 6.2D.4 38.522: No changes needed 38.905: R5-213053 | 1 | 100% | 100% |  |  | 100%
28 | Y | 38.521-1 Tx | 6.5D.1_1 | Occupied bandwidth for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. | Ericsson | RAN5#91-e (May-21) | R5-206894 | Ref: 38.101-1 6.5D.1 Test applicability is TBD Test point analysis is TBD 38.522: 38.905: R5-214721 | 1 | 70% | 70% |  |  | 70%
29 |  | 38.521-1 Tx | 6.5D.2_1 | Out of band emission for UL MIMO (Rel-16 onward) | New Sub-title |  |  |  | Sub-title | 0
30 |  | 38.521-1 Tx | 6.5D.2_1.1 | General | Measurement is changed to sum of both antenna connectors: Updating minimum requirement |  | RAN5#91-e (May-21) |  | Ref: 38.101-1 6.5D.2 | 0.1 | 0% | 0% |  |  | 0%
31 | Y | 38.521-1 Tx | 6.5D.2_1.2 | Spectrum Emission Mask for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power |  | RAN5#91-e (May-21) |  | Ref: 38.101-1 6.5D.2 38.522: 38.905: | 1 | 0% | 0% |  |  | 0%
32 | Y | 38.521-1 Tx | 6.5D.2_1.3 | Additional spectrum emission mask for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power |  | RAN5#91-e (May-21) |  | Ref: 38.101-1 6.5D.2 38.522: 38.905: | 1 | 0% | 0% |  |  | 0%
33 | Y | 38.521-1 Tx | 6.5D.2_1.4.1 | NR ACLR for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Ericsson | RAN5#91-e (May-21) |  | Ref: 38.101-1 6.5D.2 38.522: 38.905: | 1 | 0% | 0% |  |  | 0%
34 | Y | 38.521-1 Tx | 6.5D.2_1.4.2 | UTRA ACLR for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Ericsson | RAN5#91-e (May-21) | R5-210996 R5-213058 | Ref: 38.101-1 6.5D.2 FFS: Applicability of test points with UL-MIMO wi and w/o ULFPTx; Refered test case 6.2D.3 is not complete. 38.522: TBDR5-218463 38.905: R5-211018 | 1 | 100% (+30%) | 100% (+30%) |  |  | 100%
35 |  | 38.521-1 Tx | 6.5D.3_1 | Spurious emissions for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement |  | RAN5#91-e (May-21) |  | Ref: 38.101-1 6.5D.3 38.522: 38.905: | 0.1 | 0% | 0% |  |  | 0%
36 | Y | 38.521-1 Tx | 6.5D.3_1.1 | General spurious emissions for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#91-e (May-21) | R5-206768 | Ref: 38.101-1 6.5D.3 Test applicability is TBD 38.522: R5-210792, R5-218463 38.905: R5-206769 | 1 | 100% (+10%) | 100% (+10%) |  |  | 100%
37 | Y | 38.521-1 Tx | 6.5D.3_1.2 | Spurious emission for UE co-existence for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#91-e (May-21) | R5-205799 | Ref: 38.101-1 6.5D.3 Test applicability is TBD 38.522: R5-210792, R5-218463 38.905: R5-206769 | 1 | 100% (+10%) | 100% (+10%) |  |  | 100%
38 | Y | 38.521-1 Tx | 6.5D.3_1.3 | Additional spurious emissions for UL MIMO (Rel-16 onward) | Measurement is changed to sum of both antenna connectors: Updating minimum requirement and test procedure. Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#91-e (May-21) | R5-205800 | Ref: 38.101-1 6.5D.3 Test applicability is TBD 38.522: R5-210792, R5-218463 38.905: R5-206769 | 1 | 100% (+10%) | 100% (+10%) |  |  | 100%
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
39 |  | 38.521-2 | 2 | Reference | Define References made in TS |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
40 |  | 38.521-2 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively | Ericsson | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
41 |  | 38.521-2 | 4 | General | define categories of test requirements |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
42 |  | 38.521-2 | 5 | Operating bands and Channel arrangement | define the frequency bands and channel arragement |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
43 |  | 38.521-2 | Annex A | measurement channels | define mesurement channels |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
44 |  | 38.521-2 | Annex B | Propagation conditions | Define propagation conditions |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
45 |  | 38.521-2 | Annex C | Downlink physical channels | Define downlink physical channels |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
46 |  | 38.521-2 | Annex D | Characteristics of the interfering signal | Define characteristics of the interfering signal |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
47 |  | 38.521-2 | Annex E | Global In-Channel TX-Test | Specifiy the measurement of all relevant parameters that describe the in-channel quality of the output signal of the TX under test in a single measurement process |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
48 |  | 38.521-2 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
49 |  | 38.521-2 | Annex G | Uplink Physical Channels | Define uplink physical channels |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
50 |  | 38.521-2 | Annex H | Statistical Testing |  |  | RAN5#93 (Dec-2021) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
TS 38.521-2: FR2 RF test cases - Tx
51 |  | 38.521-2 Tx | 6.2D.1 | UE maximum output power for UL MIMO | Sub-title Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power |  |  |  |  | 0
196 |  | 38.521-2 Tx | 6.2D.1.0 | General | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei, Apple , SGS | RAN5#93 (Nov-21) | R5-216111 | Ref: 38.101-2 6.2D.1 | 0.1 | 100% | 100% |  |  |  | 100%
197 | Y | 38.521-2 Tx | 6.2D.1.1 | UE maximum output power - EIRP and TRP for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei, Apple , SGS | RAN5#93 (Nov-21) | R5-216111 | Ref: 38.101-2 6.2D.1 38.522: 38.905: Editor’s note: This clause is incomplete. The following aspects are either missing or not yet determined: - No test points are defined for 2-layer UL MIMO since there is no configuration satisfying MPR=0dB requirements in RAN4. - Measurement Uncertainties and Test Tolerances are FFS for power class 1, 2 ,4 and 5. - Test Procedures for EIRP beam peak Extreme Conditions are FFS. - Configuration of ULFPTx is FFS. | 1 | 50% | 50% |  |  |  | 50%
198 | Y | 38.521-2 Tx | 6.2D.1.2 | 6.2D.1.2 UE maximum output power - Spherical coverage for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei, Apple , SGS | RAN5#93 (Nov-21) | R5-216111 | Ref: 38.101-2 6.2D.1 38.522: 38.905: Editor’s note: This clause is incomplete. The following aspects are either missing or not yet determined: - No test points are defined for 2-layer UL MIMO since there is no configuration satisfying MPR=0dB requirements in RAN4. - Measurement Uncertainties and Test Tolerances are FFS for power class 1, 2 ,4 and 5. - Test Procedures for EIRP beam peak Extreme Conditions are FFS. - Configuration of ULFPTx is FFS. | 1 | 50% | 50% |  |  |  | 50%
52 |  | 38.521-2 Tx | 6.2D.2 | UE maximum output power reduction for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Huawei | RAN5#93 (Nov-21) |  | Ref: 38.101-2 6.2D.2 38.522: 38.905: | 1 | 0% | 0% |  |  |  | 0%
53 |  | 38.521-2 Tx | 6.2D.3 | UE additional maximum output power reduction for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power |  | RAN5#93 (Nov-21) |  | Ref: 38.101-2 6.2D.3 38.522: 38.905: | 1 | 0% | 0% |  |  |  | 0%
54 |  | 38.521-2 Tx | 6.2D.4 | Configured transmitted power for UL MIMO | Updating minimum requirement Adding test description for ULFPTx Mode 1 (DFT-s-OFDM only), Mode 2 and Mode Full power | Ericsson | RAN5#93 (Nov-21) |  | Ref: 38.101-2 6.2D.4 38.522: 38.905: | 1 | 0% | 0% |  |  |  | 0%
TS 38.521-4: Demod/QSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
General
55 |  | 38.521-4 | 2 | References | Define References made in TS |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
56 |  | 38.521-4 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively |  | RAN5#93 (Nov-21) |  | TS 38.101-4 cl.3 | 0.1 | 0% | 0% |  |  | 0%
57 |  | 38.521-4 | 4 | General | define categories of test requirements |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0%
58 |  | 38.521-4 | 5.1.1.3 | Applicability of requirements for optional UE features | define applicability of multi-TRP test cases | Apple | RAN5#93 (Nov-21) | R5-216787 | TS 38.101-4 cl.5.1.1.3 | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
59 |  | 38.521-4 | 5.1.1.8 | Applicability of different requirements with Multi-TRP | define test cases selection rule of multi-TRP test cases | Apple | RAN5#93 (Nov-21) | R5-216786 | TS 38.101-4 cl.5.1.1.8 | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
195 |  | 38.521-4 | 6.1.1.3 | Applicability of requirements for optional UE features | define applicability of PMI reporting test cases | Huawei | RAN5#93 (Nov-21) | R5-218312 | TS 38.101-4 cl.5.1.1.3 | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
Demodulation performance requirements (Conducted requirements) (Clause 5)
60 |  | 38.521-4 | 5.2 | PDSCH demodulation requirements | Sub-title |  |  |  |  | 0
61 |  | 38.521-4 | 5.2.2.1.11 | 2Rx FDD FR1 PDSCH Single-DCI based SDM scheme performance | Sub-title |  |  |  |  | 0
162 |  | 38.521-4 | 5.2.2.1.11.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R25-212933 | TS 38.101-4 cl.5.2.2.1.11 Brackets in RAN4 | 0.1 | 90% | 90% | 90% |  | 90% |  | 90%
163 | Y | 38.521-4 | 5.2.2.1.11_1 | 2Rx FDD FR1 PDSCH Single-DCI based SDM scheme performance - 2x2 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI | Huawei | RAN5#93 (Nov-21) | R25-212933 | TS 38.101-4 cl.5.2.2.1.11 Brackets in RAN4 TS 38.522: R5-212939 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Minimum requirements are within brackets - MU and TT are FFS | 1 | 90% | 90% | 90% |  | 90% |  | 90%
62 |  | 38.521-4 | 5.2.2.1.12 | 2Rx FDD FR1 PDSCH Multi-DCI based transmission scheme performance | Sub-title |  |  |  |  | 0
164 |  | 38.521-4 | 5.2.2.1.12.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-216126 | TS 38.101-4 cl.5.2.2.1.12 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
165 | Y | 38.521-4 | 5.2.2.1.12_1 | 2Rx FDD FR1 PDSCH Multi-DCI based transmission scheme performance - 2x2 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Multi-DCI | Huawei | RAN5#93 (Nov-21) | R5-216126 | TS 38.101-4 cl.5.2.2.1.12 TS 38.522: R5-215935 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
63 |  | 38.521-4 | 5.2.2.1.13 | 2Rx FDD FR1 PDSCH Single-DCI based FDM scheme A performance | Sub-title |  |  |  |  | 0
166 |  | 38.521-4 | 5.2.2.1.13.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-216127 | TS 38.101-4 cl.5.2.2.1.13 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
167 | Y | 38.521-4 | 5.2.2.1.13_1 | 2Rx FDD FR1 PDSCH Single-DCI based FDM scheme A performance - 2x2 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based FDM scheme A | Huawei | RAN5#93 (Nov-21) | R5-216127 | TS 38.101-4 cl.5.2.2.1.13 TS 38.522: R5-215935 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
64 |  | 38.521-4 | 5.2.2.1.14 | 2Rx FDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance | Sub-title |  |  |  |  | 0
168 |  | 38.521-4 | 5.2.2.1.14.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-216128 | TS 38.101-4 cl.5.2.2.1.14 | 0.1 | 90% | 90% | 90% |  | 90% |  | 90%
169 | Y | 38.521-4 | 5.2.2.1.14_1 | 2Rx FDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance - 2x2 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based Inter-slot TDM scheme | Huawei | RAN5#93 (Nov-21) | R5-216128 | TS 38.101-4 cl.5.2.2.1.14 TS 38.522: R5-215935 Annex G is FFS | 1 | 90% | 90% | 90% |  | 90% |  | 90%
65 |  | 38.521-4 | 5.2.2.2.11 | 2Rx TDD FR1 PDSCH Single-DCI based SDM scheme performance | Sub-title |  |  |  |  | 0
170 |  | 38.521-4 | 5.2.2.2.11.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R25-212934 | TS 38.101-4 cl.5.2.2.2.11 Brackets in RAN4 | 0.1 | 90% | 90% | 90% |  | 90% |  | 90%
171 | Y | 38.521-4 | 5.2.2.2.11_1 | 2Rx TDD FR1 PDSCH Single-DCI based SDM scheme performance - 2x2 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI | Huawei | RAN5#93 (Nov-21) | R25-212934 | TS 38.101-4 cl.5.2.2.2.11 TS 38.522: R5-212939 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Minimum requirements are within brackets - MU and TT are FFS | 1 | 90% | 90% | 90% |  | 90% |  | 90%
66 |  | 38.521-4 | 5.2.2.2.12 | 2Rx TDD FR1 PDSCH Multi-DCI based transmission scheme performance | Sub-title |  |  |  |  | 0
172 |  | 38.521-4 | 5.2.2.2.12.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-215084 | TS 38.101-4 cl.5.2.2.2.12 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
173 | Y | 38.521-4 | 5.2.2.2.12_1 | 2Rx TDD FR1 PDSCH Multi-DCI based transmission scheme performance - 2x2 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Multi-DCI | Huawei | RAN5#93 (Nov-21) | R5-215084 | TS 38.101-4 cl.5.2.2.2.12 TS 38.522: R5-215935 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
67 |  | 38.521-4 | 5.2.2.2.13 | 2Rx TDD FR1 PDSCH Single-DCI based FDM scheme A performance | Sub-title |  |  |  |  | 0
174 |  | 38.521-4 | 5.2.2.2.13.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-215085 | TS 38.101-4 cl.5.2.2.2.13 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
175 | Y | 38.521-4 | 5.2.2.2.13_1 | 2Rx TDD FR1 PDSCH Single-DCI based FDM scheme A performance - 2x2 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based FDM scheme A | Huawei | RAN5#93 (Nov-21) | R5-215085 | TS 38.101-4 cl.5.2.2.2.13 TS 38.522: R5-215935 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
68 |  | 38.521-4 | 5.2.2.2.14 | 2Rx TDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance | Sub-title |  |  |  |  | 0
176 |  | 38.521-4 | 5.2.2.2.14.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-216071 | TS 38.101-4 cl.5.2.2.2.14 | 0.1 | 90% | 90% | 90% |  | 90% |  | 90%
177 | Y | 38.521-4 | 5.2.2.2.14_1 | 2Rx TDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance - 2x2 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based Inter-slot TDM scheme | Huawei | RAN5#93 (Nov-21) | R5-216071 | TS 38.101-4 cl.5.2.2.2.14 TS 38.522: R5-215935 Annex G is FFS | 1 | 90% | 90% | 90% |  | 90% |  | 90%
69 |  | 38.521-4 | 5.2.3.1.11 | 4Rx FDD FR1 PDSCH Single-DCI based SDM scheme performance | Sub-title |  |  |  |  | 0
178 |  | 38.521-4 | 5.2.3.1.11.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R25-212935 | TS 38.101-4 cl.5.2.3.1.11 Brackets in RAN4 | 0.1 | 90% | 90% | 90% |  | 90% |  | 90%
179 | Y | 38.521-4 | 5.2.3.1.11_1 | 4Rx FDD FR1 PDSCH Single-DCI based SDM scheme performance - 2x4 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI | Huawei | RAN5#93 (Nov-21) | R25-212935 | TS 38.101-4 cl.5.2.3.1.11 Brackets in RAN4 TS 38.522: R5-212939 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Minimum requirements are within brackets - MU and TT are FFS | 1 | 90% | 90% | 90% |  | 90% |  | 90%
70 |  | 38.521-4 | 5.2.3.1.12 | 4Rx FDD FR1 PDSCH Multi-DCI based transmission scheme performance | Sub-title |  |  |  |  | 0
180 |  | 38.521-4 | 5.2.3.1.12.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-215934 | TS 38.101-4 cl.5.2.3.1.12 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
181 | Y | 38.521-4 | 5.2.3.1.12_1 | 4Rx FDD FR1 PDSCH Multi-DCI based transmission scheme performance - 2x4 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Multi-DCI | Huawei | RAN5#93 (Nov-21) | R5-215934 | TS 38.101-4 cl.5.2.3.1.12 TS 38.522: R5-215935 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
71 |  | 38.521-4 | 5.2.3.1.13 | 4Rx FDD FR1 PDSCH Single-DCI based FDM scheme A performance | Sub-title |  |  |  |  | 0
182 |  | 38.521-4 | 5.2.3.1.13.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-216129 | TS 38.101-4 cl.5.2.3.1.13 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
183 | Y | 38.521-4 | 5.2.3.1.13_1 | 4Rx FDD FR1 PDSCH Single-DCI based FDM scheme A performance - 2x4 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based FDM scheme A | Huawei | RAN5#93 (Nov-21) | R5-216129 | TS 38.101-4 cl.5.2.3.1.13 TS 38.522: R5-215935 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
72 |  | 38.521-4 | 5.2.3.1.14 | 4Rx FDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance | Sub-title |  |  |  |  | 0
184 |  | 38.521-4 | 5.2.3.1.14.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-216130 | TS 38.101-4 cl.5.2.3.1.14 | 0.1 | 90% | 90% | 90% |  | 90% |  | 90%
185 | Y | 38.521-4 | 5.2.3.1.14_1 | 4Rx FDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance - 2x4 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based Inter-slot TDM scheme | Huawei | RAN5#93 (Nov-21) | R5-216130 | TS 38.101-4 cl.5.2.3.1.14 TS 38.522: R5-215935 Annex G is FFS | 1 | 90% | 90% | 90% |  | 90% |  | 90%
73 |  | 38.521-4 | 5.2.3.2.11 | 4Rx TDD FR1 PDSCH Single-DCI based SDM scheme performance | Sub-title |  |  |  |  | 0
186 |  | 38.521-4 | 5.2.3.2.11.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-212936 | TS 38.101-4 cl.5.2.3.2.11 Brackets in RAN4 | 0.1 | 90% | 90% | 90% |  | 90% |  | 90%
187 | Y | 38.521-4 | 5.2.3.2.11_1 | 4Rx TDD FR1 PDSCH Single-DCI based SDM scheme performance - 2x4 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI | Huawei | RAN5#93 (Nov-21) | R5-212936 | TS 38.101-4 cl.5.2.3.2.11 Brackets in RAN4 TS 38.522: R5-212939 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Minimum requirements are within brackets - MU and TT are FFS | 1 | 90% | 90% | 90% |  | 90% |  | 90%
74 |  | 38.521-4 | 5.2.3.2.12 | 4Rx TDD FR1 PDSCH Multi-DCI based transmission scheme performance | Sub-title |  |  |  |  | 0
188 |  | 38.521-4 | 5.2.3.2.12.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-215090 | TS 38.101-4 cl.5.2.3.2.12 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
189 | Y | 38.521-4 | 5.2.3.2.12_1 | 4Rx TDD FR1 PDSCH Multi-DCI based transmission scheme performance - 2x4 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Multi-DCI | Huawei | RAN5#93 (Nov-21) | R5-215090 | TS 38.101-4 cl.5.2.3.2.12 TS 38.522: R5-215935 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
75 |  | 38.521-4 | 5.2.3.2.13 | 4Rx TDD FR1 PDSCH Single-DCI based FDM scheme A performance | Sub-title |  |  |  |  | 0
190 |  | 38.521-4 | 5.2.3.2.13.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-215091 | TS 38.101-4 cl.5.2.3.2.13 | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
191 | Y | 38.521-4 | 5.2.3.2.13_1 | 4Rx TDD FR1 PDSCH Single-DCI based FDM scheme A performance - 2x4 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based FDM scheme A | Huawei | RAN5#93 (Nov-21) | R5-215091 | TS 38.101-4 cl.5.2.3.2.13 TS 38.522: R5-215935 | 1 | 100% | 100% | 100% |  | 100% |  | 100%
76 |  | 38.521-4 | 5.2.3.2.14 | 4Rx TDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance | Sub-title |  |  |  |  | 0
192 |  | 38.521-4 | 5.2.3.2.14.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-215092 | TS 38.101-4 cl.5.2.3.2.14 | 0.1 | 90% | 90% | 90% |  | 90% |  | 90%
193 | Y | 38.521-4 | 5.2.3.2.14_1 | 4Rx TDD FR1 PDSCH Single-DCI based Inter-slot TDM scheme performance - 2x4 MIMO | PDSCH demodulation requirements for PDSCH from 2TRPs with Single-DCI based Inter-slot TDM scheme | Huawei | RAN5#93 (Nov-21) | R5-215092 | TS 38.101-4 cl.5.2.3.2.14 TS 38.522: R5-215935 Annex G is FFS | 1 | 90% | 90% | 90% |  | 90% |  | 90%
CSI reporting requirements (Conducted requirements) (Clause 6)
77 |  | 38.521-4 | 6.3 | Reporting of Precoding Matrix Indicator (PMI) | Sub-title |  | RAN5#93 (Nov-21) |  | R4-2103833 | 0.1 | 0% | 0% | 0% |  | 0% |  | 0%
78 | Y | 38.521-4 | 6.3.2.1.6 | 2Rx FDD FR1 Multiple PMI with 16Tx Enhanced Type II codebook for both SA and NSA | PMI reporting using enhanced Type II codebook | Huawei | RAN5#93 (Nov-21) | R5-218308 | TS 38.101-4 cl.6.3.2.1.6 Brackets in RAN4 TS 38.522 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Connection figure for 16 Tx is missing | 1 | 90% (+90%) | 90% (+90%) | 90% (+90%) |  | 90% |  | 90%
79 | Y | 38.521-4 | 6.3.2.2.6 | 2Rx TDD FR1 Multiple PMI with 16Tx Enhanced Type II codebook for both SA and NSA | PMI reporting using enhanced Type II codebook | Huawei | RAN5#93 (Nov-21) | R5-218309 | TS 38.101-4 cl.6.3.2.2.6 Brackets in RAN4 TS 38.522 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Connection figure for 16 Tx is missing | 1 | 90% (+90%) | 90% (+90%) | 90% (+90%) |  | 90% |  | 90%
80 | Y | 38.521-4 | 6.3.3.1.6 | 4Rx FDD FR1 Multiple PMI with 16Tx Enhanced Type II codebook for both SA and NSA | PMI reporting using enhanced Type II codebook | Huawei | RAN5#93 (Nov-21) | R5-218310 | TS 38.101-4 cl.6.3.3.1.6 Brackets in RAN4 TS 38.522 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Connection figure for 16 Tx is missing | 1 | 90% (+90%) | 90% (+90%) | 90% (+90%) |  | 90% |  | 90%
81 | Y | 38.521-4 | 6.3.3.2.6 | 4Rx TDD FR1 Multiple PMI with 16Tx Enhanced Type II codebook for both SA and NSA | PMI reporting using enhanced Type II codebook | Huawei | RAN5#93 (Nov-21) | R5-218311 | TS 38.101-4 cl.6.3.3.2.6 Brackets in RAN4 TS 38.522 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Connection figure for 16 Tx is missing | 1 | 90% (+90%) | 90% (+90%) | 90% (+90%) |  | 90% |  | 90%
Annex
82 |  | 38.521-4 | Annex A | measurement channels | define mesurement channels | Huawei | RAN5#93 (Nov-21) | R5-212937 R5-215093 R5-217363 | TS 38.101-4 cl.A.3 R.PDSCH.1-2.5 FDD, R.PDSCH.1-3.2 FDD, R.PDSCH.1-3.3 FDD, R.PDSCH.1-3.4 FDD, R.PDSCH.1-11.2 FDD, R.PDSCH.2-2.5 TDD, R.PDSCH.2-3.2 TDD, R.PDSCH.2-3.3 TDD, R.PDSCH.2-3.4 TDD, R.PDSCH.1-16.2 TDD | 0.1 | 70% (+20%) | 70% (+20%) | 70% (+20%) |  | 70% |  | 70%
83 |  | 38.521-4 | Annex B | Propagation conditions | Define propagation conditions | Huawei | RAN5#93 (Nov-21) | R5-217364 | TS 38.101-4 cl.B.2 B.2.3.2.3A Beam steering approach with dual cluster beams | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% |  | 100%
84 |  | 38.521-4 | Annex C | Downlink physical channels | Define downlink physical channels |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% | 0% |  | 0% |  | 0%
194 |  | 38.521-4 | Annex F | Measurement uncertainties and test tolerances | MU and TT | Huawei | RAN5#93 (Nov-21) | R5-215094 R5-218462 |  | 1 | 100% (+50%) | 100% (+50%) | 100% (+50%) |  | 100% |  | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Adding applicability for test cases in 38.521-1 | Huawei | RAN5#93 (Nov-21) | R5-210792 |  | 1 | 0% | 0% |  |  | 0%
|  | 38.522 | 4.1.2 | FR2 standalone conformance test cases | Adding applicability for test cases in 38.521-2 |  |  |  |  | 0.3 | 0% | 0% |  |  |  | 0%
|  | 38.522 | 4.1.4 | Performance conformance test cases | Adding applicability for test cases in 38.521-4 | Huawei |  | R5-212939 R5-215935 R5-218463 |  | 1 | 70% (+20%) | 70% (+20%) | 70% (+20%) |  | 70% |  | 70%
|  | 38.522 | 4.2 | RRM conformance test cases | Adding applicability for test cases in 38.533 |  |  |  |  | 0.5 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | Test cases for measurement performance(~4), Beam Failure Detection and Link Recovery (~8), Pathloss reference signal switching delay(~4) |  |  |  |  | 16 | 0% | 0% |  |  | 0% | 0%
General
85 |  | 38.533 | 2 | References | Define References made in TS |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0% | 0%
86 |  | 38.533 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively | Huawei | RAN5#93 (Nov-21) | R5-217211 | TS 38.133 cl.3 | 0.1 | 50% (+50%) | 50% (+50%) |  |  | 100% | 0%
87 |  | 38.533 | 4 | General | define categories of test requirements |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  |  | 0% | 0%
EN-DC tests within FR1 (Clause 4)
88 |  | 38.533 | 4.5 | Signaling characteristics | Sub-title |  |  |  |  | 0
|  | 38.533 | 4.5.5 | Link recovery procedures | Sub-title |  |  |  |  | 0
89 | Y | 38.533 | 4.5.5.5 | EN-DC FR1 Scell CSI-RS-based beam failure detection and SSB-based link recovery in non-DRX | BFD and LR procedure | Sporton | RAN5#93 (Nov-21) | R5-218320 | TS 38.133 cl.A.4.5.5.5 TS 38.903 TS 38.522 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - Test applicability is incomplete in TS 38.522. - MU & TT is FFS | 1 | 80% (+80%) |  | 80% (+80%) |  |  |  | 80%
90 | Y | 38.533 | 4.5.5.6 | EN-DC FR1 Scell CSI-RS-based beam failure detection and SSB-based link recovery in DRX | BFD and LR procedure | Sporton | RAN5#93 (Nov-21) | R5-218321 | TS 38.133 cl.A.4.5.5.6 TS 38.903 TS 38.522 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - Test applicability is incomplete in TS 38.522. - MU & TT is FFS | 1 | 80% (+80%) |  | 80% (+80%) |  |  |  | 80%
91 |  | 38.533 | 4.6 | Measurement procedures | Sub-title |  |  |  |  | 0
92 |  | 38.533 | 4.6.7 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
93 |  | 38.533 | 4.6.7.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-217203 | TS 38.133 cl.9.8.4.1, 9.8.4.2, 9.8.4.3 | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
94 | Y | 38.533 | 4.6.7.1 | EN-DC FR1 CSI-RS based CMR and no dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-218313 | TS 38.133 cl.A.4.6.7.1 TS 38.903 TS 38.522 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - The test requirement is FFS. - MU/TT is FFS. - Connection Diagram is TBD since the antenna configuration is not determined in TS 38.133. | 1 | 80% (+80%) |  | 80% (+80%) |  |  |  | 80%
95 | Y | 38.533 | 4.6.7.2 | EN-DC FR1 SSB based CMR and dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-218314 | TS 38.133 cl.A.4.6.7.2 TS 38.903 TS 38.522 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - The test requirement is FFS. - MU/TT is FFS. - Connection Diagram is TBD since the antenna configuration is not determined in TS 38.133. | 1 | 80% (+80%) |  | 80% (+80%) |  |  |  | 80%
96 | Y | 38.533 | 4.6.7.3 | EN-DC FR1 CSI-RS based CMR and dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-218315 | TS 38.133 cl.A.4.6.7.3 TS 38.903 TS 38.522 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - The test requirement is FFS. - MU/TT is FFS. - Connection Diagram is TBD since the antenna configuration is not determined in TS 38.133. | 1 | 80% (+80%) |  | 80% (+80%) |  |  |  | 80%
97 |  | 38.533 | 4.7 | Measurement Performance requirements | Sub-title |  |  |  |  | 0
98 |  | 38.533 | 4.7.7 | L1-SINR measurement for beam reporting | New Sub-title | Sporton | RAN5#93 (Nov-21) |  | R4-2100938 | 0
99 |  | 38.533 | 4.7.7.0 | Minimum conformance requirements |  | Sporton | RAN5#93 (Nov-21) | R5-218322 | TS 38.133 cl.9.8.4.1, 9.8.4.2, 9.8.3, 10.1.x, 10.1.Y1,3 | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
100 | Y | 38.533 | 4.7.7.1 | EN-DC FR1 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-218322 | TS 38.133 cl.A.4.7.7.1 TS 38.903 TS 38.522 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - The test requirement is FFS. - MU/TT is FFS. - Test applicability is incomplete in TS 38.522 | 1 | 80% (+80%) |  | 80% (+80%) |  |  |  | 80%
101 | Y | 38.533 | 4.7.7.2 | EN-DC FR1 SSB based CMR and dedicated IMR L1-SINR absolute measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-218464 | TS 38.133 cl.A.4.7.7.2 TS 38.903 TS 38.522 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - The test requirement is FFS. - MU/TT is FFS. - Test applicability is incomplete in TS 38.522. | 1 | 80% (+80%) |  | 80% (+80%) |  |  |  | 80%
102 | Y | 38.533 | 4.7.7.3 | EN-DC FR1 CSI-RS based CMR and dedicated IMR L1-SINR measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-218323 | TS 38.133 cl.A.4.7.7.3 TS 38.903 TS 38.522 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - MU & TT needs further study - Test applicability is incomplete | 1 | 80% (+80%) |  | 80% (+80%) |  |  |  | 80%
EN-DC tests including FR2 (Clause 5)
103 |  | 38.533 | 5.5 | Signaling characteristics | Sub-title |  |  |  |  | 0
104 | Y | 38.533 | 5.5.5.6 | EN-DC FR2 Scell CSI-RS-based beam failure detection and link recovery in non-DRX | BFD and LR procedure |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.5.5.5.6 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
105 | Y | 38.533 | 5.5.5.7 | EN-DC FR2 Scell CSI-RS-based beam failure detection and link recovery in DRX | BFD and LR procedure |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.5.5.5.7 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
106 |  | 38.533 | 5.6 | Measurement procedures | Sub-title |  |  |  |  | 0
107 |  | 38.533 | 5.6.5 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
108 |  | 38.533 | 5.6.5.0 | Minimum conformance requirements |  |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.9.8.4.1, 9.8.4.2, 9.8.4.3 | 0.1 | 0% |  | 0% |  |  |  |  | 0%
109 | Y | 38.533 | 5.6.5.1 | EN-DC FR2 CSI-RS based CMR and no dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.5.6.5.1 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
110 | Y | 38.533 | 5.6.5.2 | EN-DC FR2 SSB based CMR and dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.5.6.5.2 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
111 | Y | 38.533 | 5.6.5.3 | EN-DC FR2 CSI-RS based CMR and dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.5.6.5.3 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
112 |  | 38.533 | 5.7 | Measurement Performance requirements | Sub-title |  |  |  |  | 0
113 |  | 38.533 | 5.7.6 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
114 |  | 38.533 | 5.7.6.0 | Minimum conformance requirements |  |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.9.5.3, 9.8.4.2, 9.8.3, 10.1.Y.2, 10.1.x.x, 10.1.Y2.3 | 0.1 | 0% |  | 0% |  |  |  |  | 0%
115 | Y | 38.533 | 5.7.6.1 | EN-DC FR2 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR measurement accuracy | L1-SINR measurement performance |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.5.7.6.1 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
116 | Y | 38.533 | 5.7.6.2 | EN-DC FR2 SSB based CMR and dedicated IMR L1-SINR absolute measurement accuracy | L1-SINR measurement performance |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.5.7.6.2 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
117 | Y | 38.533 | 5.7.6.3 | EN-DC FR2 CSI-RS based CMR and dedicated IMR L1-SINR measurement accuracy | L1-SINR measurement performance |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.5.7.6.3 TS 38.903 TS 38.522 | 1 | 0% |  | 0% |  |  |  |  | 0%
NR standalone in FR1 (Clause 6)
118 |  | 38.533 | 6.5 | Signalling characteristics | Sub-title |  |  |  |  | 0
119 | Y | 38.533 | 6.5.5.5 | NR SA FR1 Scell CSI-RS-based beam failure detection and SSB-based link recovery in non-DRX | BFD and LR procedure |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.6.5.5.5 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  | 0%
120 | Y | 38.533 | 6.5.5.6 | NR SA FR1 Scell CSI-RS-based beam failure detection and SSB-based link recovery in DRX | BFD and LR procedure |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.6.5.5.6 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  | 0%
121 |  | 38.533 | 6.6 | Measurement procedures | Sub-title |  |  |  |  | 0
122 |  | 38.533 | 6.6.8 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
123 |  | 38.533 | 6.6.8.0 | Minimum conformance requirements |  | Huawei | RAN5#93 (Nov-21) | R5-217207 | TS 38.133 cl.9.8.4.1, 9.8.4.2, 9.8.4.3 | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
124 | Y | 38.533 | 6.6.8.1 | NR SA FR1 CSI-RS based CMR and no dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-218316 | TS 38.133 cl.A.6.6.8.1 TS 38.903 TS 38.522 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - The test requirement is FFS. - MU/TT is FFS. - Connection Diagram is TBD since the antenna configuration is not determined in TS 38.133. | 1 | 80% (+80%) | 80% (+80%) |  |  | 80%
125 | Y | 38.533 | 6.6.8.2 | NR SA FR1 SSB based CMR and dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-218317 | TS 38.133 cl.A.6.6.8.2 TS 38.903 TS 38.522 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - The test requirement is FFS. - MU/TT is FFS. - Connection Diagram is TBD since the antenna configuration is not determined in TS 38.133. | 1 | 80% (+80%) | 80% (+80%) |  |  | 80%
126 | Y | 38.533 | 6.6.8.3 | NR SA FR1 CSI-RS based CMR and dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) | R5-218318 | TS 38.133 cl.A.6.6.8.3 TS 38.903 TS 38.522 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - The test requirement is FFS. - MU/TT is FFS. - Connection Diagram is TBD since the antenna configuration is not determined in TS 38.133. | 1 | 80% (+80%) | 80% (+80%) |  |  | 80%
127 |  | 38.533 | 6.7 | Measurement Performance requirements | Sub-title |  |  |  |  | 0
128 |  | 38.533 | 6.7.9 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
129 |  | 38.533 | 6.7.9.0 | Minimum conformance requirements |  |  | RAN5#93 (Nov-21) | R5-218324 | TS 38.133 cl.9.5.3, 9.8.4.2, 9.8.3, 10.1.X.2, 10.1.x.x, 10.1.Y1.3 | 0.1 | 100% (+100%) | 100% (+100%) |  |  | 100%
130 | Y | 38.533 | 6.7.9.1 | NR SA FR1 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-218324 | TS 38.133 cl.A.6.7.9.1 TS 38.903 TS 38.522 Editor’s note: This test case is incomplete. The following aspects are either missing or not yet determined: - Test applicability is incomplete in TS 38.522. - Test Tolerance is FFS | 1 | 80% (+80%) | 80% (+80%) |  |  | 80%
131 | Y | 38.533 | 6.7.9.2 | NR SA FR1 SSB based CMR and dedicated IMR L1-SINR absolute measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-218325 | TS 38.133 cl.A.6.7.9.2 TS 38.903 TS 38.522 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - MU & TT needs further study - Test Procedure is incomplete - Test applicability is incomplete in TS 38.522 | 1 | 80% (+80%) | 80% (+80%) |  |  | 80%
132 | Y | 38.533 | 6.7.9.3 | NR SA FR1 CSI-RS based CMR and dedicated IMR L1-SINR measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) | R5-218326 | TS 38.133 cl.A.6.7.9.3 TS 38.903 TS 38.522 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - MU & TT needs further study - Test Procedure is incomplete - Message content is incomplete - Test applicability is not added in TS 38.522 yet | 1 | 80% (+80%) | 80% (+80%) |  |  | 80%
SA tests in FR2 (Clause 7)
133 |  | 38.533 | 7.5 | Signaling characteristics | Sub-title |  |  |  |  | 0
134 | Y | 38.533 | 7.5.5.6 | NR SA FR2 Scell CSI-RS-based beam failure detection and link recovery in non-DRX | BFD and LR procedure |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.7.5.5.6 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  |  | 0%
135 | Y | 38.533 | 7.5.5.7 | NR SA FR2 Scell CSI-RS-based beam failure detection and link recovery in DRX | BFD and LR procedure |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.7.5.5.7 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  |  | 0%
136 |  | 38.533 | 7.6 | Measurement procedures | Sub-title |  |  |  |  | 0
137 |  | 38.533 | 7.6.6 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
138 |  | 38.533 | 7.6.6.0 | Minimum conformance requirements |  |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.9.8.4.1, 9.8.4.2, 9.8.4.3 | 0.1 | 0% | 0% |  |  |  | 0%
139 | Y | 38.533 | 7.6.6.1 | NR SA FR2 CSI-RS based CMR and no dedicated IMR L1-SINR measurement in non-DRX | L1-SINR measurement procedure | Huawei | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.7.6.6.1 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  |  | 0%
140 | Y | 38.533 | 7.6.6.2 | NR SA FR2 SSB based CMR and dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.7.6.6.2 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  |  | 0%
141 | Y | 38.533 | 7.6.6.3 | NR SA FR2 CSI-RS based CMR and dedicated IMR L1-SINR measurement in DRX | L1-SINR measurement procedure |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.7.6.6.3 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  |  | 0%
142 |  | 38.533 | 7.7 | Measurement Performance requirements | Sub-title |  |  |  |  | 0
143 |  | 38.533 | 7.7.6 | L1-SINR measurement for beam reporting | New Sub-title |  | RAN5#93 (Nov-21) |  | R4-2100938 | 0
144 |  | 38.533 | 7.7.6.0 | Minimum conformance requirements |  |  | RAN5#93 (Nov-21) |  | TS 38.133 cl.9.5.3, 9.8.4.2, 9.8.3, 10.1.Y.2, 10.1.x.x, 10.1.Y2.3 | 0.1 | 0% | 0% |  |  |  | 0%
145 | Y | 38.533 | 7.7.6.1 | NR SA FR2 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.7.7.6.1 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  |  | 0%
146 | Y | 38.533 | 7.7.6.2 | NR SA FR2 SSB based CMR and dedicated IMR L1-SINR measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.7.7.6.2 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  |  | 0%
147 | Y | 38.533 | 7.7.6.3 | NR SA FR2 CSI-RS based CMR and dedicated IMR L1-SINR measurement accuracy | L1-SINR measurement performance | Sporton | RAN5#93 (Nov-21) |  | TS 38.133 cl.A.7.7.6.3 TS 38.903 TS 38.522 | 1 | 0% | 0% |  |  |  | 0%
Annex
148 |  | 38.533 | Annex A | RRM test configurations | RRM test configurations Adding CSI-RS, CSI-IM configurations |  | TBD | R5-217213 R5-218319 | R4-2100938 | 0.1 | 50% (+50%) | 50% (+50%) | 50% (+50%) |  | 100% | 0% | 100% | 0%
149 |  | 38.533 | Annex B | Conditions for RRM requirements applicability for operating bands | Define propagation conditions |  | TBD |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
150 |  | 38.533 | Annex C | Downlink physical channels and propagation conditions | Define downlink physical channels |  | TBD |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
151 |  | 38.533 | Annex D | Deviations from standard test configuration | Define deviations from standard test configuration |  | TBD |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
152 |  | 38.533 | Annex E | Cell configuration mapping | Define cell configuration mapping |  | TBD | R5-218327 |  | 0.1 | 25% (+25%) | 0% | 50% (+50%) |  | 0% | 0% | 100% | 0%
153 |  | 38.533 | Annex F | Measurement uncertainties and test tolerances | Define measurement uncertainties and test tolerances |  | TBD |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
154 |  | 38.533 | Annex H | Default message contents for RRM |  |  | TBD | R5-217214 |  | 0.1 | 40% (+40%) | 40% (+40%) | 40% (+40%) |  | 80% | 0% | 80% | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
155 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | TT analysis for RRM Test cases |  | TBD |  |  | 0.3 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
156 |  | 38.903 | Annex B | Acceptable uncertainty of test system for test cases defined in TS 38.521-2 for radiative testing | TT analysis for FR2 RF Test cases |  | TBD |  |  | 0.5 | 0% | 0% |  |  |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
157 |  | 38.905 | 4.1 | Test point analysis for FR1 test cases in TS 38.521-1 | TT analysis for FR1 RF Test cases | Huawei, Ericsson | RAN5#93 (Nov-21) | R5-206857, R5-206858, R5-206769, R5-211809, R5-211810, R5-211811, R5-210791, R5-211018, R5-211134 R5-213053 R5-214721 R5-216142 |  | 1 | 60% | 60% |  |  | 60%
158 |  | 38.905 | 4.2 | Test point analysis for FR2 test cases in TS 38.521-2 | TT analysis for FR2 RF Test cases |  | RAN5#93 (Nov-21) |  |  | 0.3 | 0% | 0% |  |  |  | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Layer 2
159 | Y | 38.523-1 | 7.1.1.3.10 | Correct Handling of HARQ process / Multiple CORESETPoolIndex | **** TP1: [TS 38.214:6.1] WITH: UE in RRC_CONNECTED state and is configured with PDCCH-Config that contains two different values of CORESETPoolIndex in ControlResourceSet WHEN: UE receives PDCCHs that schedule two non-overlapping in time domain PUSCHs are associated to different ControlResourceSets having different values of CORESETPoolIndex THEN: UE sends PUSCHs following the scheduling information of PDCCHs | Motorola Mobility | RAN5#91-e (May-21) | R5-206415, R5-210880 | 38.523-2: R5-206416 FFS how to ensure performance of overlapping PDSCH: 1. how to deal with self-interference when 2 PDSCH are transmitted on same channel 2. DMRS needs different CDM group 3. DCI needs different TCI state and scrambling ID | 1 | 65% | 65% | 65% |  | 60% | 70% | 60% | 70%
RRC
160 |  | 38.523-1 | FFS | eMIMO / Measurement configuration control and reporting / RANK 3~4 in enhanced type II codebook | **** TP1: [TS 38.214:6.1] WITH: UE in RRC_CONNECTED state and is configured with typeII-RI-Restriction-r16 of value '1000' WHEN: The PMI reporting is triggered by DCI THEN: UE reports PMI of RANK 4 with enhanced type II codebook | Motorola Mobility | RAN5#91-e (May-21) |  | 38.523-2: 38.508-2: | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
161 |  | 38.523-2 | 4 | Recommended Test Case Applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD | R5-206416 |  | 0.2 | 50% | 50% | 50% |  | 50% | 50% | 50% | 50%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.