## Cover sheet
3GPP TSG-RAN WG5 Meeting #93-e | [10 empty] | R5-217406
Electronic Meeting, 8th - 19th Nov 2021
Agenda Item: | 7.4.2
Source: | Huawei, CMCC
Title: | WP for Physical Layer Enhancements for NR Ultra-Reliable and Low Latency Communication (URLLC)
Work item code: | NR_L1enh_URLLC-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of the UE Conformance Test Aspects for Enhancements on MIMO for NR work item is to define the UE conformance requirements corresponding to WID on enhancement on MIMO for NR, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-16. At the RAN#88 meeting in June 2020 the Rel-16 RAN5 work item for UE Conformance Test Aspects for Enhancements on MIMO for NR was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 63% (+18%) | 3 | 27
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 62.8% (+18.3%) | 3 | 27
FR1 |  | 70.8% (+23.2%) | 3 | 25
FR2 |  | 41.2% (+5%) | 3 | 7
NSA Option 3 (EN-DC) |  | 62.8% (+18.1%) | 3 | 27
FR1 |  | 70.8% (+22.9%) | 3 | 25
FR2 |  | 41.2% (+5%) | 3 | 7
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 61.4% (+36.4%) |  |  | 66.7% (+41.7%) |  |  | 50% (+25%) |  |  |  | 66.7% (+41.7%) |  |  | 50% (+25%)
Common ICS | 38.508-2 | 30% (+0%) |  |  | 30% |  |  | 30% |  |  |  | 30% |  |  | 30%
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4 | 51.2% (+20.9%) | 0 | 22 | 72.3% (+28.9%) | 0 | 20 | 5.3% (+3.3%) | 0 | 2 |  | 72.3% (+28.5%) | 0 | 20 | 5.3% (+3.3%) | 0 | 2
RRM test cases | 38.533
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 47.9% (+20.7%) |  |  | 70% (+30%) |  |  | 0% |  |  |  | 70% (+30%) |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 60% (+0%) | 3 | 5 | 60% | 3 | 5 | 60% | 3 | 5 |  | 60% | 3 | 5 | 60% | 3 | 5
Applicability Protocol test cases | 38.523-2 | 60% (+0%) |  |  | 60% |  |  | 60% |  |  |  | 60% |  |  | 60%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-202566 | New WID: UE Conformance Test Aspects - Physical Layer Enhancements for NR Ultra-Reliable and Low Latency Communication (URLLC); Huawei, CMCC
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Physical Layer Enhancements for NR Ultra-Reliable and Low Latency Communication (URLLC) | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_L1enh_URLLC-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Physical Layer Enhancements for NR Ultra-Reliable and Low Latency Communication (URLLC) comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [13 empty] | vs Area
WP Resp: |  | Chunying Gu, Huawei |  |  | guchunying@huawei.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 | FR2
[15 empty] | 70.8% (+23.2%) | 41.2% (+5%) | 70.8% (+22.9%) | 41.2% (+5%)
[15 empty] | 42 | 22 | 42 (+2) | 22
[15 empty] | 30.5 (+1) | 11.4 | 30.5 (+1.2) | 11.4
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS - RAN and CN
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4.3 | Reference test conditions | Adding necessary test conditions for URLLC features | Huawei | RAN5#93 (Nov-2021) | R5-217379 |  | 1 | 50% (+50%) | 50% (+50%) | 50% (+50%) |  | 50% | 50% | 50% | 50%
2 |  | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | New message and IE definition for URLLC features | Huawei | RAN5#93 (Nov-2021) | R5-212946 |  | 1 | 50% | 50% | 50% |  | 50% | 50% | 50% | 50%
3 |  | 38.508-1 | 5 | Test environments for RF test | Necessary changes to RF test environments | Huawei | RAN5#93 (Nov-2021) | R5-218414 |  | 1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% |  | 100%
TS 38.508-2: Common ICS
4 |  | 38.508-2 | A.4 | ICS proforma tables | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | Huawei, Motorola | RAN5#93 (Nov-2021) | R5-212947 R5-213191 R5-215951 R5-214934 |  | 0.2 | 30% | 30% | 30% |  | 30% | 30% | 30% | 30%
NR RF/RRM
TS 38.521-4: Demod/QSI reporting test cases
General
5 |  | 38.521-4 | 2 | References | Define References made in TS | Bureau Veritas | RAN5#93 (Nov-2021) |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
6 |  | 38.521-4 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively | Bureau Veritas | RAN5#93 (Nov-2021) |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
7 |  | 38.521-4 | 4 | General | define categories of test requirements | Bureau Veritas | RAN5#93 (Nov-2021) |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
8 |  | 38.521-4 | Annex A | measurement channels | define mesurement channels | Bureau Veritas | RAN5#93 (Nov-2021) | R5-214016 R5-217378 |  | 0.1 | 75% (+25%) | 75% (+25%) | 75% (+25%) |  | 100% | 50% | 100% | 50%
9 |  | 38.521-4 | Annex B | Propagation conditions | Define propagation conditions | Bureau Veritas | RAN5#93 (Nov-2021) |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
10 |  | 38.521-4 | Annex C | Downlink physical channels | Define downlink physical channels | Bureau Veritas | RAN5#93 (Nov-2021) |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
50 |  | 38.521-4 | Annex F | Downlink physical channels | Measurement uncertainties and test tolerances |  | RAN5#93 (Nov-2021) | R5-214103 R5-217375 |  | 0.1 | 40% (+30%) | 40% (+30%) | 40% (+30%) |  | 70% | 10% | 70% | 10%
11 |  | 38.521-4 | Annex G | Statistical Testing | Define statistical testing considering Ultra-reliable |  | RAN5#93 (Nov-2021) | R5-218360 | RAN4 LS R5-205038 and R5-211286 | 0.1 | 45% (+45%) | 45% (+45%) | 45% (+45%) |  | 90% | 0% | 90% | 0%
Demodulation performance requirements (Conducted requirements) (Clause 5)
12 |  | 38.521-4 | 5.1.1.3 | Applicability of requirements for optional UE features | define applicability of URLLC test cases | Bureau Veritas | RAN5#93 (Nov-2021) | R5-217377 |  | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% |  | 100%
13 |  | 38.521-4 | 5.1.1.4 | Applicability of requirements for mandatory UE features with capability signalling | define applicability of URLLC test cases | Bureau Veritas | RAN5#93 (Nov-2021) | R5-217377 |  | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% |  | 100%
14 |  | 38.521-4 | 5.2 | PDSCH demodulation requirements | Sub-title |  |  |  |  | 0
15 | Y | 38.521-4 | 5.2.2.1.5 | 2Rx FDD FR1 PDSCH 0.001% BLER performance | PDSCH demodulation requirements for PDSCH with 0.001% BLER | Huawei | RAN5#93 (Nov-2021) | R5-214099 R5-218358 | TS 38.101-4 5.2.2.1.5 38.522:R5-212948, R5-217381 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - MU factor due to finite test time nees further study | 1 | 90% (+30%) | 90% (+30%) | 90% (+30%) |  | 90% |  | 90%
16 | Y | 38.521-4 | 5.2.2.1.6 | 2Rx FDD FR1 PDSCH repetitions over multiple slots performance | PDSCH demodulation requirements for PDSCH with repetitions over multiple slots | Sporton | RAN5#93 (Nov-2021) | R5-215954 R5-218357 | TS 38.101-4 5.2.2.1.6 38.522: R5-215960 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Statistical significance in Annex G is FFS - MU factor due to finite test time needs further study - Test Procedure is incomplete | 1 | 40% | 40% | 40% |  | 40% |  | 40%
17 | Y | 38.521-4 | 5.2.2.1.7 | 2Rx FDD FR1 PDSCH Mapping Type B and UE processing capability 2 performance | PDSCH demodulation requirements for PDSCH with Mapping Type B and UE processing capability 2 | Huawei | RAN5#93 (Nov-2021) | R5-215952 R5-217370 | TS 38.101-4 5.2.2.1.7 38.522: R5-215960, R5-217381 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Minimum requirements are within brackets. | 1 | 90% (+20%) | 90% (+20%) | 90% (+20%) |  | 90% |  | 90%
18 | Y | 38.521-4 | 5.2.2.1.8 | 2Rx FDD FR1 PDSCH pre-emption performance | PDSCH demodulation requirements for PDSCH with pre-emption | Sporton | RAN5#93 (Nov-2021) | R5-215955 R5-218357 | TS 38.101-4 5.2.2.1.8 38.522: R5-215960 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Statistical significance in Annex G is FFS - MU factor due to finite test time needs further study - Test Procedure is incomplete | 1 | 70% | 70% | 70% |  | 70% |  | 70%
19 | Y | 38.521-4 | 5.2.2.2.5 | 2Rx TDD FR1 PDSCH 0.001% BLER performance | PDSCH demodulation requirements for PDSCH with 0.001% BLER | Huawei | RAN5#93 (Nov-2021) | R5-214100 R5-218358 | TS 38.101-4 5.2.2.2.5 38.522:R5-212948, R5-217381 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - MU factor due to finite test time nees further study | 1 | 90% (+30%) | 90% (+30%) | 90% (+30%) |  | 90% |  | 90%
20 | Y | 38.521-4 | 5.2.2.2.6 | 2Rx TDD FR1 PDSCH repetitions over multiple slots performance | PDSCH demodulation requirements for PDSCH with repetitions over multiple slots | Sporton | RAN5#93 (Nov-2021) | R5-215956 R5-218357 | TS 38.101-4 5.2.2.2.6 38.522: R5-215960, R5-217381 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Statistical significance in Annex G is FFS - MU factor due to finite test time needs further study - Test Procedure is incomplete | 1 | 70% | 70% | 70% |  | 70% |  | 70%
21 | Y | 38.521-4 | 5.2.2.2.7 | 2Rx TDD FR1 PDSCH Mapping Type B and UE processing capability 2 performance | PDSCH demodulation requirements for PDSCH with Mapping Type B and UE processing capability 2 | Huawei | RAN5#93 (Nov-2021) | R5-215953 R5-217370 | TS 38.101-4 5.2.2.2.7 38.522: R5-215960, R5-217381 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Minimum requirements are within brackets. | 1 | 90% (+20%) | 90% (+20%) | 90% (+20%) |  | 90% |  | 90%
22 | Y | 38.521-4 | 5.2.2.2.8 | 2Rx TDD FR1 PDSCH pre-emption performance | PDSCH demodulation requirements for PDSCH with pre-emption | Sporton | RAN5#93 (Nov-2021) | R5-215957 R5-218357 | TS 38.101-4 5.2.2.2.8 38.522: R5-215960 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Statistical significance in Annex G is FFS - MU factor due to finite test time needs further study - Test Procedure is incomplete | 1 | 70% | 70% | 70% |  | 70% |  | 70%
23 | Y | 38.521-4 | 5.2.3.1.5 | 4Rx FDD FR1 PDSCH 0.001% BLER performance | PDSCH demodulation requirements for PDSCH with 0.001% BLER | Huawei | RAN5#93 (Nov-2021) | R5-214101 R5-218358 | TS 38.101-4 5.2.3.1.5 38.522:R5-212948, R5-217381 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Statistical significance in Annex G is FFS - MU factor due to finite test time nees further study | 1 | 90% (+30%) | 90% (+30%) | 90% (+30%) |  | 90% |  | 90%
24 | Y | 38.521-4 | 5.2.3.1.6 | 4Rx FDD FR1 PDSCH repetitions over multiple slots performance | PDSCH demodulation requirements for PDSCH with repetitions over multiple slots | Sporton | RAN5#93 (Nov-2021) | R5-215958 | TS 38.101-4 5.2.3.1.6 38.522: R5-215960, R5-217381 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Statistical significance in Annex G is FFS - MU factor due to finite test time needs further study - Test Procedure is incomplete | 1 | 70% | 70% | 70% |  | 70% |  | 70%
25 | Y | 38.521-4 | 5.2.3.1.7 | 4Rx FDD FR1 PDSCH Mapping Type B and UE processing capability 2 performance | PDSCH demodulation requirements for PDSCH with Mapping Type B and UE processing capability 2 | Huawei | RAN5#93 (Nov-2021) | R5-216078 R5-217370 | TS 38.101-4 5.2.3.1.7 38.522: R5-215960, R5-217381 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Minimum requirements are within brackets. | 1 | 90% (+20%) | 90% (+20%) | 90% (+20%) |  | 90% |  | 90%
26 | Y | 38.521-4 | 5.2.3.1.8 | 4Rx FDD FR1 PDSCH pre-emption performance | PDSCH demodulation requirements for PDSCH with pre-emption |  | RAN5#93 (Nov-2021) | R5-21xxxx | TS 38.101-4 5.2.3.1.8 38.522: | 1 | 0% | 0% | 0% |  | 0% |  | 0%
27 | Y | 38.521-4 | 5.2.3.2.5 | 4Rx TDD FR1 PDSCH 0.001% BLER performance | PDSCH demodulation requirements for PDSCH with 0.001% BLER | Huawei | RAN5#93 (Nov-2021) | R5-214102 R5-218358 | TS 38.101-4 5.2.3.2.5 38.522:R5-212948, R5-217381 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Statistical significance in Annex G is FFS - MU factor due to finite test time nees further study | 1 | 90% (+30%) | 90% (+30%) | 90% (+30%) |  | 90% |  | 90%
28 | Y | 38.521-4 | 5.2.3.2.6 | 4Rx TDD FR1 PDSCH repetitions over multiple slots performance | PDSCH demodulation requirements for PDSCH with repetitions over multiple slots | Sporton | RAN5#93 (Nov-2021) | R5-215959 | TS 38.101-4 5.2.3.2.6 38.522: R5-215960, R5-217381 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Statistical significance in Annex G is FFS - MU factor due to finite test time needs further study - Test Procedure is incomplete | 1 | 70% | 70% | 70% |  | 70% |  | 70%
29 | Y | 38.521-4 | 5.2.3.2.7 | 4Rx TDD FR1 PDSCH Mapping Type B and UE processing capability 2 performance | PDSCH demodulation requirements for PDSCH with Mapping Type B and UE processing capability 2 | Huawei | RAN5#93 (Nov-2021) | R5-215103 R5-217370 | TS 38.101-4 5.2.3.2.7 38.522: R5-215960, R5-217381 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Minimum requirements are within brackets. | 1 | 90% (+20%) | 90% (+20%) | 90% (+20%) |  | 90% |  | 90%
30 | Y | 38.521-4 | 5.2.3.2.8 | 4Rx TDD FR1 PDSCH pre-emption performance | PDSCH demodulation requirements for PDSCH with pre-emption |  | RAN5#93 (Nov-2021) | R5-21xxxx | TS 38.101-4 5.2.3.2.8 38.522: | 1 | 0% | 0% | 0% |  | 0% |  | 0%
CSI reporting requirements (Conducted requirements) (Clause 6)
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
45 |  | 38.521-4 | 6.1.1.3 | Applicability of requirements for optional UE features | define applicability of URLLC test cases | Bureau Veritas | RAN5#93 (Nov-2021) | R5-217377 | TS 38.101-4 6.1.1.3 | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% |  | 100%
46 | Y | 38.521-4 | 6.2.2.1.1.2 | 2Rx FDD FR1 periodic CQI reporting with Table 3 under AWGN conditions for both SA and NSA | PDSCH with 0.001% BLER with reported CQI | Sporton | RAN5#93 (Nov-2021) | R5-218359 | TS 38.101-4 6.2.2.1.1.2 38.522: R5-217381 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Whether to adopt minimum sample for pass/fail verdict needs further study. | 1 | 90% (+90%) | 90% (+90%) | 90% (+90%) |  | 90% |  | 90%
47 | Y | 38.521-4 | 6.2.2.2.1.2 | 2Rx TDD FR1 periodic CQI reporting with Table 3 under AWGN conditions for both SA and NSA | PDSCH with 0.001% BLER with reported CQI | Huawei | RAN5#93 (Nov-2021) | R5-218467 | TS 38.101-4 6.2.2.2.1.2 38.522: R5-217381 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Whether to adopt minimum sample for pass/fail verdict needs further study. | 1 | 90% (+90%) | 90% (+90%) | 90% (+90%) |  | 90% |  | 90%
48 | Y | 38.521-4 | 6.2.3.1.1.2 | 4Rx FDD FR1 periodic CQI reporting with Table 3 under AWGN conditions for both SA and NSA | PDSCH with 0.001% BLER with reported CQI | Huawei | RAN5#93 (Nov-2021) | R5-218468 | TS 38.101-4 6.2.3.1.1.2 38.522: R5-217381 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Whether to adopt minimum sample for pass/fail verdict needs further study. | 1 | 90% (+90%) | 90% (+90%) | 90% (+90%) |  | 90% |  | 90%
49 | Y | 38.521-4 | 6.2.3.2.1.2 | 4Rx TDD FR1 periodic CQI reporting with Table 3 under AWGN conditions for both SA and NSA | PDSCH with 0.001% BLER with reported CQI | Huawei | RAN5#93 (Nov-2021) | R5-218469 | TS 38.101-4 6.2.3.2.1.2 38.522: R5-217381 Editor's note: This clause is incomplete. The following aspects are either missing or not yet determined: - Whether to adopt minimum sample for pass/fail verdict needs further study. | 1 | 90% (+90%) | 90% (+90%) | 90% (+90%) |  | 90% |  | 90%
Demodulation performance requirements (Radiated requirements) (Clause 7)
31 |  | 38.521-4 | 7.1 | Applicability of requirements | Sub-title |  | RAN5#93 (Nov-2021) |  |  | 0
32 |  | 38.521-4 | 7.1.1.3 | Applicability of requirements for optional UE features |  | Bureau Veritas | RAN5#93 (Nov-2021) | R5-217377 | TS 38.101-4 7.1.1.3 | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  |  | 100% |  | 100%
33 |  | 38.521-4 | 7.1.1.4 | Applicability of requirements for mandatory UE features with capability signalling |  | Bureau Veritas | RAN5#93 (Nov-2021) | R5-21xxxx | TS 38.101-4 7.1.1.4 | 0.1 | 0% | 0% | 0% |  |  | 0% |  | 0%
34 |  | 38.521-4 | 7.2 | PDSCH demodulation requirements | Sub-title |  |  |  |  | 0
35 | Y | 38.521-4 | 7.2.2.2.2 | 2Rx TDD FR2 PDSCH repetitions over multiple slots performance | PDSCH demodulation requirements for PDSCH with repetitions over multiple slots |  | RAN5#93 (Nov-2021) | R5-21xxxx | TS 38.101-4 7.2.2.2.2 38.522: | 1 | 0% | 0% | 0% |  |  | 0% |  | 0%
36 | Y | 38.521-4 | 7.2.2.2.3 | 2Rx TDD FR2 PDSCH Mapping Type B performance | PDSCH demodulation requirements for PDSCH with Mapping Type B |  | RAN5#93 (Nov-2021) | R5-21xxxx | TS 38.101-4 7.2.2.2.3 38.522: | 1 | 0% | 0% | 0% |  |  | 0% |  | 0%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
37 |  | 38.522 | 4.1.4 | Performance conformance test cases | Adding applicability for test cases in 38.521-4 | Bureau Veritas | RAN5#93 (Nov-2021) | R5-212948 R5-215960 R5-217381 |  | 1 | 35% (+15%) | 35% (+15%) | 35% (+15%) |  | 70% | 0% | 70% | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Layer 2
38 | Y | 38.523-1 | 7.1.1.2.5 | Correct HARQ process handling / DL grant prioritization | **** TP1: [TS 38.213:9.1] with { UE in RRC_CONNECTED state and is configured with two PUCCH-config each correpsonds to a PHY priority,} ensure that { when { UE receives two MAC PDU with DL grant indicating different priorities } then { UE transmit the HARQ feedback using correct PUCCH resource } } | Motorola Mobility | RAN5#93 (Nov-2021) | R5-21xxxx | Depending on capability dci-DL-PriorityIndicator-r16 38.523-2: | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
39 | Y | 38.523-1 | 7.1.1.3.12 | Correct Handling of UL HARQ process / PUSCH Repetition Type B | **** TP1: [TS 38.214:6.1.2.3] with { UE in RRC_CONNECTED state and is configured with PUSCH repetition type B } ensure that { when { UE receives an UL Grant with toggled NDI and has data available for transmission } then { UE transmits a new MAC PDU and repeats the MAC PDU in proper actural transmission times and selects the redundancy version correctly } } | Motorola Mobility | RAN5#93 (Nov-2021) | R5-213637 R5-216319 | Depending on capability pusch-RepetitionTypeB-r16 38.523-2: R5-213672 | 1 | 100% | 100% | 100% |  | 100% | 100% | 100% | 100%
40 | Y | 38.523-1 | 7.1.1.3.13 | Logical channel prioritization handling with Mapping restrictions / physical layer priority | **** TP1: [TS 38.213:9] with {UE in RRC_CONNECTED state with allowedPHY-PriorityIndex configured } ensure that { when { UE is scheduled by DCI including priority indicator } then { UE serves the logical channels according to their priority and configured PHY priority } } | Motorola Mobility | RAN5#93 (Nov-2021) | R5-21xxxx | Depending on capability dci-UL-PriorityIndicator-r16, ul-IntraUE-Mux-r16 and lch-ToGrantPriorityRestriction-r16 38.523-2: | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
41 | Y | 38.523-1 | 7.1.1.4.1.5 | DL-SCH transport block size selection / DCI format 1_2 | **** TP1: [TS 38.212:7.3.1.1.3, 7.3.1.2.3, TS 38.214 5.1.2.1, 6.1.2.1] with { UE in RRC_CONNECTED state } ensure that { when { UE on PDCCH receives DCI format 1_2 indicating a resource block assignment correspondent to physical resource blocks , Time domain resource assignment and a modulation and coding } then { UE decodes the received transport block of size correspondent as per Modulation Coding scheme, time domain resource allocation and PRB's and forwards it to higher layers } } | Motorola Mobility | RAN5#93 (Nov-2021) | R5-216318 | Depending on capability pusch-RepetitionTypeB-r16 38.523-2: R5-214931 | 1 | 100% | 100% | 100% |  | 100% | 100% | 100% | 100%
42 | Y | 38.523-1 | 7.1.1.4.2.6 | UL-SCH Transport Block Size selection / DCI format 0_2 | **** TP1: [TS 38.212:7.3.1.1.3, 7.3.1.2.3, TS 38.214 5.1.2.1, 6.1.2.1] with { UE in RRC_CONNECTED state } ensure that { when { UE has pending data for transmission and receives on PDCCH DCI format 0_2 indicating a resource block assignment correspondent to physical resource blocks , Time domain resource assignment and modulation and coding } then { UE transmits MAC PDU on PUSCH as per Modulation Coding scheme, time domain resource allocation and PRB's } } | Motorola Mobility | RAN5#93 (Nov-2021) | R5-216317 | Depending on capability dci-UL-PriorityIndicator-r16 and lch-ToGrantPriorityRestriction-r16 38.523-2: R5-214931 | 1 | 100% | 100% | 100% |  | 100% | 100% | 100% | 100%
TS 38.523-2: Applicability for Protocol test cases
43 |  | 38.523-2 | 4 | Recommended Test Case Applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | RAN5#93 (Nov-2021) | R5-213672 R5-214931 |  | 0.2 | 60% | 60% | 60% |  | 60% | 60% | 60% | 60%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
44 |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.