## Cover sheet
3GPP TSG-RAN WG5 Meeting #93-e | [10 empty] | R5-217650
Electronic Meeting, 8th - 19th November 2021
Agenda Item: | 7.4.2
Source: | Ericsson
Title: | Work plan: UE Conformance Test Aspects – Rel14 Enhanced Full Dimension MIMO for LTE
Work item code: | LTE_eFDMIMO-UEConTest
Release: | Rel-14
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At the RAN#86 meeting in December 2019 the Rel-15 RAN5 work item for UE Conformance Test Aspects – Even further enhanced MTC for LTE was approved At the RAN#83 meeting in March 2019 the Rel-14 RAN5 work item for UE Conformance Test Aspects - Elevation Beamforming/Full-Dimension MIMO for LTE was approved in [1]. The purpose of present document is to provide a work plan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items for eFD-MIMO. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 28% | 2 | 12.6
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE |  | 27.8% | 2 | 12.6
FDD |  | 27.8% | 1 | 6.3
TDD |  | 27.8% | 1 | 6.3
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD |  |  | TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 0% |  |  | 0% |  |  | 0%
LTE RF/RRM
RF common parts | 36.521-1 | 0% |  |  | 0% |  |  | 0%
RF Demod test cases | 36.521-1 Demod | 18.8% | 2 | 12.6 | 18.8% | 1 | 6.3 | 18.8% | 1 | 6.3
Applicability RF, Demod/QSI and RRM test cases | 36.521-2 | 5% |  |  | 5% |  |  | 5%
Test Tolerances analysis receiver test cases | 36.904
5 References
[1] RP-190509 | New WID on UE Conformance Test Aspects - Enhancements on Full-Dimension (FD) MIMO for LTE; Supporting companies: Ericsson, SRTC, T-Mobile US, Telecom Italia, Qualcomm
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Rel14 Enhanced Full Dimension MIMO for LTE | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_eFDMIMO-UEConTest
WP Scope: |  | RF performance test cases for Rel-14 Enhanced Full Dimension MIMO for LTE | [12 empty] | vs Area
WP Resp: |  | Mikael Zirén, Ericsson |  |  | mikael.ziren@ericsson.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD | TDD
[14 empty] | 27.8% | 27.8%
[14 empty] | 14 | 14
[14 empty] | 9.6 | 9.6
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
TBD |  | 36.508 | Annex A | Connection diagrams | Required connection diagrams are handled under each test case. This task represent the overall competion of connection diagrams. |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
LTE RF/RRM
TS 36.521-1: RF test cases - Common parts (general clauses, Annexes)
TBD |  | 36.521-1 | Annex A | RMC | Define Reference Measurement Channels |  | TBD |  |  | 0.3 | 0% | 0% |  | 0% | 0%
TBD |  | 36.521-1 | Annex B | Propagation Conditions | Add new Beamforming models |  | TBD |  |  | 0.3 | 0% | 0% |  | 0% | 0%
|  | 36.904 | Annex F | Test Tolerances | Required Test Tolerance analysis for Annex F are handled under each impacted test case. | Each company introducing a new TC
TBD |  | 36.521-1 | Annex G | Statistical test time | Required Test Tolerance analysis for Annex F are handled under each impacted test case. | Each company introducing a new TC
TS 36.521-1: Demod/QSI reporting test cases
Demodulation of PDSCH (User-Specific Reference Symbols)
TBD |  | 36.521-1 Demod | 8.1.2 | Applicability of requirements |  |  | TBD |  |  | 0.3 | 0% | 0% |  | 0% | 0%
TBD | Y | 36.521-1 Demod | 8.3.1.1.10 | FDD PDSCH Single-layer Spatial Multiplexing on antenna ports 7 or 8 without a simultaneous transmission for eFD-MIMO | Add new test case including required TT in Annex F. If needed add connection diagram in 36.508 Annex A. | Ericsson | RAN5#96 (Aug-22) | R5-214329 |  | 1 | 100% | 100% |  | 100%
TBD | Y | 36.521-1 Demod | 8.3.1.4 | FDD Performance Requirements for semiOpenLoop transmission | Add new test case including required TT in Annex F. If needed add connection diagram in 36.508 Annex A. | Ericsson | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 36.521-1 Demod | 8.3.2.1.11 | TDD PDSCH Single-layer Spatial Multiplexing on antenna ports 7 or 8 without a simultaneous transmission for eFD-MIMO | Add new test case including required TT in Annex F. If needed add connection diagram in 36.508 Annex A. | Ericsson | RAN5#96 (Aug-22) | R5-214330 |  | 1 | 100% | 100% |  |  | 100%
TBD | Y | 36.521-1 Demod | 8.3.2.5 | TDD Performance Requirements for semiOpenLoop transmission | Add new test case including required TT in Annex F. If needed add connection diagram in 36.508 Annex A. | Ericsson | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
Reporting of Precoding Matrix Indicator (PMI)
TBD | Y | 36.521-1 Demod | 9.4.1.3.1_1 | FDD PMI Reporting with Class B codebook – PUSCH 3-1 (Single PMI) for eFD-MIMO | Add new test case including required TT in Annex F. If needed add connection diagram in 36.508 Annex A. |  | TBD |  | core requirement 9.4.1.3.1 Similar as TC 9.4.1.3.1_D but with different NZP CSI-RS config | 0.3 | 0% | 0% |  | 0%
TBD | Y | 36.521-1 Demod | 9.4.1.3.2_1 | TDD PMI Reporting with Class B codebook – PUSCH 3-1 (Single PMI) for eFD-MIMO | Add new test case including required TT in Annex F. If needed add connection diagram in 36.508 Annex A. |  | TBD |  | core requirement 9.4.1.3.2 Similar as TC 9.4.1.3.2_D but with different NZP CSI-RS config | 0.3 | 0% | 0% |  |  | 0%
TBD | Y | 36.521-1 Demod | 9.4.1.3.5 | FDD PMI Reporting with 24Tx Class A codebook – PUSCH 3-1 (Single PMI) for eFD-MIMO | Add new test case including required TT in Annex F. If needed add connection diagram in 36.508 Annex A. |  | TBD |  | core requirement 9.4.1.3.5 Similar as TC 9.4.1.3.3 but with more ports | 1 | 0% | 0% |  | 0%
TBD | Y | 36.521-1 Demod | 9.4.1.3.6 | TDD PMI Reporting with 24Tx Class A codebook – PUSCH 3-1 (Single PMI) for eFD-MIMO | Add new test case including required TT in Annex F. If needed add connection diagram in 36.508 Annex A. |  | TBD |  | core requirement 9.4.1.3.6 Similar as TC 9.4.1.3.4 but with more ports | 1 | 0% | 0% |  |  | 0%
TBD |  | 36.521-1 Demod | 9.4.1.4.3 | FDD PMI Reporting with Class B alternative codebook – PUCCH 1-1 for FD-MIMO | Add new sub tests Add TT analysis Add TT in Annex F | Ericsson | TBD |  | The new subtest 1a for eFD-MIMO is already present in 36.521-1 | 0.3 | 100% | 100% |  | 100%
TBD |  | 36.521-1 Demod | 9.4.1.4.4 | TDD PMI Reporting with Class B alternative codebook – PUCCH 1-1 for FD-MIMO | Add new sub tests Add TT analysis Add TT in Annex F | Ericsson | TBD |  | The new subtest 1a for eFD-MIMO is already present in 36.521-1 | 0.3 | 100% | 100% |  |  | 100%
TBD | Y | 36.521-1 Demod | 9.4.2.3.7 | FDD PMI Reporting with Class A 32Tx codebook - PUSCH 1-2 (Multiple PMI) for eFD-MIMO | Add new test case including required TT in Annex F. If needed add connection diagram in 36.508 Annex A. |  | TBD |  | core requirement 9.4.2.3.7 Similar as TC 9.4.2.3.5 but with more ports | 1 | 0% | 0% |  | 0%
TBD | Y | 36.521-1 Demod | 9.4.2.3.8 | TDD PMI Reporting with Class A 32Tx codebook - PUSCH 1-2 (Multiple PMI) for eFD-MIMO | Add new test case including required TT in Annex F. If needed add connection diagram in 36.508 Annex A. |  | TBD |  | core requirement 9.4.2.3.8 Similar as TC 9.4.2.3.6 but with more ports | 1 | 0% | 0% |  |  | 0%
TBD | Y | 36.521-1 Demod | 9.4.2.3.9 | FDD PMI Reporting with Class A 16Tx advanced codebook - PUSCH 1-2 (Multiple PMI) for eFD-MIMO | Add new test case including required TT in Annex F. If needed add connection diagram in 36.508 Annex A. |  | TBD |  | core requirement 9.4.2.3.9 Similar as TC 9.4.2.3.5 but with different codebook config | 1 | 0% | 0% |  | 0%
TBD | Y | 36.521-1 Demod | 9.4.2.3.10 | TDD PMI Reporting with Class A 16Tx advanced codebook - PUSCH 1-2 (Multiple PMI) for eFD-MIMO | Add new test case including required TT in Annex F. If needed add connection diagram in 36.508 Annex A. |  | TBD |  | core requirement 9.4.2.3.10 9.4.2.3.6 but with different codebook config | 1 | 0% | 0% |  |  | 0%
Reporting of Hybrid Channel state information
TBD | Y | 36.521-1 Demod | 9.11.1.1 | FDD Hybrid CSI-RS Resource Indicator and PMI Reporting – PUSCH 3-1 | Add new test case including required TT in Annex F. If needed add connection diagram in 36.508 Annex A. |  | TBD |  | core requirement 9.11.1.1 | 1 | 0% | 0% |  | 0%
TBD | Y | 36.521-1 Demod | 9.11.1.2 | TDD Hybrid CSI-RS Resource Indicator and PMI Reporting – PUSCH 3-1 | Add new test case including required TT in Annex F. If needed add connection diagram in 36.508 Annex A. |  | TBD |  | core requirement 9.11.1.2 | 1 | 0% | 0% |  |  | 0%
TS 36.521-2: Applicability for RF, Demod/QSI reporting and RRM test cases
TBD |  | 36.521-2 | Table 4.1-1 | Applicability of RF conformance test cases | Add test case applicability statements for the new test cases introduced in 36.521-1. | Ericsson | TBD | R5-214331 |  | 0.1 | 5% | 5% |  | 5% | 5%
TR 36.904: Test Tolerances analysis receiver test cases
TBD |  | 36.904 |  | Test Tolerance analysis for each test case addition | Required Test Tolerance analysis for Annex F are handled under each impacted test case. This task represent the overall completion of all TT analysis. | Each company introducing a new TC | TBD |  | No impact as the new test cases in this WI are all single cell | 1 | 100% | 100% |  | 100% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.