## Cover sheet
RAN5 meeting #94e | [10 empty] | R5-220957
Electronic meeting, 21st February - 4th March 2022
Agenda Item: | 7.4.2
Source: | Qualcomm Incorporated
Title: | WP UE Conformance Test Aspects - Support of eCall over IMS for NR
Work item code: | NR_EIEI-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work plan is to define the UE conformance test aspects corresponding to WID on Rel-16 Support of eCall over IMS for NR.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 48% (+48%) | 8 (+8) | 19 (+19)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 48.4% (+48.4%) | 8 (+8) | 19 (+19)
FR1 |  | 48.4% (+48.4%) | 8 (+8) | 19 (+19)
FR2 |  | 48.4% (+48.4%) | 8 (+8) | 19 (+19)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 96.7% (+96.7%) |  |  | 96.7% (+96.7%) |  |  | 96.7% (+96.7%)
Common ICS | 38.508-2 | 0% |  |  | 0% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 21.4% (+21.4%) | 3 (+3) | 14 (+14) | 21.4% (+21.4%) | 3 (+3) | 14 (+14) | 21.4% (+21.4%) | 3 (+3) | 14 (+14)
Applicability Protocol test cases | 38.523-2 | 30% (+30%) |  |  | 30% (+30%) |  |  | 30% (+30%)
Test suites (TTCN) | 38.523-3
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5 | 90% (+90%) | 5 (+5) | 5 (+5) | 90% (+90%) | 5 (+5) | 5 (+5) | 90% (+90%) | 5 (+5) | 5 (+5)
Applicability and ICS IMS test cases | 34.229-2 | 60% (+60%) |  |  | 60% (+60%) |  |  | 60% (+60%)
IMS Test suite (TTCN) | 34.229-3
5 References
[1] RP-210704 | Support of eCall over IMS for NR
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Support of eCall over IMS for NR | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_EIEI-UEConTest
WP Scope: |  | The objective of this work plan is to define the UE conformance test aspects corresponding to WID on Rel-16 Support of eCall over IMS for NR. | [12 empty] | vs Area
WP Resp: |  | Bharadwaj Kumar Cheruvu |  |  | bcheruvu@qti.qualcomm.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 48.4% (+48.4%) | 48.4% (+48.4%)
[14 empty] | 34 (+34) | 34 (+34)
[14 empty] | 21.9 (+21.9) | 21.9 (+21.9)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
3 |  | 38.508-1 | 4 | Addition of generic procedures for ecall over IMS for NR | 1. Procedure for eCall over IMS establishment in 5GS – Normal Service 2. Procedure for eCall over IMS establishment in 5GS eCall only Support | Qualcomm | RAN5#95 (May-22) | R5-216328 R5-217944 |  | 0.5 | 90% (+90%) | 90% (+90%) |  | 90% | 90%
26 |  | 38.508-1 | 4 | ASN.1 update for ecall over IMS for NR | SIB1 updates | Qualcomm | RAN5#92 (Aug-21) | R5-216327 |  | 0.5 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
27 |  | 38.508-1 | 4 | USIM configuration update | USIM configurations | Qualcomm | RAN5#92 (Aug-21) | R5-216329 R5-221070 |  | 0.5 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.508-2: Common ICS
4 |  | 38.508-2 | A.4 | Introduce PICS parameters for eCall over IMS for NR test cases | Add new ICS statements |  | RAN5#95 (May-22) |  | RAT specific PICS are defined for NR EIEI in 34.229-2. For now, this is a placeholder. | 0.1 | 0% | 0% |  | 0% | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
General tests
31 | Y | 38.523-1 | 8.1.4.1.10 | eCall Only mode / Intra NR handover / Success / Inter-frequency | FFS |  | RAN5#95 (May-22) |  | LTE test case 8.2.4.28 | 1 | 0% | 0% |  | 0% | 0%
2 |  | 38.523-1 | 11.5 | eCall over IMS | New sub-clause header |  |  |  |  | 0
5 | Y | 38.523-1 | 11.5.1 | eCall Only mode / T3444 / eCall inactivity procedure / Removal of eCall only restriction after an eCall over IMS / 5GS to EPS | (1) with { UE is switched ON with eCall only enabled USIM } ensure that { when { UE reads ims-EmergencySupport and eCallOverIMS-Support from SIB1 } then { UE enters substate 5GMM-DEREGISTERED.eCALL-INACTIVE and shall not start registration procedure } } (2) with { The UE is in the state 5GMM-DEREGISTERED.eCALL-INACTIVE } ensure that { when { UE is requested to make a manual eCall } then { UE sends REGISTRATION REQUEST message with 5GS registration type set to 'initial registration' } } (3) with { UE receives REGISTRATION ACCEPT message and IMS voice over PS session is supported over 3GPP access } ensure that { when { UE is in 5GMM-REGISTERED.NORMAL-SERVICE state and an initial IMS registration is performed } then { the UE establishes a New emergency PDU session by sending an UL NAS TRANSPORT message with Request type set to "initial emergency request" and a PDU SESSION ESTABLISHMENT REQUEST } } (4) with { UE receives an RRCRelease message and enters RRC_IDLE state } ensure that { when { UE receives a Paging message with MT MMTEL voice call } then {the UE answers the paging request for MT MMTEL voice call } } (5) with { UE receives an RRCRelease message and enters RRC_IDLE state } ensure that { when { UE starts T3444 for 12Hours and the periodic registration update timer T3512 expires } then { the UE initiates the registration procedure for mobility and periodic registration update and indicates "periodic registration updating" in the 5GS registration type IE } } (6) with { UE in state 5GMM-REGISTERED and 5GMM-IDLE on a 5GC NR cell } ensure that { when { UE detects a suitable EPC E-UTRA cell after the serving NGC cell becomes not suitable when eCall Inactivity timer T3444 is running } then { UE performs a Inter-system change from N1 mode to S1 mode by initiating and successfully completing a TAU procedure } } (7) with { UE in state EMM-REGISTERED and EMM-IDLE on an E-UTRA cell } ensure that { when { UE detects a suitable NGC cell after the serving E-UTRA cell becomes not suitable when eCall Inactivity timer T3444 is running } then { UE performs a Inter-system change from S1 mode to N1 mode by initiating and successfully completing a mobility and periodic registration update procedure } } (8) with { UE is in RRC_IDLE state } ensure that { when { eCall Inactivity timer T3444 expires } then { The UE performs Deregistration procedure } } | Qualcomm | RAN5#93 (Nov-21) | R5-217945 | LTE test case 11.3.1 | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
6 | Y | 38.523-1 | 11.5.2 | eCall Only mode / T3445 / eCall inactivity procedure / Removal of eCall only restriction after a call to URI for test service / 5GS to EPS | (1) with { The UE is in the state 5GMM-DEREGISTERED.eCALL-INACTIVE } ensure that { when { UE is requested to make an eCall to URI for test service } then { UE sends REGISTRATION REQUEST message with 5GS registration type set to 'initial registration' } } (2) with { UE receives REGISTRATION ACCEPT message and IMS voice over PS session is supported over 3GPP access } ensure that { when { UE is in 5GMM-REGISTERED.NORMAL-SERVICE state and an initial registration is performed } then { the UE establishes a new PDU session by sending an UL NAS TRANSPORT message with Request type set to "initial request" and a PDU SESSION ESTABLISHMENT REQUEST } } (3) with { UE receives an RRCRelease message and enters RRC_IDLE state } ensure that { when { UE receives a Paging message with MT MMTEL voice call } then {the UE answers the paging request for MT MMTEL voice call } } (4) with { UE receives an RRCRelease message and enters RRC_IDLE state } ensure that { when { UE starts T3445 for 12Hours and the periodic registration update timer T3512 expires } then { the UE initiates the registration procedure for mobility and periodic registration update and indicates "periodic registration updating" in the 5GS registration type IE } } (5) with { UE in state 5GMM-REGISTERED and 5GMM-IDLE on a 5GC NR cell } ensure that { when { UE detects a suitable EPC E-UTRA cell after the serving NGC cell becomes not suitable when eCall Inactivity timer T3445 is running } then { UE performs a Inter-system change from N1 mode to S1 mode by initiating and successfully completing a TAU procedure } } (6) with { UE in state EMM-REGISTERED and EMM-IDLE on an E-UTRA cell } ensure that { when { UE detects a suitable NGC cell after the serving E-UTRA cell becomes not suitable when eCall Inactivity timer T3445 is running } then { UE performs a Inter-system change from S1 mode to N1 mode by initiating and successfully completing a mobility and periodic registration update procedure } } (7) with { UE is in RRC_IDLE state } ensure that { when { eCall Inactivity timer T3445 expires } then { The UE performs Deregistration procedure } } | Qualcomm | RAN5#93 (Nov-21) | R5-217946 | LTE test case 11.3.2 | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
7 | Y | 38.523-1 | 11.5.3 | eCall Only mode / 5GS supports IMS voice over PS session / 5GS does not support emergency service / eCall over EPS / eCall using eCall using CS domain / eCall failure if EPS and CS domain are not available | FFS |  | RAN5#95 (May-22) |  | LTE test case 11.3.4 | 1 | 0% | 0% |  | 0% | 0%
8 | Y | 38.523-1 | 11.5.4 | eCall Only mode / 5GS supports IMS voice over PS session / 5GS supports emergency service / eCall over IMS is supported / RACH failure in NR cell / eCall over EPS | FFS |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
9 | Y | 38.523-1 | 11.5.5 | eCall Only mode / Limited service state / Call to URI for test service should not be attempted / eCall over IMS should be attempted / 5GS | (1) with { UE in eCALL-INACTIVE.LIMITED-SERVICE state } ensure that { when { UE is requested to make an eCall to URI for test service } then { UE does not transmit any RRCSetupRequest message } } (2) with { UE in eCALL-INACTIVE.LIMITED-SERVICE state } ensure that { when { UE is requested to make a manual eCall } then { UE transmits a REGISTRATION REQUEST message with registration type set to “emergency” } } | Qualcomm | RAN5#94 (Feb-22) | R5-221595 | LTE test case 11.3.6 | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
10 | Y | 38.523-1 | 11.5.6 | eCall capable / 5GS supports IMS voice over PS session / 5GS supports emergency service / eCall over IMS is not supported / eCall using the CS domain / emergency call over IMS if eCall using the CS domain is not available / UTRA | FFS |  | RAN5#95 (May-22) |  | LTE test case 11.3.3 | 1 | 0% | 0% |  | 0% | 0%
29 | Y | 38.523-1 | 11.5.7 | eCall Only mode / SRVCC Handover to CS domain / UTRAN / MSD Update / Success / 5GS | FFS |  | RAN5#95 (May-22) |  | LTE test case 11.3.7 | 1 | 0% | 0% |  | 0% | 0%
30 | Y | 38.523-1 | 11.5.8 | eCall Only mode / 5GS supports IMS voice over PS session / 5GS supports emergency service / eCall over IMS is supported / RACH failure in NR cell / eCall using the CS domain | FFS |  | RAN5#95 (May-22) |  | LTE test case 11.3.5 | 1 | 0% | 0% |  | 0% | 0%
32 | Y | 38.523-1 | 11.5.9 | eCall only mode / Manual initiation / Emergency registration / Abnormal case / IM CN sends a 486 (Busy Here) / UE performs eCall in CS domain / UTRAN or GERAN / 5GS | 24.229, cl. 5.1.6.11.1, 5.1.6.11.2 | Qualcomm | RAN5#95 (May-22) |  | LTE test case 21.13 | 1 | 0% | 0% |  | 0% | 0%
33 | Y | 38.523-1 | 11.5.10 | eCall only mode / Automatic initiation / Emergency registration / Abnormal case / IM CN sends a 600 (Busy Everywhere) / UE performs eCall in CS domain / UTRAN or GERAN / 5GS | 24.229, cl. 5.1.6.11.1, 5.1.6.11.2 | Qualcomm | RAN5#95 (May-22) |  | LTE test case 21.16 | 1 | 0% | 0% |  | 0% | 0%
34 | Y | 38.523-1 | 11.5.11 | eCall only mode / Automatic initiation / Emergency registration / Abnormal case / IM CN sends a 603 (Decline) / UE performs eCall in CS domain / UTRAN or GERAN / 5GS | 24.229, cl. 5.1.6.11.1, 5.1.6.11.2 | Qualcomm | RAN5#95 (May-22) |  | LTE test case 21.18 | 1 | 0% | 0% |  | 0% | 0%
35 | Y | 38.523-1 | 11.5.12 | eCall Only mode / 5GS supports IMS voice over PS session / 5GS supports emergency service / eCall over IMS is not supported / eCall over EPS | FFS |  |  |  |  | 1 | 0% | 0% |  | 0% | 0%
36 | Y | 38.523-1 | 11.5.13 | eCall over IMS / Manual initiation / MSD transfer Failure / UE performs eCall in CS domain after Timer expiry / UTRAN or GERAN / 5GS | 24.229, 5.1.6.11.3 |  | RAN5#95 (May-22) |  | LTE test case 21.3 | 1 | 0% | 0% |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
11 |  | 38.523-2 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.523-1 | Add test case applicability statements for the new test cases introduced in 38.523-1 | Qualcomm | RAN5#95 (May-22) | R5-217947 R5-221040 | Addition of applicability conditions for 38.523-1 test cases | 0.1 | 30% (+30%) | 30% (+30%) |  | 30% | 30%
TS 38.523-3: Protocol test suites (TTCN)
12 |  | 38.523-3 | 9.2, TBD | Introduction of Signaling Test Environment for eCall over IMS for NR | Define PIXIT parameters needed for NR EIEI and test models |  | RAN5#95 (May-22) | R5-221596 | Test model for NR EIEI PIXITS for NR EIEI | TBD | 5% (+5%) | 5% (+5%) |  | 5% | 5%
IMS
TS 34.229-1: IMS over LTE protocol test cases
1 |  | 34.229-1 | TBD | TBD | New sub-clause header sub-clause task to be identified |  | TBD |  | Placeholder for adding conditions related to NR EIEI in Annex A | 0 | 0% | 0% |  | 0% | 0%
TS 34.229-5: IMS over 5GS protocol test cases
28 |  | 34.229-5 | Annex | Addition of generic procedures for ecall over IMS for NR | Generic test procedure for eCall setup and MSD Update in 5GS | Qualcomm | RAN5#93 (Nov-21) | R5-216331 | Generic procedure for NR EIEI call setup and MSD update | 1 | 40% (+40%) | 40% (+40%) |  | 40% | 40%
13 |  | 34.229-5 | 11 | eCall over IMS | New sub-clause header |  |  |  |  | 0
14 | Y | 34.229-5 | 11.1 | eCall over IMS / Manual initiation / Normal registration / Emergency registration / Success / 200 OK with ACK / 5GS | 24.229, cl. 5.1.6.11.1, 5.1.6.11.2 (1) with { UE being registered to IMS } ensure that { when { UE is being made to initiate a manual eCall over IMS } then { UE sends a correctly composed initial REGISTER request for IMS emergency registration } } (2) with { UE having sent an unprotected REGISTER request } ensure that { when { UE receives a valid 401 (Unauthorized) response for the initial REGISTER request sent } then { UE correctly authenticates itself by sending another REGISTER request with a correctly composed Authorization header using the AKAv1-MD5 algorithm } } (3) with { UE having sent unprotected and then protected REGISTER request } ensure that { when { UE receives a valid 200 OK response for the REGISTER sent for authentication } then { UE sends a correctly composed INVITE request with MSD } } (4) with { UE having sent INVITE with MSD for manual eCall over IMS } ensure that { when { UE receives 200 OK containing acknowledgement of reception of MSD } then { UE sends ACK } } (5) with { eCall over IMS being established } ensure that { when { Network sends BYE } then { UE sends 200 OK for BYE } } | Qualcomm | RAN5#93 (Nov-21) | R5-216332 | LTE test case 21.1 | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
15 | Y | 34.229-5 | 11.2 | eCall over IMS / Automatic initiation / Normal registration / Emergency registration / Success / 200 OK with ACK / 5GS | 24.229, cl. 5.1.6.11.1, 5.1.6.11.2 (1) with { UE being registered to IMS } ensure that { when { UE is being made to initiate an automatic eCall over IMS } then { UE sends a correctly composed initial REGISTER request for IMS emergency registration } } (2) with { UE having sent an unprotected REGISTER request } ensure that { when { UE receives a valid 401 (Unauthorized) response for the initial REGISTER request sent } then { UE correctly authenticates itself by sending another REGISTER request with a correctly composed Authorization header using the AKAv1-MD5 algorithm } } (3) with { UE having sent unprotected and then protected REGISTER request } ensure that { when { UE receives a valid 200 OK response for the REGISTER sent for authentication } then { UE sends a correctly composed INVITE request with MSD } } (4) with { UE having sent INVITE with MSD for automatic eCall over IMS } ensure that { when { UE receives 200 OK containing acknowledgement of reception of MSD } then { UE sends ACK } } (5) with { eCall over IMS being established } ensure that { when { Network sends BYE } then { UE sends 200 OK for BYE } } | Qualcomm | RAN5#93 (Nov-21) | R5-218010 | LTE test case 21.2 | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
16 |  | 34.229-5 | 11.3 | Void | [5 empty] | 0 | 0% | 0% |  | 0% | 0%
17 | Y | 34.229-5 | 11.4 | eCall over IMS / Manual initiation / MSD transfer and 200 OK with ACK / SIP INFO request for MSD Update / Success / 5GS | 24.229, 5.1.6.11.3 (1) with { UE being registered to IMS } ensure that { when { UE is being made to initiate a manual eCall over IMS } then { UE performs IMS emergency registration and sends correctly composed INVITE with MSD } } (2) with { UE having sent an INVITE } ensure that { when { UE receives 200 OK containing acknowledgement of reception of MSD } then { UE sends ACK } } (3) with { eCall over IMS being established } ensure that { when { UE receives SIP INFO requesting MSD update } then { UE sends 200 OK acknowledging SIP INFO } } (4) with { UE having sent 200 OK for SIP INFO } ensure that { when { UE is able to provide the updated MSD } then { UE sends a correctly composed SIP INFO with updated MSD information } } (5) with { UE having received 200 OK acknowledging the reception of updated MSD in SIP INFO } ensure that { when { Network sends BYE } then { UE sends 200 OK for BYE } } | Qualcomm | RAN5#93 (Nov-21) | R5-218011 | LTE test case 21.4 | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
18 | Y | 34.229-5 | 11.5 | eCall over IMS / Automatic initiation / MSD transfer and 200 OK with ACK / SIP INFO request for MSD Update / Success / 5GS | (1) with { UE being registered to IMS } ensure that { when { UE is being made to initiate an automatic eCall over IMS } then { UE performs IMS emergency registration and sends correctly composed INVITE with MSD } } (2) with { UE having sent an INVITE } ensure that { when { UE receives 200 OK containing acknowledgement of reception of MSD } then { UE sends ACK } } (3) with { eCall over IMS being established } ensure that { when { UE receives SIP INFO requesting MSD update } then { UE sends 200 OK acknowledging SIP INFO } } (4) with { UE having sent 200 OK for SIP INFO } ensure that { when { UE is able to provide the updated MSD } then { UE sends a correctly composed SIP INFO with updated MSD information } } (5) with { UE having received 200 OK acknowledging the reception of updated MSD in SIP INFO } ensure that { when { Network sends BYE } then { UE sends 200 OK for BYE } } | Qualcomm | RAN5#94 (Feb-22) | R5-221597 | LTE test case 21.5 | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
19 | Y | 34.229-5 | 11.6 | eCall over IMS / Automatic initiation / MSD transfer and 200 OK with ACK / SIP INFO request for unsupported MSD / UE indicates unsuccessful in SIP INFO / 5GS | (1) with { UE being registered to IMS } ensure that { when { UE is being made to initiate an automatic eCall over IMS } then { UE performs IMS emergency registration and sends correctly composed INVITE with MSD } } (2) with { UE having sent an INVITE } ensure that { when { UE receives 200 OK containing acknowledgement of reception of MSD } then { UE sends ACK } } (3) with { automatic eCall over IMS being established } ensure that { when { UE receives SIP INFO requesting MSD update with unsupported datatype } then { UE sends 200 OK acknowledging SIP INFO } } (4) with { UE having sent 200 OK for SIP INFO } ensure that { when { UE is unable to provide the MSD information } then { UE sends a correctly composed SIP INFO with “success” attribute set to false in ack element } } | Qualcomm | RAN5#94 (Feb-22) | R5-221598 | LTE test case 21.6 | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
20 |  | 34.229-5 | 11.7 | Void | [5 empty] | 0 | 0% | 0% |  | 0% | 0%
21 |  | 34.229-5 | 11.8 | Void | [5 empty] | 0 | 0% | 0% |  | 0% | 0%
22 |  | 34.229-5 | 11.9 | Void | [5 empty] | 0 | 0% | 0% |  | 0% | 0%
TS 34.229-2: Applicability and ICS for IMS protocol test cases
23 |  | 34.229-2 | A.4 | Introduce PICS parameters for eCall over IMS for NR test cases | Add new ICS statements. | Qualcomm | RAN5#94 (Feb-22) | R5-217948 | To add PICS parmaters for support of NR eCall feature | 0.1 | 80% (+80%) | 80% (+80%) |  | 80% | 80%
24 |  | 34.229-2 | 4.2 | Add applicabilities of new test cases | Add test case applicability statements for the new test cases introduced in 34.229-1 and/or 34.229-5. | Qualcomm | RAN5#95 (May-22) | R5-216330 R5-217948 R5-222045 | Addition of applicability conditions for 34.229-5 test cases | 0.1 | 40% (+40%) | 40% (+40%) |  | 40% | 40%
TS 34.229-3: IMS test suite (TTCN)
25 |  | 34.229-3 | TBD | Introduction of Signaling Test Environment for eCall over IMS for NR |  |  | RAN5#95 (May-22) |  | IMS Test model for NR EIEI | TBD | 0% | 0% |  | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.