## Cover sheet
RAN5 meeting #96e | [10 empty] | R5-224320
Electronic Meeting, August 15th to August 26th 2022
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | WP UE Conformance – NR small data transmissions in INACTIVE state
Work item code: | NR_SmallData_INACTIVE-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 15% (+15%) | 0 | 8 (+8)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 15% (+15%) | 0 | 8 (+8)
FR1 |  | 15% (+15%) | 0 | 8 (+8)
FR2 |  | 15% (+15%) | 0 | 8 (+8)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 75% (+75%) |  |  | 75% (+75%) |  |  | 75% (+75%)
Common ICS | 38.508-2 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 8 (+8) | 0% | 0 | 8 (+8) | 0% | 0 | 8 (+8)
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3 | 0% |  |  | 0% |  |  | 0%
5 References
[1] RP-221238 | UE Conformance – NR small data transmissions in INACTIVE state
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | NR small data transmissions in INACTIVE state | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_SmallData_INACTIVE-UEConTest
WP Scope: |  | <WP Scope description> | [12 empty] | vs Area
WP Resp: |  | Yogesh Tugnawat |  |  | Yogesht@qti.qualcomm.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 15% (+15%) | 15% (+15%)
[14 empty] | 15 (+15) | 15 (+15)
[14 empty] | 14 (+14) | 14 (+14)
0%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4, 6 | Introduction of General and Signaling Test Environment for Rel-17 Small Data Transmission Tests | ASN.1 and other updates All RRC updates from 38.331 | Qualcomm | RAN5#96 (Aug-22) | R5-225352 R5-225353 R5-225354 R5-225355 |  | 1 | 75% (+75%) | 75% (+75%) |  | 75% | 75%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | A.4.4 | Introduction of common implementation conformance statements for Rel-17 Small Data Transmission Tests | Add ICS as needed for the test case applicability statements for the new test cases | Qualcomm | RAN5#96 (Aug-22) | R5-224331 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.523-1: Protocol test cases
MAC
17 |  | 38.523-1 | 7.1 | NR Layer 2 | [5 empty] | 0
18 |  | 38.523-1 | 7.1.1 | MAC |  |  | RAN5#97 (Nov-22) |  |  | 0
19 |  | 38.523-1 | 7.1.1.13 | Small Data Transmission (SDT) |  |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
20 | Y | 38.523-1 | 7.1.1.13.x | RA Based SDT/2-step RACH/Successful (1) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is not configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is less than or equal to sdt-DataVolumeThreshold and RSRP is above the configured sdt-RSRP-Threshold} then { UE shall initiate 2-step RA based SDT procedure } } (2) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is not configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is greater than sdt-DataVolumeThreshold and RSRP is above the configured sdt-RSRP-Threshold} then { UE shall not initiate RA based SDT procedure and starts normal RRC Resume procedure} } (3) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is not configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is less than or equal to sdt-DataVolumeThreshold and RSRP is below the configured sdt-RSRP-Threshold} then { UE shall not initiate RA based SDT procedure and starts normal RRC Resume procedure } } | TS 38.321, clauses 5.1.1b, 5.1.1c | Motorola Mobility | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
21 | Y | 38.523-1 | 7.1.1.13.x | RA Based SDT/4-step RACH/Successful (1) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is not configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is less than or equal to sdt-DataVolumeThreshold and RSRP is above the configured sdt-RSRP-Threshold} then { UE shall initiate 4-step RA based SDT procedure } } (2) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is not configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is greater than sdt-DataVolumeThreshold and RSRP is above the configured sdt-RSRP-Threshold} then { UE shall not initiate RA based SDT procedure and starts normal RRC Resume procedure} } (3) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is not configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is less than or equal to sdt-DataVolumeThreshold and RSRP is below the configured sdt-RSRP-Threshold} then { UE shall not initiate RA based SDT procedure and starts normal RRC Resume procedure } } | TS 38.321, clauses 5.1.1b, 5.1.1c | Motorola Mobility | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
26 | Y | 38.523-1 | 7.1.1.13.x | RA Based SDT/2-step RACH/not complete/ RA_TYPE to 4-stepRA | TS 38.321, clauses 5.1.1b, 5.1.1c | Motorola Mobility | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
22 | Y | 38.523-1 | 7.1.1.13.x | RA Based SDT/4-step RA based SDT/Time Alignment Timer expiry | TS 38.321, clauses 5.1.1b, 5.1.1c, 5.2 | Motorola Mobility | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
RRC
4 |  | 38.523-1 | 8.1 | NR RRC | Existing sub-clause header |  |  |  |  | 0
5 |  | 38.523-1 | 8.1.5 | RRC others | Existing sub-clause header |  |  |  |  | 0
11 |  | 38.523-1 | 8.1.5.1 | UE capability transfer | Existing sub-clause header |  |  |  |  | 0
12 |  | 38.523-1 | 8.1.5.1.1 | UE capability transfer / Success | TS 38.331, clauses 6.3.3 | Qualcomm | RAN5#97 (Nov-22) |  |  | 0 | 0% | 0% |  | 0% | 0%
6 |  | 38.523-1 | 8.1.5.12 | Small Data Transmission | Existing sub-clause header |  |  |  |  | 0
7 | Y | 38.523-1 | 8.1.1.5.12.x | RRC SDT/CG based SDT/Success (1) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is less than or equal to sdt-DataVolumeThreshold and RSRP is above the configured sdt-RSRP-Threshold and at least one SSB configured for CG-SDT with SS-RSRP above cg-SDT-RSRP-ThresholdSSB} then { UE shall initiate CG based SDT procedure and starts RRC Resume procedure } } (2) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is greater than sdt-DataVolumeThreshold} then { UE shall not initiate CG based SDT procedure and starts normal RRC Resume procedure } } (3) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is less than or equal to sdt-DataVolumeThreshold and RSRP is above the configured sdt-RSRP-Threshold and at least one SSB configured for CG-SDT with SS-RSRP above cg-SDT-RSRP-ThresholdSSB is not available} then { UE shall not initiate CG based SDT procedure and starts normal RRC Resume procedure } } | TS 38.331, clauses 5.3.1.1, 5.3.8.3,5.3.13.1, 5.3.13.1b, 5.3.13.2, 5.3.13.3 | Huawei, Hisilicon | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
8 | Y | 38.523-1 | 8.1.1.5.12.x | RRC SDT/CG based SDT/Failure | TS 38.331, clauses 5.3.1.1, 5.3.8.3,5.3.13.1, 5.3.13.1b, 5.3.135 | Qualcomm | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
9 | Y | 38.523-1 | 8.1.1.5.12.x | RRC SDT/CG based SDT ongoing/Data on non-SDT Radio Bearers (1) with { UE in NR RRC_INACTIVE state and CG based SDT procedure is ongoing} ensure that { when { UE has data to transmit on non-SDT Radio Bearers} then { UE shall send UEAssistanceInformation message with nonSDT-DataIndication set } } | TS 38.331, clauses 5.3.1.1, 5.3.8.3,5.3.13.1, 5.3.13.1b, 5.3.13.2, 5.3.13.3 | Nokia | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
27 | Y | 38.523-1 | 8.1.1.5.12.x | RRC SDT/CG based SDT /SDT-SRB2-Indication | TS 38.331, clauses 5.3.1.1, 5.3.8.3,5.3.13.1, 5.3.13.1b, 5.3.13.2, 5.3.13.3 TS 24.501 clause 5.3.1.4. | Nokia | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
23 |  | 38.523-2 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.523-1 |  |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
24 |  | 38.523-3 | NA | Introduction of General and Signaling Test Environment for SDT |  |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
Overall WP completion
25 |  |  |  | Overall Definition and scope of WI |  |  | RAN5#97 (Nov-22) |  |  | 1 | 35% (+35%) | 35% (+35%) |  | 35% | 35%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.