## Cover sheet
3GPP TSG RAN WG5#96-e | [8 empty] | R5-224980
<Electronic meeting, 15th - 26th Aug 2022>
Agenda Item: | 7.4.2
Source: | China Unicom
Title: | UE Conformance - High power UE (power class 2) for one NR FDD band
Work item code: | NR_PC2_UE_FDD-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
The objective of the UE Conformance - High power UE (power class 2) for one NR FDD band work item is to define the UE conformance requirements, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications in Rel-17. At the RAN#96 meeting the Rel-17 RAN5 work item for UE Conformance - High power UE (power class 2) for one NR FDD band was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed configurations (Note 1) | Number of new configurations | Comments
Overall completion |  | 67% (+62%) | 0 | 2
Completion Compensation |  | -
| Note 1: | Only test cases / configurations completed for all applicable WP areas and sub-areas are counted. For completed test cases / configurations per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed configurations | Number of new configurations | Comments
SA Option 2 (SA NR) (FDD) |  | 66.8% (+61.7%) | 0 | 2
FDD |  | 66.8% (+61.7%) | 0 | 2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS:Area Scope | TS/Area | Completion | Number of new completed PC2 configurations | Number of new PC2 configurations | FDD
[5 empty] | Completion | Number of new completed test cases / configurations | Number of new test cases / configurations
NR FDD HPUE (PC2) configuration
NR FDD PC2 (1 band)
NR FDD PC2 (one band) | NR FDD PC2 (one band)
5 References
[1] RP-221158 | WID on UE Conformance - High power UE (power class 2) for one NR FDD band for RAN#96e
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP on UE Conformance - High power UE (power class 2) for one NR FDD band | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | Relative weight of effort vs TS contribution | [8 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_PC2_UE_FDD-UEConTest | [14 empty] | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 5 | 5
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 work item UE Conformance - High power UE (power class 2) for one NR FDD band comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID) | [14 empty] | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-x: Common Clause | 38.521-x: Tx test cases / 38.522: Test case applicability | 38.521-x: Rx test cases / 38.522 Test case applicability | 38.521-4: RF perfromance test cases / 38.522: Test case applicability | 38.533: RRM test cases / 38:.522 Test case applicability | 38.903: MU and TT | 38.905: Test point analysis
WP Resp: |  | Yu Shi, China Unicom |  |  | shiyu19@chinaunicom.cn | [7 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new configuration or test case? | TS/Area | Configuration / Test case clause | UL configuration(s) / Test case title | Type of change | Interested Operator | Company | Status | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FDD
66.8% (+61.7%)
3
2
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [15 empty] | CALCULATED CELLS | TS STATUS INPUT
38.101-1: HPUE (PC2) for one NR FDD bands
1 | Y | NR FDD PC2 (one band) | n1 |  | New PC2 Config | China Unicom | China Unicom，MediaTek | Ongoing | RAN5#97 (Nov-22) | 38.905: R5-225746 38.521-1: R5-225750 R5-224843 R5-224982 R5-225768 38.508-2: R5-225242 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 0% | 100% | 100% | 100% | 100% | 0% |  | 0% | 100%
2 | Y | NR FDD PC2 (one band) | n3 |  | New PC2 Config | China Unicom | China Unicom，MediaTek | Ongoing | RAN5#97 (Nov-22) | 38.905: R5-225746 38.521-1: R5-225750 R5-224843 R5-224982 R5-225768 38.508-2: R5-225242 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 0% | 100% | 100% | 100% | 100% | 0% |  | 0% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on S1: The TS's weight number is used to set the reletive weights between TS contributions used in the overall calculation of completeness of teh WP item. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new configuration or a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on M6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on Q12: Rapporteur guideline to assign applicable sub-areas for a WP item (columns S to X) To Set applicable sub-area(s) for a WP item do: - Copy the formula/cell content from one of the other non-empty cells under the "WP item status vs Area" section (columns S to X). To Clear applicable sub-area(s) for a WP item do: - Select the cell for teh WP item for the sub-area and press <Delete>-botton (clear content of the cell).