## Cover sheet
3GPP TSG-RAN WG5 meeting #97 | [10 empty] | R5-225947
Toulouse, France, 14 - 18 Nov 2022
Agenda Item: | 7.4.2
Source: | Nokia, Apple
Title: | WP UE Conformance – Further enhancements of NR RF requirements for FR2
Work item code: | NR_RF_FR2_req_enh2-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to WID (890059) on Further enhancements of NR RF requirements for FR2. This work item will cover RF and RRM conformance test specifications for Further enhancements of NR RF requirements for FR2. At the RAN#97-e meeting in Sep 2022 the Rel-17 RAN5 work item for UE Conformance - Further enhancements of NR RF requirements for FR2 was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | #NAME? | #NAME? | #NAME?
Completion Compensation |  | #NAME?
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR2) |  | #NAME? | #NAME? | #NAME?
FR2 |  | #NAME? | #NAME? | #NAME?
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Common ICS | 38.508-2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
NR RF/RRM
FR2 RF common parts | 38.521-2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
FR2 RF Tx test cases | 38.521-2 Tx | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
FR2 RF Rx test cases | 38.521-2 Rx | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
EN-DC FR2 RF test cases | 38.521-3 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Applicability RF, Demod/QSI and RRM test cases | 38.522 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
RRM test cases | 38.533 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Test Point analysis receiver and transmitter test cases | 38.905 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
5 References
[1] RP-221932 | New WID on UE Conformance – Further enhancements of NR RF requirements for frequency range 2 (FR2)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance – Further enhancements of NR RF requirements for frequency range 2 (FR2) | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_RF_FR2_req_enh2-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance – Further enhancements of NR RF requirements for FR2 comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Tuomo Säynäjäkangas, Nokia Ashwin Mohan, Apple |  |  | tuomo.saynajakangas@nokia.com ashwin_mohan@apple.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR2
#NAME?
#NAME?
#NAME?
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | #NAME? | #NAME?
1 |  | 38.508-1 | 4.3 | Reference test conditions | Add necessary test conditions for Rel-17 NR RF FR2 aspects | Nokia | RAN5#101 (Nov-23) |  |  | 0.1 | #NAME? | #NAME? |  | 0%
2 |  | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | New message and IE definition for new Rel-17 NR RF FR2 features | Nokia | RAN5#101 (Nov-23) |  |  | 0.1 | #NAME? | #NAME? |  | 0%
3 |  | 38.508-1 | 5 | Test environments for RF test | Necessary changes to RF test environments | Nokia | RAN5#101 (Nov-23) |  |  | 0.1 | #NAME? | #NAME? |  | 0%
TS 38.508-2: Common ICS
4 |  | 38.508-2 | A,4 | ICS proforma tables | Add ICS as needed for the test case applicability statements for Rel-17 NR RF FR2 aspects | Nokia | RAN5#101 (Nov-23) |  |  | 0.1 | #NAME? | #NAME? |  | 0%
NR RF/RRM | [10 empty] | #NAME? | #NAME?
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | #NAME? | #NAME?
TBD |  | 38.521-2 | 2 | References | Define relevant references made in TS | Nokia | RAN5#101 (Nov-23) |  |  | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreviations respectively | Nokia | RAN5#101 (Nov-23) | R5-225966 | ΔTIB symbols not included as no operator interest for inter-band UL CA | 0.1 | #NAME? | #NAME? |  | 50%
TBD |  | 38.521-2 | 4 | General | Define categories of test requirements | Nokia | RAN5#101 (Nov-23) |  |  | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 | 5.2A | Operating bands for CA | Inter-band CA configuration updates for CA_n258-n261 |  | RAN5#101 (Nov-23) |  | 5.2A.2, bands No operator interest for CA_n258-n261 | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 | 5.3A.4 | UE channel bandwidth per operating band for CA | CA bandwidth class updates to support contiguous downlink aggregated channel BW up to 1600 MHz | Nokia | RAN5#101 (Nov-23) | R5-225967 | NR CA BW classes R2-R12 Fallback group 5 No operator interest | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 | 5.5A.3 | Configurations for inter-band CA | Uplink CA configurations for inter-band CA |  | RAN5#101 (Nov-23) |  | CA_n257A-n259A=>no operator interest CA_n260A-n261A=>no operator interest | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 | Annex A | Measurement channels | Reference Measurement Channels for TDD | Apple | RAN5#97 (Nov-22) | R5-227774 | RMC updates for UL gap RF test | 0.1 | #NAME? | #NAME? |  | 50%
TBD |  | 38.521-2 | Annex B | Propagation conditions | Possible propagation conditions updates in Rel-17 NR RF FR2 tests | Nokia | RAN5#99 (May-23) |  | Possible changes? | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 | Annex C | Downlink physical channels | Define new downlink physical channels in Rel-17 | Nokia | RAN5#99 (May-23) |  | Possible changes? | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 | Annex D | Interfering signals | Define any updates to characteristics of the interfering signal updates in Rel-17 NR RF FR2 tests | Nokia | RAN5#99 (May-23) |  | Possible changes? | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 | Annex E | Global In-Channel TX-Test | Specifiy the measurement of all relevant parameters that describe the in-channel quality of the output signal of the TX under test in a single measurement process (Rel-17 Updates, if any) | Nokia | RAN5#99 (May-23) |  | Possible changes? | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT for updated Rel-17 test cases/bands |  | RAN5#101 (Nov-23) |  |  | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 | Annex G | Uplink Physical Channels | Difference of relative phase and errors | Apple | RAN5#98 (Mar-23) |  | Correction to figure to show joint 2x2 channel for FR2 UL coherent MIMO | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 | Annex H | Statistical Testing | TBD | Nokia | RAN5#99 (May-23) |  | Possible changes? | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 | Annex K | EIRP, TRP, and EIS measurement procedures | Update procedures if needeed for Rel-17 | Nokia | RAN5#99 (May-23) |  | Possible changes? | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 | Annex P | Modified MPR Behavior | Rel-17 updates | Nokia | RAN5#99 (May-23) |  | Possible changes? | 0.1 | #NAME? | #NAME? |  | 0%
TS 38.521-2: FR2 RF test cases - Tx
|  | 38.521-2 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | #NAME? | #NAME?
TBD |  | 38.521-2 Tx | 6.2.1.1.3.2 | UE maximum output power for power class 2 | New requirements for band n259 | Nokia | RAN5#97 (Nov-22) | R5-227783 | Test requirement in 6.2.1.1.5 and 6.2.1.2.5 (Spherical coverage) No operator interest | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.2.4 | Configured transmitted power | Update P-MPRf,c to include testing of UL gap for Tx power management | Apple | RAN5#98 (Mar-23) |  |  | 0.1 | #NAME? | #NAME? |  | 0%
TBD | Y | 38.521-2 Tx | 6.2.5 | Requirements for UL gap for TX power management | New TC to include UL gap for Tx power management | Apple | RAN5#98 (Mar-23) | R5-227774 |  | 1 | #NAME? | #NAME? |  | 10%
|  | 38.521-2 Tx | 6.2A | Transmit power for CA | Existing sub-clause header | [5 empty] | #NAME? | #NAME?
|  | 38.521-2 Tx | 6.2A.1 | UE maximum output power for CA | Existing sub-clause header | [5 empty] | #NAME? | #NAME?
TBD |  | 38.521-2 Tx | 6.2A.1.0 | Minimum conformance requirements | New requirements for inter-band UL CA for PC1, PC2 and PC5 | Apple | RAN5#101 (Nov-23) |  | CA_n257A-n259A=>no operator interest CA_n260A-n261A=>no operator interest | 0.1 | #NAME? | #NAME? |  | 0%
|  | 38.521-2 Tx | 6.2A.1.1 | UE maximum output power - EIRP and TRP for CA | Existing sub-clause header | [5 empty] | #NAME? | #NAME?
TBD |  | 38.521-2 Tx | 6.2A.1.1.1 | UE maximum output power - EIRP and TRP for CA (2UL CA) | New requirements for inter-band UL CA for PC1, PC2 and PC5 | Apple | RAN5#101 (Nov-23) |  | CA_n257A-n259A=>no operator interest CA_n260A-n261A=>no operator interest | 0.1 | #NAME? | #NAME? |  | 0%
|  | 38.521-2 Tx | 6.2A.2 | UE maximum output power reduction for CA | Existing sub-clause header | [5 empty] | #NAME? | #NAME?
|  | 38.521-2 Tx | 6.2A.2.0.1 | Minimum conformance requirements General | New requirements for inter-band uplink CA with two NR bands |  | RAN5#101 (Nov-23) |  | Each UL band is configured with a single CC No operator interest for inter-band UL CA | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.2.0.2 | Maximum output power reduction for power class 1 | New requirements for inter-band uplink CA for CA_n260A-n261A |  | RAN5#101 (Nov-23) |  | No operator interest for CA_n260A-n261A | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.2.0.3 | Maximum output power reduction for power class 2 | New requirements for inter-band uplink CA for CA_n257A-n259A |  | RAN5#101 (Nov-23) |  | No operator interest for CA_n257-n259 | 0.1 | #NAME? | #NAME? |  | 0%
TBD | Y | 38.521-2 Tx | 6.2A.2.0.6 | Maximum output power reduction for power class 5 | New requirements for inter-band uplink CA for CA_n257A-n259A |  | RAN5#101 (Nov-23) |  | No operator interest for CA_n257-n259 | 1 | #NAME? | #NAME? |  | 0%
|  | 38.521-2 Tx | 6.2A.4 | Configured transmitted power for CA | Existing sub-clause header | [5 empty] | #NAME? | #NAME?
TBD |  | 38.521-2 Tx | 6.2A.4.0.1 | Minimum conformance requirements for intra-band UL CA | Clarify that clause 6.2A.4.0 is applicable to intra-band CA | Apple | RAN5#99 (May-23) |  | Change clause number to 6.2A.4.0.1 No need to change yet | 0.1 | #NAME? | #NAME? |  | 0%
TBD | Y | 38.521-2 Tx | 6.2A.4.0.2 | Minimum conformance requirements for inter-band UL CA | New clause for inter-band uplink CA | Apple | RAN5#99 (May-23) |  | No operator interest for inter-band UL CA | 1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.4.1 | Configured transmitted power for CA (2UL CA) | New requirements for inter-band uplink CA | Apple | RAN5#99 (May-23) |  | No operator interest for inter-band UL CA | 0.1 | #NAME? | #NAME? |  | 0%
TBD | Y | 38.521-2 Tx | 6.2A.5 | Requirements for UL gap for TX power management in CA | New TC to include UL gap for Tx power management in CA | Apple | RAN5#100 (Aug-23) |  |  | 1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.3.2 | Transmit OFF power | Include UL gap for for the band for which UL transmission is stopped | Apple | RAN5#99 (May-23) |  |  | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.3A.1 | Minimum output power for CA | Existing sub-clause header | [5 empty] | #NAME? | #NAME?
TBD |  | 38.521-2 Tx | 6.3A.1.0 | Minimum conformance requirements | New requirements for inter-band uplink CA with two NR bands. |  | RAN5#100 (Aug-23) |  | Each UL band is configured with a single CC. New table for PC5 No operator interest for inter-band UL CA | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.3A.2 | Transmit OFF power for CA | Existing sub-clause header | [5 empty] | #NAME? | #NAME?
TBD |  | 38.521-2 Tx | 6.3A.2.0 | Minimum conformance requirements | New requirements for inter-band uplink CA with two NR bands |  | RAN5#98 (Mar-23) |  | Each UL band is configured with a single CC No operator interest for inter-band UL CA | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.3A.3 | Transmit ON/OFF time mask for CA | Existing sub-clause header | [5 empty] | #NAME? | #NAME?
TBD |  | 38.521-2 Tx | 6.3A.3.0 | Minimum conformance requirements | New requirements for inter-band uplink CA with two NR bands |  | RAN5#98 (Mar-23) |  | Each UL band is configured with a single CC No operator interest for inter-band UL CA | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.3A.3.1 | General ON/OFF time mask for CA | New requirements for inter-band uplink CA |  | RAN5#98 (Mar-23) |  | Each UL band is configured with a single CC No operator interest for inter-band UL CA | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.4A.1.0 | Frequency error for CA | New requirements for inter-band uplink CA with two NR bands |  | RAN5#98 (Mar-23) |  | Each UL band is configured with a single CC No operator interest for inter-band UL CA | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.4A.2.0 | Transmit modulation quality for CA | New requirements for inter-band uplink CA with two NR bands |  | RAN5#98 (Mar-23) |  | Each UL band is configured with a single CC No operator interest for inter-band UL CA | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.4A.2.1 | Error vector magnitude for CA | New requirements for inter-band uplink CA with two NR bands. |  | RAN5#98 (Mar-23) |  | Each UL band is configured with a single CC No operator interest for inter-band UL CA | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.4A.2.2 | Carrier leakage for CA | New requirements for inter-band uplink CA with two NR bands. Add PC5 |  | RAN5#98 (Mar-23) |  | Each UL band is configured with a single CC No operator interest for inter-band UL CA | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.4A.2.3 | In-band emissions for CA | New requirements for inter-band uplink CA with two NR bands. Add PC5 |  | RAN5#98 (Mar-23) |  | Each UL band is configured with a single CC No operator interest for inter-band UL CA | 0.1 | #NAME? | #NAME? |  | 0%
TBD | Y | 38.521-2 Tx | 6.4A.2.4 | EVM equalizer spectrum flatness | New requirements for inter-band uplink CA with two NR bands. |  | RAN5#98 (Mar-23) |  | Each UL band is configured with a single CC No operator interest for inter-band UL CA | 1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.5A.1 | Occupied bandwidth for CA | Existing sub-clause header | [5 empty] | #NAME? | #NAME?
TBD |  | 38.521-2 Tx | 6.5A.1.0.0 | General | Add intra-band CA for General |  | RAN5#99 (May-23) |  | No need to change yet | 0.1 | #NAME? | #NAME? |  | 0%
TBD | Y | 38.521-2 Tx | 6.5A.1.0.3 | Occupied bandwidth for inter-band UL CA | New requirements for inter-band uplink CA with two NR bands |  | RAN5#99 (May-23) |  | Each UL band is configured with a single CC No operator interest for inter-band UL CA | 1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.5A.2.1 | Spectrum emission mask for CA | Existing sub-clause header | [5 empty] | #NAME? | #NAME?
TBD |  | 38.521-2 Tx | 6.5A.2.1.0.0 | General | Add intra-band CA for General |  | RAN5#99 (May-23) |  | No need to change yet | 0.1 | #NAME? | #NAME? |  | 0%
TBD | Y | 38.521-2 Tx | 6.5A.2.1.0.3 | Spectrum emission mask for inter-band UL CA | New requirements for inter-band uplink CA with two NR bands |  | RAN5#99 (May-23) |  | Each UL band is configured with a single CC No operator interest for inter-band UL CA | 1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.5A.2.2 | Adjacent channel leakage ratio for CA | Existing sub-clause header | [5 empty] | #NAME? | #NAME?
TBD | Y | 38.521-2 Tx | 6.5A.2.2.0.3 | Adjacent channel leakage ratio for inter-band UL CA | New requirements for inter-band uplink CA with two NR bands |  | RAN5#99 (May-23) |  | Each UL band is configured with a single CC No operator interest for inter-band UL CA | 1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.5A.3 | Spurious emissions for CA | Existing sub-clause header | [5 empty] | #NAME? | #NAME?
TBD |  | 38.521-2 Tx | 6.5A.3.1.0.0 | General | Add intra-band CA for General |  | RAN5#100 (Aug-23) |  | No need to change yet | 0.1 | #NAME? | #NAME? |  | 0%
TBD | Y | 38.521-2 Tx | 6.5A.3.1.0.3 | Spurious emissions for inter-band UL CA | New requirements for inter-band uplink CA with two NR bands |  | RAN5#100 (Aug-23) |  | Each UL band is configured with a single CC No operator interest for inter-band UL CA | 1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.5A.3.2.0 | Spurious emission band UE co-existence for CA | Include inter-band uplink CA |  | RAN5#101 (Nov-23) |  | CA_n257A-n259A=>no operator interest CA_n260A-n261A=>no operator interest | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Tx | 6.6A | Beam Correspondence for CA | New requirements for inter-band uplink CA with two NR bands | Apple | RAN5#100 (Aug-23) |  | Each UL band is configured with a single CC No operator interest for inter-band UL CA | 0.1 | #NAME? | #NAME? |  | 0%
TS 38.521-2: FR2 RF test cases - Rx
|  | 38.521-2 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | #NAME? | #NAME?
TBD |  | 38.521-2 Rx | 7.3.2 | Reference sensitivity power level | Add PC2 requirements for band n259 Add PC1-PC4 requirements for bands n262 and n263 | Nokia, Apple | RAN5#97 (Nov-22) | R5-227784, R5-228042 | No operator interest for n259 PC2 or n263 | 0.1 | #NAME? | #NAME? |  | 30%
TBD |  | 38.521-2 Rx | 7.3.4 | EIS spherical coverage | Existing sub-clause header | [5 empty] | #NAME? | #NAME?
TBD |  | 38.521-2 Rx | 7.3.4.3 | Minimum conformance requirements | Add PC2 requirements for band n259 Add PC1-PC4 requirements for bands n262 and n263 | Nokia, Apple | RAN5#97 (Nov-22) | R5-227951, R5-228041 | No operator interest for n259 PC2 or n263 | 0.1 | #NAME? | #NAME? |  | 30%
TBD |  | 38.521-2 Rx | 7.3A.2 | Reference sensitivity power level for CA | Existing sub-clause header | [5 empty] | #NAME? | #NAME?
TBD |  | 38.521-2 Rx | 7.3A.2.0.1 | Intra-band contiguous CA | Add Aggregate Channel Bandwidth from 1200 to 2000MHz | Apple | RAN5#101 (Nov-23) | R5-227779 |  | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Rx | 7.3A.2.0.3 | Inter-band CA | Add requirements for CA_n257-n259, CA_n258-n260 and CA_n258-n261 | Apple | RAN5#101 (Nov-23) | R5-227319 | Add power classes to Table 7.3A.2.0.3-1 No operator interest for CA combos | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Rx | 7.3A.2.1 | Reference sensitivity power level for CA (2DL CA) | Add test requirements for CA_n257-n259 and CA_n258-n261 | Apple | RAN5#101 (Nov-23) |  | No operator interest for CA combos | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.521-2 Rx | 7.3A.3 | EIS spherical coverage for CA | Existing sub-clause header | [5 empty] | #NAME? | #NAME?
TBD | Y | 38.521-2 Rx | 7.3A.3.0.3 | EIS spherical coverage for Inter-band CA | Add requirements for CA_n257-n259, CA_n258-n260 and CA_n258-n261 | Apple | RAN5#101 (Nov-23) | R5-227316 | Add power classes to Table 7.3A.2.0.3-1 No operator interest for CA combos | 0.1 | #NAME? | #NAME? |  | 0%
TBD | Y | 38.521-2 Rx | 7.3A.3.1 | EIS spherical coverage for CA (2DL CA) | Add test requirements for CA_n257-n259 and CA_n258-n261 | Apple | RAN5#101 (Nov-23) |  | No operator interest for CA combos | 0.1 | #NAME? | #NAME? |  | 0%
TBD | Y | 38.521-2 Rx | 7.5A.0.1 | Adjacent channel selectivity for Intra-band contiguous CA | Add bands n263 and n264 requirements | Apple | RAN5#101 (Nov-23) | R5-227778 |  | 0.1 | #NAME? | #NAME? |  | 0%
TBD | Y | 38.521-2 Rx | 7.6.2.3 | In-band blocking | Add bands n259, n262, n263 and channel bandwidth from 800 to 200MHz | Apple | RAN5#101 (Nov-23) | R5-228043 | No operator interest for n263 | 0.1 | #NAME? | #NAME? |  | 30%
TS 38.521-3: EN-DC FR2 RF test cases - necessary updates
|  | 38.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | #NAME? | #NAME?
TBD |  | 38.521-3 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and test tolerances for the new EN-DC test case |  | RAN5#101 (Nov-23) |  |  | 0.1 | #NAME? | #NAME? |  | 0%
TBD | Y | 38.521-3 |  | Requirements for UL gap for TX power management | New TC to enable testing of Rel-17 FR2 RF Enhancements related to UL gap for Tx power management | Apple | RAN5#100 (Aug-23) |  |  | 1 | #NAME? | #NAME? |  | 0%
TBD | Y | 38.521-3 |  |  |  | Apple | RAN5#101 (Nov-23) |  | Anything else needed? | 0.1 | #NAME? | #NAME? |  | 0%
TS 38.522: Applicability for RF and RRM FR2 test cases
TBD |  | 38.522 | 4,1,2 | RF FR2 standalone conformance test cases | Add test case applicability statements for the test cases introduced for 38.521-2. | Nokia | RAN5#101 (Nov-23) |  | Check new TCs | 0.1 | #NAME? | #NAME? |  | 0%
TBD |  | 38.522 | 4.2 | RRM FR2 standalone conformance test cases | Add test case applicability statements for the test cases introduced for 38.533 | Nokia | RAN5#101 (Nov-23) |  | Check new TCs | 0.1 | #NAME? | #NAME? |  | 0%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | #NAME? | #NAME?
TBD | Y | 38.533 | 7.5.4 or 7.5.11 | UE UL carrier RRC reconfiguration Delay | Add UE UL carrier RRC reconfiguration Delay for FR2, including verification for interruption at UL carrier RRC reconfiguration. | Nokia | RAN5#99 (May-23) |  |  | 1 | #NAME? | #NAME? |  | 0%
TBD | Y | 38.533 | 7.5.3.3 | SCell Activation and deactivation for SCell in FR2 inter-band in non-DRX | Add SCell activation and deactivation delay test for FR2 inter-band CA scenario |  | RAN5#99 (May-23) |  |  | 1 | #NAME? | #NAME? |  | 0%
TBD | Y | 38.533 | 9.1.11 | UL gap for Tx power management | Confirm X value in prioritization of valid CSI reporting during RRM procedures over overlapping UL gaps. | Apple | RAN5#100 (Aug-23) |  |  | 1 | #NAME? | #NAME? |  | 0%
TR 38.903: Test Tolerances analysis RRM and RF test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | #NAME? | #NAME?
TBD |  | 38.903 | Annex A.2 | Handling of common Test Tolerance topics for radiated test cases defined in TS 38.533 | TT analysis for FR2 RRM Test cases |  | RAN5#101 (Nov-23) |  |  | 0.2 | #NAME? | #NAME? |  | 0%
TBD |  | 38.903 | Annex A.4 | Design of radiated test cases defined in TS 38.533 | TT analysis for FR2 RRM Test cases |  | RAN5#101 (Nov-23) |  |  | 0.2 | #NAME? | #NAME? |  | 0%
TBD |  | 38.903 | Annex B | Acceptable uncertainty of test system for test cases defined in TS 38.521-2 for radiative testing | TT analysis for FR2 RF Test cases |  | RAN5#101 (Nov-23) |  |  | 0.2 | #NAME? | #NAME? |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | #NAME? | #NAME?
TBD |  | 38.905 | 4.2 | Test point analysis for FR2 test cases in TS 38.521-2 | TP analysis for FR2 RF Test cases |  | RAN5#101 (Nov-23) |  |  | 0.2 | #NAME? | #NAME? |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.