## Slide 1: MCC TF160 Status Report
Olivier Genoud
Task Force 160 Leader, 3GPP MCC

## Slide 2
TTCN workflow Simplified view
Note: Each step above has a feedback loop to any previous step(s) (e.g. prose/TTCN bug report).
Who:
RAN5_SIG
TF160 +
SS Vendors
TF160
SS Vendor(s) +
UE Vendor(s) +
TF160
Where:
RAN5 meeting
TTCN Workshop
ETSI
SS/UE Vendor
lab
scope of this report
Notes: ASP: Abstract Service Primitive
SS: System Simulator
TTCN: Testing and Test Control Notation (version 3)
UE: User Equipment

## Slide 3
Test Models – 5G:
  Rel-16:
    NR V2X: endorsed ASP updates needed by the NR sidelink SDAP test model.
  Rel-17:
    NR NTN: endorsed corrections to the NTN Timing Advance values used in the NR NTN test model.
    NR feMIMO: endorsed ASP updates for reporting SRS reception to TTCN.
  Rel-18:
    eRedCap: endorsed test model & ASP updates to support reduced bit rate & reduced baseband bandwidth (for SCS 30KHz).
    eDRX enh.: endorsed test model updates to support RRC_INACTIVE state enhancements.
    NR NTN enh.: endorsed test model & ASP updates to support PUCCH repetition for RA Msg4 HARQ-ACK.
    NR_Mob_enh2: endorsed test model & ASP updates to support LTM (Lower Layer Triggered Mobility).
  Prose CRs to TS 38.523-3 submitted at RAN5#107 for the above.
Test models & system interface design Progress at TTCN Workshop #69 (24th Apr’25)
Notes: ASP: Abstract Service Primitive

## Slide 4
Test Models – LTE:
  Rel-18 band 106: endorsed test model updates to support 3MHz bandwidth.
Test Models – NB-IoT:
  Rel-13: endorsed test model updates to support broadcast of up to 3 SI messages.
  Rel-15: endorsed ASP updates to support MO-EDT (Early Data Transmission).
  Rel-16: endorsed ASP updates to support PUR (Preconfigured UL Resource).
Test Models – IMS:
  TCP: discussed several improvements to the handling of the closing of a TCP connection.
Prose CRs to TS 36.523-3 submitted at RAN5#107 for the above.
Test models & system interface design Progress at TTCN Workshop #69 (24th Apr’25)
Notes: ASP: Abstract Service Primitive

## Slide 5
Test Models – MCX:
  Rel-17 MCX: endorsed MCX IPCAN test model & ASP updates to add support of NR/5GC as an additional IPCAN.
  Prose CR to TS 37.579-5 submitted at RAN5#107 for the above.
RAN5 TTCN Workshop #69 material:
  https://portal.3gpp.org/Home.aspx#/meeting?MtgId=81724
Test models & system interface design Progress at TTCN Workshop #69 (24th Apr’25)
Notes: ASP: Abstract Service Primitive

## Slide 6: TTCN development Progress for period: March to May’25
Completed:
  5G Rel-17:
    NR NTN (default Tx-Rx separation)
    NR coverage enhancements
    NR QoE management & optimization (SRB4)
    UAS connectivity, identification, tracking
  LTE:
    Rel-12 Access Class Barring per PLMN
Started:
  5G-Advanced Rel-18:
    NR NTN enhancements
    NR MT small data Tx (SDT)
    NR & MR-DC in-device co-existence (IDC) enh.
    NR FR1 3MHz BW (n106)
  IMS:
    Rel-18 IMS data channel
    Rel-19 eCall over IMS alignment with CEN
  Mission Critical Rel-17:
    MCPTT over NR/5GC
    MCVideo over NR/5GC
    MCData over NR/5GC
Progressed:
  5G:
    Rel-16 V2X with NR sidelink
    Rel-17 NR MIMO further enh.
  5G-Advanced Rel-18:
    eRedCap UE
    NR coverage further enh.
    NR dual Tx/Rx MUSIM
    NR multi-carrier enh. (DCI x_3)
    XR enhancements for NR
  NB-IoT Rel-18:
    IoT NTN enhancements
  Positioning Rel-18:
    Expanded & improved NR positioning
Notes: Completed: The TTCN of all test cases is ready for verification.
Progressed: TTCN development ongoing, not yet completed.
Started: TTCN development has started since last report.
Suspended: TTCN development on hold due to external blocker.

## Slide 7: TTCN verification Progress for period: 12th Feb --> 15th May’25
Completed:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
NR eDRX | Rel-17 | 541 | 4 / 4 | +1 | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 8: TTCN verification Progress for period: 12th Feb --> 15th May’25
Progressed – 5G (EN-DC, NR/5GC):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
EN-DC access stratum | Rel-15 | 503 | 98 / 104 | = | 
NR/5GC access stratum | Rel-15 | 503 | 154 / 163 | = | 
NR/5GC NR-DC | Rel-15 | 503 | 14 / 24 | = | 
NR/5GC NR CA | Rel-15 | 510 | 31 / 33 | = | 
EN-DC NR CA | Rel-15 | 512 | 14 / 18 | = | 
5G private network - SNPN | Rel-16 | 518 | 7 / 9 | = | 
NR mobility enhancements | Rel-16 | 522 | 10 / 16 | = | 
NR UE power saving | Rel-16 | 533 | 5 / 9 | +2 | 
IMS eCall over NR/5GC (38.523) | Rel-16 | 537 | 4 / 15 | = | 
MR-DC & NR CA enhancements | Rel-16 | none | 9 / 28 | = | 
MPS Priority Indication | Rel-16 | none | 3 / 4 | = | 
NR reduced capability (RedCap) | Rel-17 | 530 | 7 / 10 | = | 
5G NW slicing enhancements - Phase 2 | Rel-17 | none | 7 / 8 | = | 
NR UE power saving enhancements | Rel-17 | 540 | 1 / 5 | = | 
NR RAN slicing enhancement | Rel-17 | none | 4 / 8 | = | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 9: TTCN verification Progress for period: 12th Feb --> 15th May’25
Progressed – IMS, Positioning, MCX:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
LTE positioning | Rel-9+ | 166, RTF-115 | 17 / 27 | = | 
MCPTT over LTE (IPCAN test model) | Rel-14 | 288, RFT-153 | 38 / 51 | = | 
MCPTT over LTE (E-UTRA test model) | Rel-14 | 288, RFT-153 | 2 / 51 | +1 | 
IMS eCall over LTE (34.229) | Rel-14 | 298 | 5 / 12 | = | 
MCData over LTE (IPCAN test model) | Rel-14 | 329, RFT-153 | 4 / 28 | = | 
MCPTT enhancements over LTE (IPCAN test model) | Rel-15 | 330, RFT-153 | 5 / 22 | = | 
IMS over NR/5GC | Rel-15 | 505 | 93 / 95 | = | 
NR Positioning | Rel-16 | none | 10 / 36 | = | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 10: TTCN verification Progress for period: 12th Feb --> 15th May’25
Progressed – 4G (LTE, eMTC, NB-IoT):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
CA intra-band contiguous | Rel-11 | 162 | 20 / 21 | = | Left: TC 7.1.2.11.1(multiple TA)
SCE-PHY | Rel-12 | 245 | 6 / 9 | = | 
eDRX | Rel-13 | 253 | 4 / 5 | = | Left: TC 9.2.4.1.3(emergency call)
eMTC (CAT-M1) | Rel-13 | 254-A | 14 / 15 | = | Left: TC 7.1.4.3a(Lch prioritization)
eMTC (CIoT) | Rel-13 | 254-C | 2 / 5 | = | 
NB-IoT (CAT-NB1) | Rel-13 | 257 | 72 / 73 | = | Left: TCs 22.1.1.M2
LAA | Rel-13 | 272 | 1 / 2 | = | Left: TC 8.3.1.32(RSSI measurement)
eNB-IoT | Rel-14 | 295 | 11 / 14 | = | Left: SC-PTM (in iWD-003), IRAT with E-UTRA
IMS eCall over LTE (36.523) | Rel-14 | 298 | 4 / 9 | = | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 11: TTCN verification Progress for period: 12th Feb --> 15th May’25
Started:
Starting:
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
LTE ACB per PLMN | Rel-12 | WI-226 | 6 / 14 | +6 | +5 under verification
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
P-CSCF restoration | Rel-15 | WI-504 | 0 / 2 |  | +2 under verification
NR NTN (GSO) | Rel-17 | none | 0 / 22 |  | +6 under verification
IMS eCall over LTE - CEN alignment (34.229) | Rel-19 | none | 0 / 8 |  | +2 under verification
Notes: Started: lists the features for which at least one (first) test case has been submitted and agreed since the last report.
Starting: lists the feature for which no test case has yet been verified, but at least one submission has been made, which is under review (consultation period still running).

## Slide 12
2024 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC# | TTCN Develpmt | 2025 WkLoad | TTCN Development Status (as of May’25) / Comments
5G V2X with NR sidelink | Rel-16 | N,L | Q2’25 | 68 | Q4’20-Q4’25 | 1.5 | 69% (@iwd-25wk11)
LTE multi-USIM UE (MUSIM) | Rel-17 | L | Q3’23 | 7 | Q4’24-Q2’25 | 1 | Not started
NR multi/broadcast services (MBS) | Rel-17 | N | Q4’23 | 48 | Q4’22-Q4’25 | 2.5 | 11% (@iwd-24wk50)
NR sidelink enhancements | Rel-17 | N | Q3’25 | 2 | Q4’22-Q4’25 | 0.5 | Not started ; no prose
NR sidelink relay | Rel-17 | N | Q3’25 | 40 | Q4’22-Q4’25 | 2.5 | Not started
NR coverage enhancements | Rel-17 | N | Q1’24 | 17 | Q1’23-Q1’25 | 0.5 | 100% (@iwd-25wk11)
NR for non-terrestrial networks (NTN) | Rel-17 | N | Q4’25 | 22 | Q1’23-Q1’25 | 0.2 | 100% (@iwd-25wk11)
NR MIMO further enhancements | Rel-17 | N | Q2’24 | 9 | Q1’23-Q2’25 | 0.5 | 89% (@iwd-25wk11)
5G ATSSS – Phases 1 & 2 | R16to17 | N,W | Q3’24 | 15 | Q2’24-Q4’25 | 1 | Not started
Dual Tx/Rx MUSIM for NR | Rel-18 | N | Q2’25 | 4 | Q3’24-Q2’25 | 0.5 | 90% (@iwd-25wk11)
IoT NTN with enhancements | Rel-18 | L | Q4’25 | 9 | Q3’24-Q4’25 | 0.5 | 75% (@iwd-25wk11)
Enhanced RedCap NR UE | Rel-18 | N | Q4’25 | 13 | Q3’24-Q4’25 | 1.5 | 90% (@iwd-25wk11)
NR multi-carrier enhancements | Rel-18 | N | Q4’25 | 24 | Q3’24-Q4’25 | 2 | 75% (@iwd-25wk11)
NR coverage further enhancements | Rel-18 | N | Q4’25 | 17 | Q3’24-Q4’25 | 1.5 | 24% (@iwd-25wk11)
NR network energy savings | Rel-18 | N | Q4’25 | 8 | Q3’24-Q4’25 | 0.5 | 60% (@iwd-24wk50)
XR enhancements for NR | Rel-18 | N | Q4’25 | 24 | Q3’24-Q4’25 | 2.3 | 40% (@iwd-25wk11)
NR mobility further enhancements | Rel-18 | N | Q4’25 | 17 | Q4’24-Q4’25 | 1.5 | 10% (@iwd-24wk37)
5G non-public networks (NPN) – Phase 2 | Rel-18 | N | Q4’25 | 9 | Q4’24-Q4’25 | 1 | Not started
Expanded & improved NR positioning | Rel-18 | N | Q2’26 | 21 | Q4’24-Q4’26 | 1 | 36% (@iwd-25wk11)
New/extended bands & band combination | R16to19 | L,N | Q4’26 | n/a | Q1’21-Q4’26 | 0.5 | 57% (@iwd-25wk11)
TTCN maintenance & deliveries |  |  |  |  | Q1–Q4 | 45 | 
Release & configuration management |  |  |  |  | Q1–Q4 | 6 | 
Total: |  |  |  | 374 |  | 74 | person-months
TTCN workplan 2025
Status of 2024 tasks carried over and maintenance tasks
Notes: Note: TTCN of some features initially started in 2024 will only be completed in 2025 due to availability of prose late in CY2024, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 13
2025 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2025 WkLoad | TTCN Development Status (as of May’25) / Comments
MCX Client – Rel-17 enhancements | Rel-17 | L,N | Q4’25 | 194 | Q1’25-Q4’25 | 4 | 40% (@iwd-25wk11)
LTE Band 106 (3 MHz BW) | Rel-18 | L | Q3’25 | n/a | Q1’25-Q4’25 | 2 | 10% ; Test Model work
NR FR1 less than 5MHz BW (3 MHz BW) | Rel-18 | N | Q4’25 | n/a | Q1’25-Q4’25 | 2 | 30% (@iwd-25wk11)
NR MT SDT | Rel-18 | N | Q4’25 | 6 | Q1’25-Q4’25 | 1 | 50% (@iwd-25wk11)
NR/MR-DC IDC enhancements | Rel-18 | N,W | Q2’26 | 5 | Q1’25-Q2’26 | 1 | 40% (@iwd-25wk11)
NR NTN enhancements | Rel-18 | N | Q4’25 | 16 | Q1’25-Q4’25 | 2.5 | 4% (@iwd-25wk11)
IMS data channel | Rel-18 | N,L | Q4’25 | 12 | Q1’25-Q4’25 | 2 | 16% (@iwd-25wk11)
LTE based 5G terrestrial broadcast | Rel-18 | L | Q4’25 | ~20 | Q3’25-Q1’26 | 1.5 | Not started ; no prose
NR air-to-ground network | Rel-18 | N | Q4’25 | 6 | Q1’25-Q4’25 | 0.5 | Not started ; no prose
NR MBS enhancements | Rel-18 | N | Q4’25 | 2 | Q1’25-Q4’25 | 0.5 | Not started ; no prose
5G ATSSS – Phase 3 | Rel-18 | N,W | Q1’26 | 8 | Q3’25-Q3’26 | 1 | Not started ; no prose
NR MIMO evolution for DL & UL | Rel-18 | N | Q4’25 | ~2 | Q1’25-Q4’25 | 0.5 | Not started ; no prose
Enhanced NR high-speed train scenario in FR2 | Rel-18 | N | Q4’25 | ~2 | Q1’25-Q4’25 | 0.5 | Not started ; no prose
NR support for UAV | Rel-18 | N | Q1’26 | 20 | Q3’25-Q3’26 | 1 | Not started ; no prose
eCall over IMS alignment with CEN | Rel-19 | N,L | Q4’25 | 26 | Q1’25-Q4’25 | 3 | 50% (@iwd-25wk11)
TEIx_Test (misc. test coverage enhancement) | Rel-8+ | All | n/a | 30 | Q1’25-Q4’25 | 3 | 2025 total after RAN5#107: 18 new tests
Total: |  |  |  | 349 |  | 26 | person-months
TTCN workplan 2025
Status of new 2025 tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 14
2025 workload is estimated at 100 person-months (pm), see previous slides.
PCG#53/OP#52 approved the 3GPP funding of 58 pm for 2025 TTCN tasks.
GCF and CTIA/PTCRB have agreed to continue TF160 financial support in 2025.
Current commitments for 2025 are as follows:
3GPP companies / 3GPP MRPs committed to provide 19 pm as voluntary contributions for 2025 TTCN development.
Total resources of 97 pm  estimated funding gap of 3 pm.
TTCN funding 2025
Status
Funding |  | 
Entity | Person-months | Comments
3GPP | 58 | PCG#53/OP#52 approved
GCF | 12 | NR_feMIMO, ATSSS, NR_cov_enh(2), NwEnergySav, NR_XR_enh, NR_MT_SDT, NR-eNTN
CTIA/PTCRB | 6 | NR-(f)eCoverage, NR-(f)eMIMO, NR-feMobility, NwEnergySav
Qualcomm | 2 | eCallCEN, NR-eNTN, NR_Mob_enh2
Total: | 78 | 
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 
Adare | 3 | 
Keysight | 1 | 
Rohde&Schwarz | 1 | 
Total: | 19 | 
Notes: MRPs: Market Representation Partners

## Slide 15: Annexes

## Slide 16: TTCN deliveries and baseline 2025 schedule
One TTCN-2 full delivery (FDD) and four TTCN-3 full deliveries.
Type definitions baseline upgrade to 3GPP Release 18 required in 2025:
  Rel-18 Phase2: partial upgrade to Rel-18 Dec'24 baseline for NR+E-UTRA+LPP due to new/updated ASN.1 IEs required by Rel-18 NR, NB-IoT & POS test cases.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
 wk03 |  |  | 17-Jan |  | GCF CAG#81 (21-22 Jan)
 wk09 |  |  | 28-Feb |  | PTCRB PVG#108 (4-6 Mar)
 wk11 | 14-Mar | 10-Mar | 14-Mar | TTCN-3 Rel-18 phase2 baseline upgrade | Partial upgrade to Rel-18 Dec'24 baseline for NR+E-UTRA+LPP
 wk17 |  |  | 25-Apr |  | GCF CAG#82 (29-30 Apr)
 wk19 |  |  | 09-May |  | PTCRB PVG#109 (13-15 May)
wk24 | 13-Jun | 09-Jun | 13-Jun | TTCN-3 | 
wk29 |  |  | 18-Jul |  | GCF CAG#83 (22-23 Jul)
wk32 |  |  | 08-Aug |  | PTCRB PVG#110 (12-14 Aug)
wk38 | 19-Sep | 15-Sep | 19-Sep | TTCN-3 | 
wk41 |  |  | 10-Oct |  | GCF CAG#84 (14-15 Oct)
wk44 |  |  | 31-Oct |  | PTCRB PVG#111 (4-6 Nov)
wk49 | 05-Dec | 01-Dec |  | TTCN2 (FDD) | 
wk50 | 12-Dec | 08-Dec | 12-Dec | TTCN-3 | 

## Slide 17
2026 Potential Candidate | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2026 WkLoad | Work Item Code / Status
MPS when access to EPC/5GC is WLAN | Rel-18 | N,L,W | Q1’26 | ~5 | 2026 | 1 | MPS_WLAN-UEConTest / New
Railways features for MCX Client | Rel-18 | N | 2026 | TBD | 2026 – 2027 | 1 | MC_AHGC_eMCSMI_Irail / no test Work Item yet
NR sidelink relay enhancements | Rel-18 | N | 2026 | TBD | 2026 – 2027 | 0.5 | NR_SL_relay_enh / no test Work Item yet
TTCN workplan: 2026 early candidates WIs with no 2025 budget, candidate for 2026 budgeting
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.