## 3GPP PJ Status
Status Report: 3GPP Standardization
Reporting Period: 04th September - 08th September 2023
Technology Domain |  |  | 3GPP Standardization
Description |  | NECI members represent as NEC Delegates at 3GPP. Contributions are made to 3GPP SA and CT Technical Specifications Group (TSG):
Work items
1 | Work items - IPR
| IDEAS |  |  |  | Target Dates | % Comp | Act Finish | Remark
| Support of dual steer across PLMN and NPN networks (5800000076 and 5800000077) Inventors: Prabhu, Tamura-san, Kundan-san, Iskren-san, and Jasmina-san. |  |  |  | 1st draft of patent application by inventors: By 01 September 2023 IPR review completed: By 25 September 2023 Joint reviewing by inventors and IPR division: By 27 September 2023 Submission to M&S: By cob 27 September 2023 Filing deadline at India: 29 September 2023 | 60% |  | Two applications will be filed. Inventors first draft is shared with IPR team for review.
| Support of femto cell in 5GS (5800000083/84) Inventors: Kundan-san, Tamura-san, Iskren-san, Chenghock-san, and Futaki-san. |  |  |  | 1st draft of patent application by inventors: By 25 August 2023 IPR review completed: By 1 September 2023 Joint reviewing by inventors and IPR division: By 6 September 2023 Submission to M&S: By cob 6 September 2023 Filing deadline at India: 8 September 2023 | 100% |  | Inventors are preparing first draft of the NID. Inventor sent the first draft to the IPR team for review. IPR teams have reviewed it and sent to it to inventors for final review. It is filed as per plan.
| Dual steer for PNI-NPN Inventors: Jasmina-san, Iskren-san, Prabhu, Kundan-san, and Tamura-san. |  |  |  | 1st draft of patent application by inventors: By 29 September 2023 IPR review completed: By 13 October 2023 Joint reviewing by inventors and IPR division: By 20 October 2023 Submission to M&S: By cob 22 October 2023 Filing deadline at India: 24 October 2023 | 20% |  | Inventors first draft is under preparation.
| REMARK |  |  | 1. IPR draft application is under preparation and review.
2 | Other items (Technical contributions, Miscellaneous)
Read and analysed the contributions of SAP#101.
| REMARK |  |  | Prepared a report for SA2#158 meeting and shared.