## Slide 1: FS_ACDC Status Update
Atsushi Minokuchi
NTT DOCOMO
FS_ACDC Rapporteur
3GPP TSG-SA WG1 Meeting #64
San Francisco, CA, USA, 11 – 15 November 2013
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: FS_ACDC Status
Is this a new WI? N
This WI has been approved at SP#57
  Approved WID is in tdoc SP-120546
Update of WID has been approved at SP#61
  Approved WID is in tdoc SP-130415
Notes: 1

## Slide 3: FS_ACDC Progress
Progress made at this meeting
  Five use case P-CRs were incorporated into TR: interaction with ACB “ACDC overrides ACB”, interaction with SSAC, different barring rates, on-going communication, trusted source of the list.
  The session agreed to use mainly the term “ACDC category” in TR.
Study Item Completion: 50%
Draft TR 22.806 Completion: 50%
Notes: 1

## Slide 4: FS_ACDC Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 3
Number of slots requested for next meeting
  sum of plenary and drafting slots: 4
Number of Drafting session participants: 20
Notes: 1

## Slide 5: FS_ACDC Completion Date
Target completion date in WID: 03/2014 SP#63
Current target completion date: 03/2014 SP#63
Will target completion date be met? N
If not, change target completion date to:
  06/2014 SP#64
Expected date to send TR to SA plenary:
  For information: SA1#66 (05/2014)
  For approval: SA1#66 (05/2014)
Notes: 1

## Slide 6: FS_ACDC Planning/Progress
Topics to focus on at SA1#65 (Jan 2014):
  Editorial clean up, incl. by using the term “ACDC category”
  To complete roaming scheme, interworking with EAB/PMOC, graceful return, network sharing aspect(SA1 output improvement proposals)
  Consolidation of potential requirements
Planning for subsequent meetings
  SA1#66 (May 2014)
    Consolidation of potential requirements (cont.)
    Conclusion
    Finalize TR
Notes: 1

## Slide 7: Work plan between meetings
Email discussion
  Editorial clean up, incl. by using the term “ACDC category”
  Tentative start date: TBD
Notes: 1

## Slide 8: FS_ACDC Progress Estimate
Estimated percentage completion:
  SA1#65 (Jan 2014): 70%
  SA1#66 (May 2014): 90%
Notes: 1

## Slide 9: FS_ACDC Agreed documents
List of agreed documents at this meeting:
S1-135071 | Rapporteur | ACDC TR: editorial changes from Rapporteur
S1-135072 | NTT DOCOMO | ACDC introduction: alignment to the updated WID
S1-135075 | NTT DOCOMO | ACDC use case: further clarification on interaction with other forms of access control - SSAC
S1-135176 | Rapporteur | FS_ACDC drafting report
S1-135179 | NTT DOCOMO | ACDC use case: control range and proportionality
S1-135335 | Qualcomm Incorporated | ACDC Use Case: Control of ACDC
S1-135183 | NTT DOCOMO, Qualcomm Incorporated | ACDC use case: further clarification on interaction with other forms of access control - ACB
S1-135311 | Sony Mobile Communication | ACDC List provisioning
S1-135184 | Rapporteur | TR 22.806 v0.4.0
Notes: 1