## Slide 1: FS_Metaverse Status Update Study on Localized Mobile Metaverse Services
Erik Guttman
Samsung
FS_Metaverse Rapporteur
3GPP TSG-SA WG1 Meeting #98-e
Electronic Meeting, 9 – 19 May 2021
Notes: 1

## Slide 2: FS_Metaverse Progress
Progress made at this meeting
  At SA1#98e
    S1-221264 TR Skeleton Feasibility Study on Localized Mobile Metaverse Services
    S1-221265 pCR pCR 22.856 - Scope
    S1-221266 pCR pCR 22.856 Informative Annex on Avatar Services
    S1-221267 pCR New Use Case for Mobile Metaverse: 5G-enabled Traffic Flow Simulation and Situational Awareness
    S1-221268 pCR pCR 22.856 Localized Metaverse Services Use Case
    S1-221269 pCR pCR on Collaborative and concurrent engineering in
    product design using metaverse services
Work/Study Item Completion: 15%
Controversial issues
  none
Notes: 1

## Slide 3: FS_Metaverse Planning
Planning for subsequent meetings
  SA1#99 (Aug 2022): 40%
    New/Updated use cases and potential requirements
  SA1#100 (Nov 2022): 65%
    New/Updated use cases and potential requirements
    Start consolidation
  SA1#100ah (Jan 2023) TBD <recommended!>: 80%
    Final work on use cases and potential requirements
    Progress / completion of consolidation.
  SA1#101 (Feb 2023): 100%
    Updated use cases and potential requirements
    Complete consolidation and conclusions
    Final TR clean-up
Notes: 1

## Slide 4: Work plan between meetings
Email coordination
  Coordination among interested/contributing companies, about planned inputs, use cases, etc.
  Before SA1 99e
    2 [~2 hour] calls proposed, to be moderated by the rapporteur
    Proposed agenda
      Discuss use cases from SA1 98e, to return again or improved to SA1 99e
      New use cases for SA1 99e
      Identify key terms and discuss overview, etc.
    Proposed times [exact dates tbd, doodle to follow]:
      Call 1: 2nd week July (~4 weeks before 13.8.22 submission deadline)
      Call 2: 1st week Aug (~1 week before submission deadline)
Notes: 1

## Slide 5: FS_Metaverse Completion Date
Current expected completion dates:
  For approval: SA#99 (03/2023)
Have these dates been changed at this meeting? No
Notes: 1

## Slide 6: FS_Metaverse History
This Study Item was agreed at SA1#97e
  Approved WID is in tdoc SP-220353
  SA1#96e – SID in tdoc S1-214247 was noted
  SA1#97e – SID in tdoc S1-220195 was agreed
  SA1#98e – TR and 5 pCRs were agreed
Notes: 1

## Slide 7: FS_Metaverse History
This WI has been agreed at SA1#87
  Approved WID is in tdoc SP-190837
History of completion rates
  SA1#98e (05/2022): 15 [target 25]%
  SA1#97e (02/2022): 0%
Notes: 1