## Sheet1
| SA WG2 Meeting #111 | [10 empty] | S2-153370
19-23 October 2015, Chengdu, China
Source: SA WG2 Chairman
Title: SA2 Work Planning Worksheet
Document for: Information
Agenda Item: 7.2
Work Item / Release: All / Rel-13 and later
Abstract of the contribution: A revision of this document will capture agreements during work planning as SA2 preparations for TSG SA and/or for future SA2 meetings.
1. Introduction
This paper provides the overview of the work item status at the time of the work planning session.
The budget figures indicated are estimates based on status reached and on discussion on expected content.
The shown budget figures may require further consolidation.
|  | previous |  |  |  |  | Oct 15 |  | Nov 15 |  | Jan 16 |  | Apr 16 |  | May 16 |  | Jul 16 |  | Oct 16 |  | Nov 16
|  | quarter | current | Target | original | accumul. | SA2#111 |  | SA2#112 |  | SA2#113 |  | SA2#114 |  | SA2#115 |  | SA2#116 |  | SA2#117 |  | SA2#118
Track | Work Item | status | status | date | plan TUs | TUs | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan |  | Plan | Actl. | Plan | Actl.
3GPP | FS_AE_CIoT | 65% | % | Dec 15 | 7 |  | 4 |  | 3
3GPP | FS_eDECOR | 0% / unstarted |  | Mar 16 | 3 |  | 1 |  | 1 |  | 1
3GPP | FS_CUPS | 0% / unstarted |  | Jun 15 | 9 |  | 1 |  | 2 |  | 2 |  | 2 |  | 2
3GPP | "FS_5G" | 0% / unstarted |  |  |  |  | 2
3GPP | eDRX | 95% |  | Dec 15 |  |  | 1
3GPP
3GPP | Maint | [5 empty] | 5 |  | 4 |  | 4 |  | 4 |  | 4 |  | 3
3GPP | TEI14 3GPP acc | [5 empty] | 1
Sum | [6 empty] | 15 | 0 | 10 | 0 | 7 | 0 | 6 | 0 | 6 | 0 | 3 | 0 | 0 | 0 | 0 | 0
|  | previous |  |  |  |  | Oct 15 |  | Nov 15 |  | Jan 16 |  | Apr 16 |  | May 16 |  | Jul 16 |  | Oct 16 |  | Nov 16
|  | quarter | current | Target | original | accumul. | SA2#111 |  | SA2#112 |  | SA2#113 |  | SA2#114 |  | SA2#115 |  | SA2#116 |  | SA2#117 |  | SA2#118
Track | Work Item | status | status | date | plan TU | TUs | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl.
other | FS_V8 | % |  | Mar 16 | 9 |  | 3 |  | 3 |  | 3
other | FS_SEW | 0% / unstarted |  | Jun 16 | 10 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
other | FS_AULC | 0% / unstarted |  | Jun 16 | 5 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
other
other | Maint | [5 empty] | 5 |  | 5 |  | 4 |  | 4 |  | 3 |  | 3
other | TEI14 PCC/QoS | [5 empty] | 0.5
other | TEI14 IMS/rel. | [5 empty] | 0.5
Sum | [6 empty] | 12 | 0 | 11 | 0 | 10 | 0 | 7 | 0 | 6 | 0 | 3 | 0 | 0 | 0 | 0 | 0