## Sheet1
SA WG2 Meeting #124
|  |  | Nov 27 - Dec 1, Reno, NV, USA | [12 empty] | S2-178850
Source: SA WG2 Chairman
Title: SA2 Work Planning Worksheet
Document for: Information
Agenda Item: 7.2
Work Item / Release: All / Rel-15 and later
Abstract of the contribution: A revision of this document will capture agreements during work planning as SA2 preparations for TSG SA and/or for future SA2 meetings.
1. Introduction
This paper provides the overview of the work item status at the time of the work planning session.
The budget figures show the estimates for the expected work or show the status reached so far.
Any shown budget figures may require further consolidation.
[10 empty] | Jan 17 |  | Feb 17 |  | Mar 17 |  | May 17 |  | Jun 17 |  | Aug 17 |  | Okt 17 |  | Nov 17 |  | Jan 18 |  | Feb 18 |  | Apr 18 |  | May 18 |  | Jul 18 |  | Aug 18 |  | Oct 18 |  | Nov 18
status estimation (%) | [5 empty] | Target | acc./plan. | planned | accumul. | SA2#118bis |  | SA2#119 |  | SA2#120 |  | SA2#121 |  | SA2#122 |  | SA2#122bis |  | SA2#123 |  | SA2#124 |  | SA2#125 |  | SA2#126 |  | SA2#127 |  | SA2#127-bis |  | SA2#128 |  | SA2#128-bis |  | SA2#129 |  | SA2#129-bis
Q4/16 | Q1/17 | Q2/17 | Q3/17 | Q4/17 | Work Item | date | TUs (%) | TUs | TUs | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Update during SA#116 | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Update during SA#116 | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl.
|  | 55 | 75 |  | 5GS_Ph1 | 2017-12-12 | 97.8061 | 196 | 191.7 | 16 | 18 | 17 | 23 | 21 | 24.2 | 26 | 27 | 26 | 31 | 26 | 32.5 | 26 | 36 | 38
10 | 30 | 90 | 100 |  | FS_USOS | 2017-06-17 | 106.6066 | 3.33 | 3.55 |  |  | 1 | 1 | 1 | 1.3 | 1.33 | 1 |  | 0.25
[5 empty] | USOS | 2017-12-17 | 0 | 0.5 | 0 | [14 empty] | 0.5
5 | 30 | 60 | 95 | 100 | FS_REAR | 2017-09-17 | 122.807 | 10.83 | 13.3 | 1 | 2 | 1 | 2 | 2 | 2.3 | 2.33 | 2 | 2 | 2 | 2 | 2 | 0.5 | 1
[5 empty] | tentative REAR | 2017-12-17 | #DIV/0! | 0 | 0
5 | 50 | 60 | 100 |  | FS_eVoLP | 2017-09-17 | 77.0318 | 2.83 | 2.18 |  |  | 1 | 1 | 1 | 0.35 | 0.33 | 0.33 | 0.5 | 0.5
|  |  |  | 100 | eVoLP | 2017-09-17 | 100 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5
| 10 | 85 | 100 |  | NAPS | 2017-09-17 | 110.2041 | 8.33 | 9.18 |  |  | 1 | 2 | 1 | 2.6 | 2.33 | 2.33 | 2 | 1.25 | 2 | 1
|  | 10 | 85 | 100 | PS_data_off_2 | 2017-09-17 | 108.5714 | 3.5 | 3.8 |  |  |  |  | 1 | 1.3 | 1 | 1 |  |  | 1 | 1 | 0.5 | 0.5
|  | 55 | 90% |  | EDCE5 | 2017-09-17 | 118.4444 | 4.5 | 5.33 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.33 | 0.5 | 1
[5 empty] | EPS_URLLC | 2018-03-01 | 12 | 2.5 | 0.3 | [12 empty] | 0.5 | 0.3 | 1 |  | 0.5 |  | 0.5
|  | 55 |  |  | FS_LTE_LIGHT_CON | 2017-06-17 | 100 | 5 | 5 |  |  |  |  | 2 | 2 | 3 | 3
|  |  | 20% |  | FS_eV2XARC | 2018-09-01 | 20.625 | 16 | 3.3 | [8 empty] | 2 | 2.3 | 2 | 1 |  |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
|  |  | 10% |  | FS_ATSSS | 2018-09-17 | 10.2308 | 13 | 1.33 | [10 empty] | 1 | 1.33 |  |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
|  |  | 15% |  | FS_5WWC | 2018-06-17 | 10.2308 | 13 | 1.33 | [10 empty] | 1 | 1.33 |  |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
|  |  | 20% |  | FS_Parlos | 2017-12-17 | 33.3333 | 3 | 1 | [10 empty] | 1 | 1 |  |  |  |  | 1 |  | 1
[5 empty] | FS_ENTRADE | 2018-09-01 | 0 | 6 | 0 | [16 empty] | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
[5 empty] | FS_eNA | 2018-09-01 | 0 | 11 | 0 | [16 empty] | 1 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
[5 empty] | FS_CIoT_5G | 2018-09-01 | 0 | 23 | 0 | [16 empty] | 3 |  | 4 |  | 4 |  | 4 |  | 4 |  | 4
[5 empty] | FS_ETSUN | 2018-09-01 | 0 | 11 | 0 | [16 empty] | 1 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
[5 empty] | TEI PtP SGI tunnel | [16 empty] | 0.5 | 0.5
TEI DCN-ID to RAN
[5 empty] | 4242 xMB for group | [18 empty] | 0.5
[5 empty] | 4731 data allowance | [16 empty] | 0.5 | 0.5 | 0.5
[5 empty] | 4218 bSRVCC | [16 empty] | 0.5
[5 empty] | QCI Override 8032 | [18 empty] | 0.5
[5 empty] | ID Attestation 6919 | [18 empty] | 1
[5 empty] | Maint 5.1 / 6.1 |  |  |  | 27.2 | 4 | 4 | 4 | 4 | 3 | 4 | 3.33 | 3.7 | 3 | 4 | 3 | 3 | 3 | 4.5 | 3 |  | 25 |  | 25 |  | 20 |  | 20
[5 empty] | Maint 5.2 / 6.2 |  |  |  | 4.16 | 1 | 1 | 1 |  | 1 | 1 | 1.33 | 1.33 | 1 | 0.5 | 1 | 0.33 | 1 | 0 | 0.25 |  | 1 |  | 1 |  | 1 |  | 1
[5 empty] | Maint 5.3 / 6.3 |  |  |  | 2.7 |  |  | 1 | 0.5 | 1 | 1 | 1 | 0.7 | 1 | 0.5 | 1 |  | 1 | 0 | 0.25 |  | 1 |  | 1 |  | 1 |  | 1
[5 empty] | Maint 5.4 / 6.4 |  |  |  | 4.55 |  |  | 1 | 1.5 | 1 | 0.7 | 1 | 1 | 1 | 1 | 1 | 0.1 | 1 | 0.25 | 0.5 |  | 1 |  | 1 |  | 1 |  | 1
[5 empty] | TEI15 3GPP acc |  |  |  | 0
[5 empty] | TEI15 PCC/QoS |  |  |  | 0.5 | [8 empty] | 0.5 | 0.5
TEI15 n3GPP
[5 empty] | TEI15 IMS/rel. |  |  |  | 0.5 | [8 empty] | 1.5 | 0.5
[5 empty] | sum |  |  |  |  | 22 | 28 | 28 | 35 | 36 | 41.75 | 43.98 | 44.39 | 41.5 | 45.3 | 43 | 45.92 | 36 | 45.05 | 46 | 0 | 41.5 | 0 | 44.5 | 0 | 38 | 0 | 38 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0
46 is the absolute maximum!