## Sheet4
[5 empty] | Key -> | Done | On target | Behind target and No External dependencies | Behind target and external dependencies | At risk
Study | RAN impacts/dependencies | % complete |  |  | Key Issue Conclusions
|  | 2020-06-01 | 2020-09-01 | 2020-10-01 | KI #1 | KI #2 | KI #3 | KI #4 | KI #5 | KI #6 | KI #7 | KI #8 | KI #9 | KI #10 | KI #11 | KI #12 | KI #13 | KI #14 | KI #15 | KI #16 | KI #17 | KI # | KI #19 | KI #20 | KI #21
5MBS | Many KI's could have RAN impact/dependency | 50% | 65% | 85% | Key Issue Conclusions KI #1: Interim (partially dep on RAN); Key Issue Conclusions KI #2: None (one soln); Key Issue Conclusions KI #3: Solved in other KI; Key Issue Conclusions KI #4: Interim; Key Issue Conclusions KI #5: N/A; Key Issue Conclusions KI #6: Interim; Key Issue Conclusions KI #7: Interim; Key Issue Conclusions KI #8: N/A; Key Issue Conclusions KI #9: None
ATSSS_Ph2 | None (but is a dependency on IETF) | 35% | 70% | 85% | Key Issue Conclusions KI #1: Interim; Key Issue Conclusions KI #2: Interim; Key Issue Conclusions KI #3: Interim
eNS_Ph2 |  | 55% | 75% | 85% | Key Issue Conclusions KI #1: Interim, SoH needed; Key Issue Conclusions KI #2: Interim, SoH needed; Key Issue Conclusions KI #3: SoH needed, dep on RAN; Key Issue Conclusions KI #4: Interim, dep on 1, 2, 3, 5; Key Issue Conclusions KI #5: SoH needed, dep on RAN?; Key Issue Conclusions KI #6: None May dep on CT1/GSMA; Key Issue Conclusions KI #7: Interim, dep on RAN; Key Issue Conclusions KI #8: None, dep on SA1, CT1
eNPN | Some solutions have RAN impacts | 55% | 75% | 88% | Key Issue Conclusions KI #1: technically endorsed, dep on SA1, SA3, RAN; Key Issue Conclusions KI #2: Interim, dep on SA1, RAN; Key Issue Conclusions KI #3: Interim, dep on SA3, RAN; Key Issue Conclusions KI #4: Interim, dep on SA3, RAN
UAS_ID | One solution (#8) proposes porting to NR the LTE aerial features. | 50% | 70% | 85% | Key Issue Conclusions KI #1: Interim; Key Issue Conclusions KI #2: Interim; Key Issue Conclusions KI #3: N/A; Key Issue Conclusions KI #4: Interim; Key Issue Conclusions KI #5: Interim; Key Issue Conclusions KI #6: Interim; Key Issue Conclusions KI #7: Interim
eNA_Ph2 | None | 55% | 70% | 85% | Interim | Interim | N/A | Interim, one soln, align with SA5 | N/A | N/A | None, one soln | Interim, align with SA3, SA4 | None | Interim | Part interim, align with SA3 | Interim, align with SA5 | Interim | None, one solution | Interim, align with SA3 | Interim | None, one solution | None | Interim | Full | None, one soln
ProSe | Relay solutions have RAN impact | 65% | 70% | 85% | Key Issue Conclusions KI #1: Interim except for DDNMF; Key Issue Conclusions KI #2: Interim; Key Issue Conclusions KI #3: Interim, dep on RAN and SA3; Key Issue Conclusions KI #4: None, dep on RAN; Key Issue Conclusions KI #5: SoH needed; Key Issue Conclusions KI #6: N/A; Key Issue Conclusions KI #7: None,dep on SA5; Key Issue Conclusions KI #8: Interim, align with other Kis
MUSIM | LS sent for feedback on some solutions | 60% | 80% | 84% | Key Issue Conclusions KI #1: Interim, SoH needed? RAN dep?; Key Issue Conclusions KI #2: None, RAN dep; Key Issue Conclusions KI #3: Interim, RAN dep
Enh_EC | None | 60% | 70% | 85% | Key Issue Conclusions KI #1: Full (some details tbd); Key Issue Conclusions KI #2: Interim; Key Issue Conclusions KI #3: Full (controversial); Key Issue Conclusions KI #4: N/A; Key Issue Conclusions KI #5: Full
IIoT | Co-ord needed on survival time, and possibly other co-ord depending on solutions chosen | 58% | 75% | 87% | Key Issue Conclusions KI #1: Interim; Key Issue Conclusions KI #2: Interim; Key Issue Conclusions KI #3: (A) Interim (B) Interim; Key Issue Conclusions KI #4: N/A; Key Issue Conclusions KI #5: Interim, dep on RAN
eV2XARC_Ph2 | Sidelink DRX operation | 25% | 70% | 85% | Key Issue Conclusions KI #1: Interim, dep on RAN