## Slide 1: SA WG2 Status report for 5WWC
Laurent Thiébaut
Nokia

## Slide 2
during the April meeting, concentrate on solutions (new and updated). New solution are not expected after April meeting . (Only solution updates or solution merges are expected after this meeting).
In May agree to a SID update shifting the TR approval to December plenary due to the need to get feedback from BBF/Cablelabs (feedback to be requested from August meeting when solutions are completed)
Complete all solutions in August (and send TR for information)
August meeting conclude on KI 2 (slicing for Non 3GPP)(evaluation and conclusions). Normative work for KI2 in October
November meeting conclude on KI 1 (different handling of devices) (evaluation and conclusions using BBF/CableLabs feedback). Normative work for KI1 in Q1 2023
Prior to the August (November) meeting have about KI 2 (KI1)
  in 2 first weeks of June a moderated email discussion
  3rd or 4th week of June a conf call where we can exchange on the Evaluation of the solutions and on the road to conclusions
At the August/November meeting, only one document will be taken as baseline for evaluation and conclusions. The other documents being for TR update will be for solution updates (August).
Overall plan

## Slide 3
General
  New solutions added in Q2. New solution are not expected anymore
  Complete all solutions in August
  August meeting conclude on KI 2 (slicing for Non 3GPP)(evaluation and conclusions). Normative work for KI2 in October
  November meeting conclude on KI 1 (different handling of devices) (using BBF/CableLabs feedback). Normative work for KI1 in Q1 2023
RAN dependencies:
  None (the SID has no RAN impacts)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5WWC_Ph2 | Study on the support for 5WWC, | 25% > 60% | Sep  Dec, 22 | SP-211640  S2-2204899

## Slide 4
  RAN and SA3 impacts and dependencies:
  None for RAN and none determined yet for SA3
Contentious Issue:
  None
Focus for the Next Meeting (August):
  Complete all solutions in August
  August meeting conclude on KI 2 (slicing for Non 3GPP)(evaluation and conclusions). Normative work for KI2 in October
Overall Plan:
  See dedicated slide
Risks:
  KI completion in Q1 2023 (due to late feedback from BBF/CableLabs)