## Slide 1: Status report for 5GS Enhancement for Energy Efficiency and Energy Saving (EnergySys)
Jungshin Park (Samsung),
Konstantinos Samdanis (Lenovo)

## Slide 2: EnergySys Status after SA#107
  Progress since SA#107
  Discussion on CRs for maintenance of TS documents was continued
  44 Tdocs were submitted to SA2#168 (24 CRs and 2 LSs are handled, 17 CRs are agreed)
  WT#1: 17 CRs agreed, including corrections on Energy Information collection and exposure
  WT#2: 6 CRs related to BDT were not handled at the meeting
  Impacts and dependencies on other WGs
  None
  Contentious issues
  None
  Next steps:
  Continue CR discussion
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1050112 | 5GS Enhancement for Energy Efficiency and Energy Saving | EnergySys | 12/12/2024 | 100% | SP-241388 | 100% | CR for maintenance

## Slide 3: FS_EnergySys/EnergySys Work Plan
Total 12.5 TUs used
  8.5 TUs (= 6.5 TU + additional 2 TUs) for Study Phase
  4 TUs for Normative Work
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Oct 2023 | 1 | 1 | TR skeleton, scope, architectural assumptions, key issue discussion
SA2#160 | Nov 2023 | 1 | 1 | Continue discussion on Key Issues, start solution discussion
SA2#160AH-e | Jan 2024 | 1 | 1 | Start solution discussion, last meeting for Key Issue proposals
SA2#161 | Feb 2024 | 1.5 | 1.5 | Continue solution discussion, last meeting for new solution proposals
SA2#162 | Apr 2024 | 1 | 1 | Focus on solution updates, only unhandled new solution proposals from #161, start discussion on evaluation and conclusion
SA2#163 | May 2024 | 1 | 1 | Critical solution updates only, Complete study conclusion, Prepare a WID proposal for normative work based on conclusion
SA2#164 | Aug 2024 | 2 | 2 | Complete study conclusions, Submit a WID proposal to SA#105
SA2#165 | Oct 2024 | 2 | 2 | Start normative work: discuss general description for essential parts of the feature, focus on changes for TS 23.501
SA2#166 | Nov 2024 | 2.5 | 2 | Continue normative work: update texts for functional descriptions in TS 23.501/503, work on procedures in TS 23.502
 | Total | 13 | 12.5 | 

## Slide 4: Backup

## Slide 5: EnergySys Status at SA#107
  Progress since SA#105
  Discussion on CRs for maintenance of TS documents has been started
  The revised WID to discontinue the unfinished issues of Rel-19, based on decision at SA#106, is submitted to SA#107
  140 Tdocs were submitted to SA2#166AH and #167 (120 CRs and 2 LSs are handled, 27 CRs and 1 LS are agreed)
  Impacts and dependencies on other WGs
  1 LS to SA5 regarding energy information collection from OAM to EIF (S2-2501217);
  1 LS to RAN2/RAN3 regarding energy saving indication from CN to RAN (S2-2413034);
  Contentious issues
  None
  Next steps:
  Continue CR discussion
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1050112 | 5GS Enhancement for Energy Efficiency and Energy Saving | EnergySys | 12/12/2024 | 70% | SP-241388 | 100% | CR for maintenance

## Slide 6: EnergySys Status after SA2#167
  Progress since SA2#167
  Discussion on CRs for maintenance of TS documents has been started from SA2#166AH
  The revised WID is agreed to discontinue the unfinished issues of Rel-19, based on the decision at SA#106
  140 Tdocs were submitted to SA2#166AH and #167 (120 CRs and 2 LSs are handled, 27 CRs and 1 LS are agreed)
  WT#1: 18 CRs agreed, including corrections on Energy consumption calculate, EIF services, and per slice per UE energy information exposure
  WT#2: 9 CRs agreed, including corrections on Energy Saving indicator and notification to the PCF
  WT#3: This Work Task is excluded from the Rel-19 scope based on the decision at SA#106
  Impacts and dependencies on other WGs
  1 LS to SA5 regarding energy information collection from OAM to EIF (S2-2501217);
  1 LS to RAN2/RAN3 regarding energy saving indication from CN to RAN (S2-2413034);
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1050112 | 5GS Enhancement for Energy Efficiency and Energy Saving | EnergySys | 12/12/2024 | 70% | SP-241388 | 100% | CR for maintenance

## Slide 7: EnergySys Status after SA2#167
  Contentious issues
  None
  Next steps:
  Continue CR discussion
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1050112 | 5GS Enhancement for Energy Efficiency and Energy Saving | EnergySys | 12/12/2024 | 70% | SP-241388 | 100% | CR for maintenance

## Slide 8: EnergySys Status at SA#106
  Progress since SA#105
  The normative work started and is progressing
  147 Tdocs were submitted for SA2#165 and #166 (56 CRs are handled, 13 CRs are agreed)
  KI#1: 8 CRs agreed, a new NF (EIF) for energy info collection and its services are defined
  KI#2: 4 CRs agreed for Energy Saving indicator in UE Subscription Data, and BDT policy negotiation
  KI#3: 1 CR agreed for UP path adjustment
  Impacts and dependencies on other WGs
  An LS to RAN WG2 and RAN WG3 is sent to request feedback on the Energy Saving Indicator that may be provided from AMF to NG-RAN to assist energy saving at RAN
  Contentious issues
  None
  Next steps:
  Continue CR discussion
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1050112 | 5GS Enhancement for Energy Efficiency and Energy Saving | EnergySys | 12/12/2024 | 0% | SP-241388 | 70% | Normative work in progress

## Slide 9: EnergySys Status after SA2#166
  Progress since SA2#165
  Total 79 Tdocs were submitted (20 Tdocs handled), and 6 CRs agreed, 2 CRs postponed, 8 CRs noted, 3 LSs noted
  KI#1: 5 CRs agreed, including EIF service definition and energy information collection procedure
  KI#2: 1 CRs agreed for Energy Saving indicator in the UE Subscription Data
  KI#3: CRs on NF selection and UP Path Adjustment are noted
  Impacts and dependencies on other WGs
  An LS to RAN WG2 and RAN WG3 is sent to request feedback on the Energy Saving Indicator that may be provided from AMF to NG-RAN to assist energy saving at RAN
  Contentious issues
  None
  Next steps:
  Continue CR discussion
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1050112 | 5GS Enhancement for Energy Efficiency and Energy Saving | EnergySys | 12/12/2024 | 20% | SP-241388 | 70% | Normative work continued

## Slide 10: EnergySys Status after SA2#165
  Progress since SA2#164
  The meeting started the normative work, and focused on the CRs for general descriptions of the feature in TS 23.501
  68 Tdocs were submitted (36 Tdocs handled), and 7 CRs agreed, 2 CRs postponed, 1 CR noted
  KI#1: 3 CRs agreed, including functional description of a new NF and arch. reference model
  KI#2: 3 CRs agreed for subscription info. & policy control aspects, and BDT policy negotiation
  KI#3: 1 CR agreed for UP path adjustment; 1 CR postponed for NF selection
  Impacts and dependencies on other WGs
  None
  Contentious issues
  Standard method for calculation of energy consumption information
  Procedure for collection of energy consumption information (new service vs. reuse of NNWDAF)
  Next steps:
  SA2#166: Continue the normative work
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1050112 | 5GS Enhancement for Energy Efficiency and Energy Saving | EnergySys | 12/12/2024 | 0% | SP-241388 | 20% | Normative work started