## Slide 1: 5GSAT_Ph3_ARCH & FS_5GSAT_Ph3-ARC Status Report Integration of satellite components in the 5G architecture Phase 3
Hucheng Wang (CATT),
Ramon Ferrus (Sateliot)

## Slide 2
Progress since SA#107
  KI#1 (regenerative payload satellite access): 2 CRs are approved for maintenance
  KI#2 (S&F): 3 CRs are approved for maintenance
  RAN impacts and dependencies
  Yes, KI#1 depends on RAN3 conclusion, and KI#2 has RAN impact.
Contentious issues
  None
Next Step
  Maintenance
5GSAT_Ph3_ARCH status after SA#107
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040027 | Integration of satellite components in the 5G architecture Phase 3 | 5GSAT_Ph3_ARCH | 14/03/2025 | 100 | SP-240986 | 100 | closed
1010033 | Study on Integration of satellite components in the 5G architecture Phase 3 | FS_5GSAT_Ph3_ARCH | 21/06/2024 | 100 | SP-231199 | 100 | closed

## Slide 3
Progress since SA2#168
  KI#1 (regenerative payload satellite access): 2 CRs are approved for maintenance
  KI#2 (S&F): 3 CRs are approved for maintenance
  RAN impacts and dependencies
  Yes, KI#1 depends on RAN3 conclusion, and KI#2 has RAN impact.
Contentious issues
  None
Next Step
  Maintenance
5GSAT_Ph3_ARCH status after SA2#168
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040027 | Integration of satellite components in the 5G architecture Phase 3 | 5GSAT_Ph3_ARCH | 14/03/2025 | 100 | SP-240986 | 100 | closed
1010033 | Study on Integration of satellite components in the 5G architecture Phase 3 | FS_5GSAT_Ph3_ARCH | 21/06/2024 | 100 | SP-231199 | 100 | closed

## Slide 4
Work plan
5GSAT_Ph3_ARCH status after SA2#167
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Qct. 2023 | 1 | 1 | 
SA2#160 | Nov. 2023 | 1 | 1 | 
SA2#160E-AH | Jan. 2024 | 1.5 | 1.5 | 
SA2#161 | Feb. 2024 | 1 | 1 | 
SA2#162 | Apr. 2024 | 1.5 | 1.5 | 
SA2#163 | May. 2024 | 1 | 1 | 
SA2#164 | Aug. 2024 | 1.5 | 1.5 | Normative work starts
SA2#165 | Qct. 2024 | 2 | 2 | 
SA2#166 | Nov. 2024 | 2 | 2 | 
SA2#166-AH-e | Jan. 2025 | 1 | 2 | Contentious issues identified for KI#2&3
SA2#167 | Feb. 2025 | 1 | 2 | Completed
Used TU’s |  | 12.5 + 4 =16.5 |  |