## Slide 1: 5G_ProSe_Ph3 Status Report
Nassima Toumi (KPN N.V.)
Rapporteur

## Slide 2: 5G_ProSe_Ph3 status after SA2#168
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020066 | Study on Proximity-based Services in 5GS – Phase 3 | FS_5G_ProSe_Ph3 | 18/06/2024 | 100% | SP-231798 | 100% | 
1040030 | Proximity-based Services in 5GS – Phase 3 | 5G_ProSe_Ph3 | 18/12/2024 | 70% | SP-240988 | 100% | 
  Progress at SA2#168
  10 CRs to TS 23.304 and one CR to TS 23.502 were agreed.
  Additional corrections and clarifications for Layer 3 UE-to-Network and UE-to-UE Relay.
  Introduction of Layer 2 UE-to-Network Relay in TS 23.304 based on RAN progress.
  Impacts and dependencies on other WGs
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN.
Outstanding issues
  None.
Next steps
  Continue maintenance work.
  Further alignment with RAN for Layer 2 UE-to-Network Relay.

## Slide 3
Total 1.75 TUs for Normative Work
5G_ProSe_Ph3 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#164 | Aug 2024 | 1 | 0.75 | Normative work, finalize the TR conclusions
SA2#165 | Oct 2024 | 0 | 0 | -
SA2#166 | Nov 2024 | 0.5 | 1 | Finalize normative work, coordination with SA3
SA2#166-Ad Hoc-e | January 2025 | 1.5 | 1 | Maintenance work and alignments based on progress from other WGs.
SA2#167 | February 2025 | - | - | -
SA2#168 | April 2025 | 0.5 | 0.5 | Maintenance work and alignments based on progress from other WGs.
SA2#169 | May 2025 | - | - | -
 | Total | 1.5+2 | 1.75+1.5 | 

## Slide 4: Backup

## Slide 5: 5G_ProSe_Ph3 status after SA2#167
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020066 | Study on Proximity-based Services in 5GS – Phase 3 | FS_5G_ProSe_Ph3 | 18/06/2024 | 100% | SP-231798 | 100% | 
1040030 | Proximity-based Services in 5GS – Phase 3 | 5G_ProSe_Ph3 | 18/12/2024 | 70% | SP-240988 | 100% | Completed
  Progress at SA2#166AH-E
  38 T-docs were submitted, including 12 LSs, 2 discussion papers and 24 CRs.
  18 CRs to TS 23.304 and one CR to TS 23.502 were agreed.
  1 reply LS sent to RAN WG2 on relay discovery announcement.
  1 reply LS sent to SA WG3 on multi-hop U2N relay architecture aspects.
  1 LS OUT sent to RAN WGs 2 and 3 on Authorization information for Layer-2 multi-hop U2N relaying to NG-RAN.
  Progress at SA2#167
  Not on the agenda.
  Impacts and dependencies on other WGs
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN.
Outstanding issues
  None.
Next steps
  Continue maintenance work.
  Alignment with RAN for Layer 2 UE-to-Network Relay.

## Slide 6: 5G_ProSe_Ph3 status at SA#107
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020066 | Study on Proximity-based Services in 5GS – Phase 3 | FS_5G_ProSe_Ph3 | 18/06/2024 | 100% | SP-231798 | 100% | 
1040030 | Proximity-based Services in 5GS – Phase 3 | 5G_ProSe_Ph3 | 18/12/2024 | 70% | SP-240988 | 100% | Completed
  Progress since SA#106
  18 CRs to TS 23.304 and one CR to TS 23.502 were agreed.
  1 reply LS sent to RAN WG2 on relay discovery announcement.
  1 reply LS sent to SA WG3 on multi-hop U2N relay architecture aspects.
  1 LS OUT sent to RAN WGs 2 and 3 on Authorization information for Layer-2 multi-hop U2N relaying to NG-RAN.
  Impacts and dependencies on other WGs
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN.
Outstanding issues
  None.
Next steps
  Continue maintenance work.
  Alignment with RAN for Layer 2 UE-to-Network Relay.

## Slide 7
Total 1.75 TUs for Normative Work
5G_ProSe_Ph3 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#164 | Aug 2024 | 1 | 0.75 | Normative work, finalize the TR conclusions
SA2#165 | Oct 2024 | 0 | 0 | -
SA2#166 | Nov 2024 | 0.5 | 1 | Finalize normative work, coordination with SA3
SA2#166-Ad Hoc-e | January 2025 | 1.5 | 1 | Maintenance work and alignments based on progress from other WGs.
SA2#167 | February 2025 |  |  | 
SA2#168+169 | Q2 2025 |  |  | 
 | Total | 1.5+1.5 | 1.75+1 | 

## Slide 8: 5G_ProSe_Ph3 status after SA2#166
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020066 | Study on Proximity-based Services in 5GS – Phase 3 | FS_5G_ProSe_Ph3 | 18/06/2024 | 100% | SP-231798 | 100% | 
1040030 | Proximity-based Services in 5GS – Phase 3 | 5G_ProSe_Ph3 | 18/12/2024 | 70% | SP-240988 | 100% | Completed
  Progress since SA2#165
  46 T-docs were submitted, 13 were handled.
  Agreed 12 CRs to TS 23.304.
  Normative text has been added to support QoS and relay re-selection for U2U and U2N relay.
  Resolved remaining ENs and added missing common identifiers for U2U relay.
  One reply LS sent to CT1 to clarify the relationship between single-hop and multi-hop capabilities and policies, and IP address allocation in U2N relay.
  Impacts and dependencies on other WGs
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN.
Outstanding issues
  None.
Next steps
  Start maintenance work.
  Alignment with RAN for Layer 2 UE-to-Network Relay.

## Slide 9: 5G_ProSe_Ph3 status at SA#106
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020066 | Study on Proximity-based Services in 5GS – Phase 3 | FS_5G_ProSe_Ph3 | 18/06/2024 | 100% | SP-231798 | 100% | 
1040030 | Proximity-based Services in 5GS – Phase 3 | 5G_ProSe_Ph3 | 18/12/2024 | 70% | SP-240988 | 100% | Completed
  Progress since SA#105
  Agreed 12 CRs to TS 23.304.
  All work tasks in the WID were captured in TS 23.304:
    WT#1: Enhance ProSe to support multi-hop UE-to-Network Relay.
    WT#2: Enhance ProSe to support Layer 3 multi-hop UE-to-UE Relays for IP PDU type based on IETF MANET Protocol.
    WT#3: Enhance ProSe to support Layer 3 multi-hop UE-to-UE Relays for Ethernet and Unstructured PDU type based on Release 18 PC5 protocol.
  Support for Multi-hop ProSe discovery and selection, communication, QoS and relay re-selection for Layer 3 UE-to-UE and UE-to-Network relay.
  One reply LS sent to CT1 to clarify the relationship between single-hop and multi-hop capabilities and policies, and IP address allocation in U2N relay.
  Impacts and dependencies on other WGs
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN.
Outstanding issues
  None.
Next steps
  Start maintenance work.
  Alignment with RAN for Layer 2 UE-to-Network Relay.

## Slide 10
Total 1.75 TUs for Normative Work
5G_ProSe_Ph3 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#164 | Aug 2024 | 1 | 0.75 | Normative work, finalize the TR conclusions
SA2#165 | Oct 2024 | 0 | 0 | -
SA2#166 | Nov 2024 | 0.5 | 1 | Finalize normative work, coordination with SA3
SA2#166-Ad Hoc-e | January 2025 |  |  | Maintenance work and alignments based on progress from other WGs.
SA2#167 | February 2025 |  |  | Maintenance work and alignments based on progress from other WGs.
 | Total | 1.5 | 1.75 | 

## Slide 11: FS_5G_ProSe_Ph3 status after SA2#164
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020066 | Study on Proximity-based Services in 5GS – Phase 3 | FS_5G_ProSe_Ph3 | 18/06/2024 | 90% | SP-231798 | 100% | Progressed
  Progress in SA2#164
  2 pCRs were approved to update the KI#2 conclusion.
  TR 23.700-03 v.1.1.0 was created based on approved contributions.
  Impacts and dependencies on other WGs
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN.
  Input required from SA3 on security related questions for different solutions.
Next steps
  Send TR to SA plenary for approval.

## Slide 12: 5G_ProSe_Ph3 status after SA2#164
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040030 | Proximity-based Services in 5GS – Phase 3 | 5G_ProSe_Ph3 | 18/12/2024 | 0% | SP-240988 | 70% | Progressed
  Progress since SA2#164
  10 CRs agreed.
  Normative text has been added to support multi-hop UE-to-Network and UE-to-UE relay.
  Impacts and dependencies on other WGs
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN.
  Input required from SA3 on security related questions.
Next steps
  Continue normative work.

## Slide 13
Total 3.5 TUs
  2 TUs for Study Phase
  1.5 TUs for Normative Work
5G_ProSe_Ph3 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 | 0.5 | TR Skeleton, TR Scope, Key Issues, Arch Assumptions
SA2#161 | Feb 2024 | 0.5 | 0.5 | Solutions
SA2#162 | Apr 2024 | 0.5 | 0.5 | New solution aspects/Solution Updates, Evaluations, Conclusions
SA2#163 | May 2024 | 0.5 | 0.5 | Evaluations, Conclusions
SA2#164 | Aug 2024 | 1 | 1 | Normative work, finalize the TR conclusions
SA2#165 | Oct 2024 | 0 |  | -
SA2#166 | Nov 2024 | 0.5 |  | Normative work, coordination with RAN and SA3 if needed
 | Total | 3.5 |  |