## Slide 1: FS_5GSAT_Ph4_ARC Status Report Study on integration of satellite components in the 5G architecture Phase 4
Hucheng Wang (CATT),
Relja Djapic (TNO)

## Slide 2
5GSAT_Ph3_ARCH status after SA#107
Progress since SA2#107
  5 pCRs are approved, including TR skeleton, TR scope, Architectural assumptions (2 pCRs), and a KI for WT-1
  RAN impacts and dependencies
  Yes, KI#1 and KI#3 have RAN impact, KI#2 may have dependency on RAN conclusion.
Contentious issues
  None
Next Step
  Continuing solution discussion.
  Introducing KI and interim agreements for WT-2.2
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070011 | Study on Integration of satellite components in the 5G architecture Phase 4 | FS_5GSAT_Ph4_ARC | 12/12/2025 | 0 | SP-250400 | 10 | In progress

## Slide 3
Progress since SA2#168
  5 pCRs are approved, including TR skeleton, TR scope, Architectural assumptions (2 pCRs), and a KI for WT-1
  RAN impacts and dependencies
  Yes, KI#1 and KI#3 have RAN impact, KI#2 may have dependency on RAN conclusion.
Contentious issues
  None
Next Step
  Continuing solution discussion.
  Introducing KI and interim agreements for WT-2.2
5GSAT_Ph3_ARCH status after SA2#168
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070011 | Study on Integration of satellite components in the 5G architecture Phase 4 | FS_5GSAT_Ph4_ARC | 12/12/2025 | 0 | SP-250400 | 10 | In progress

## Slide 4
5GSAT_Ph3_ARCH status after SA2#168
Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#168 | Apr. 2025 | 1 | 1 | 1 TU for TR scope, TR skeleton, Assumption, KI definition. Start solution discussion
SA2#169 | May. 2025 | 2 |  | Last chance for KI update, continue solution discussion
SA2#170 | Aug. 2025 | 1.5(2) |  | Last meeting for new solution, and start solution evaluation
SA2#171 | Qct. 2025 | 1(2) |  | Last meeting for solution update, continue solution evaluation and try to conclude topics with common understanding Submit WI to SA2 for information
SA2#172 | Nov. 2025 | 1(1.5) |  | Conclude the study Approve the WI in SA2.
SA2#173 | Feb. 2025 | 2 |  | Normative work starts
SA2#174 | Apr. 2025 | 2 |  | 
SA2#175 | May. 2025 | 1.5(2.5) |  | 
SA2#176 | Aug. 2025 | 1(2) |  | 
Used TU’s |  |  |  | 
NOTE: depending on prioritization in SA#108, WT-2.1 might start in Q3. |  |  |  |