## Slide 1: Status report for EnergySys Phase 2
Konstantinos Samdanis (Lenovo)
Zhuoyi Chen (China Telecom)

## Slide 2: FS_EnergySys_Ph2 Status at SA#168
  Progress – 13 pCRs Agreed
  Approved TR skeleton, scope and architecture assumptions
  Approved description of KIs for all WTs in SID
  Approved 1 solution related to KI1
  Approved 6 solutions related to KI2
  Impacts and dependencies on other WGs
  Dependency on SA5 related to new performance measurements regarding renewable energy.
  Dependency on RAN WGs regarding new performance measurements.
  Contentious issues
  What “accurate enough“ means in terms of energy related measurements in the approved SID? How it can be defined for Rel-20?
  Next steps:
  Try to agree on the notion of accuracy related to energy related measurements for Rel-20.
  Encourage new solutions for KI 1
  Continue to handle new solutons for KI 2 and KI 3
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070058 | New SID on Energy Efficiency and Energy Saving Phase 2 | FS_EnergySys_Ph2 | 12/12/2024 | 0% | SP-250417 | 20% | 

## Slide 3: FS_EnergySys_Ph2 Work Plan
Meeting | Date | Planned TUs | Actual Used TUs | Action plan
SA2#168 | Apr. 2025 | 1 | 1 | TR skeleton, scope, Terms, Architectural assumptions & Requirements Key Issues for all WTs.
SA2#169 | May 2025 | 2 |  | Key Issue updates (if necessary), New solutions for approved Key Issues.
SA2#170 | Aug. 2025 | 1 |  | New solutions and solution updates. Last meeting for new solutions.
SA#109 | Sep. 2025 | - | - | For information
SA2#171 | Oct. 2025 | 1 |  | Solution updates. Evaluation and conclusion.
SA2#172 | Nov.2025 | 1 |  | Conclusion.
SA#110 | Dec 2025 | - | - | For Approval
 | Total | 6 | 1 |