## Slide 1: Rel-20 AmbientIoT_Ph2_ARC Status Report
Runze Zhou (Huawei), Fei Lu (OPPO)
(Rapporteurs)

## Slide 2: FS_AmbientIoT_Ph2_ARC Status after SA2#170
  Progress since SA#109
  Key issue 1: (interim) conclusion reached for architecture, protocol stack, radio resource allocation. Partial conclusion reached for UE reader authorization and revocation, UE reader selection. Several FFS remain.
  Key issue 2: 15 new solutions are approved
  TR 23.700-30 v.0.2.0 is available.
  Impacts and dependencies on other WGs
  Some solutions include editor’s notes need coordination with RAN and SA3
Outstanding issues
  Key issue 1 has already used the 0.5 TU planned in the SID, and not been completed yet.
Next steps
  November meeting: start and prioritize the key issue 2 conclusion, and no discussion on key issue 1
  February meeting: finalize key issue 1 and key issue 2 conclusions, key issue 1 will focus on essential features and have limited discussion time.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1080063 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT_Ph2_ARC | 10/03/2026 | 15% | SP-250834 | 50% | 

## Slide 3
FS_AmbientIoT_Ph2_ARC work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#170 | Aug 2025 | 1 | 1 | Finalize scope, architecture assumptions and requirements, and key issues Solution for WT#2 Solution for WT#1 (only for information)
SA2#171 | Oct 2025 | 1.5 | 1.5 | Key issue 1: interim conclusions and conclusions Key issue 2: continue solution discussion, interim conclusions
SA2#172 | Nov 2025 | 1 |  | start and prioritize the key issue 2 conclusion no discussion on key issue 1
SA2#173 | Feb 2025 | 1 |  | finalize key issue 1 and key issue 2 conclusions, key issue 1 will focus on essential features and have limited discussion time
Total TU | Total | 4.5 | 2.5 | 

## Slide 4: BACKUP

## Slide 5: FS_AmbientIoT_Ph2_ARC Status after SA2#170
  Progress since SA#108
  Overall work plan has been discussed in the conference call at Aug 12th .
  TR 23.700-30 v.0.1.0 is available.
  64 contributions were submitted, 10 contributions agreed (including TR skeleton, scope, architecture and assumptions, key issues for WT#1 and WT#2, 4 solutions for key issue#2).
  Impacts and dependencies on other WGs
  Some solutions include editor’s notes need coordination with RAN
Outstanding issues
  None.
Next steps
  Start interim conclusion and conclusion for key issue 1
  Continue solution discussion for key issue 2
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1080063 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT_Ph2_ARC | 10/03/2026 | 0 | SP-250834 | 15% | 

## Slide 6: FS_AmbientIoT_Ph2_ARC Status at SA#109
  Progress since SA#108
  Overall work plan has been discussed in the conference call at Aug 12th .
  TR 23.700-30 v.0.1.0 is available.
  64 contributions were submitted, 10 contributions agreed (including TR skeleton, scope, architecture and assumptions, key issues for WT#1 and WT#2, 4 solutions for key issue#2).
  Impacts and dependencies on other WGs
  Some solutions include editor’s notes need coordination with RAN.
Outstanding issues
  None.
Next steps
  Start interim conclusions and conclusions for key issue 1.
  Continue solution discussions for key issue 2
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1080063 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT_Ph2_ARC | 10/03/2026 | 0 | SP-250834 | 15% |