## Slide 1: Status report for EnergySys Phase 2
Konstantinos Samdanis (Lenovo)
Zhuoyi Chen (China Telecom)

## Slide 2: FS_EnergySys_Ph2 Status at SA2#172
  Progress since SA2#171
  Approved 4 pCRs, complete final conclusion per each KI
  Approved 2 LSs, one for RAN 2 related to AQP and other to SA5 related to charging
  TR 23.700-67 (v1.2.0) is ready to plenary for approval
  Impacts and dependencies on other WGs
  Dependency on SA5 related to renewable energy.
  Dependency on RAN related to AQP
  Dependency on CT4 related to NF profile enhancements
  Contentious issues
  None.
  Next steps:
  Start normative work.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070058 | New SID on Energy Efficiency and Energy Saving Phase 2 | FS_EnergySys_Ph2 | 12/12/2025 | 95% | SP-250417 | 100% | 

## Slide 3: FS_EnergySys_Ph2 Status at SA#110
  Progress since SA#109
  Approved 8 pCRs, complete interim principle and final conclusion per each KI.
  Approved 3 LSs, one for RAN 2 related to AQP, one to 1 LS to SA5 related to the support of renewable energy and one to SA5 related to charging
TR 23.700-67 (v1.2.0) for approval
  Impacts and dependencies on other WGs
  Dependency on SA5 related to renewable energy.
  Dependency on RAN related to AQP
  Dependency on CT4 related to NF profile enhancements
  Contentious issues
  None.
  Next steps:
  Start normative work.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070058 | New SID on Energy Efficiency and Energy Saving Phase 2 | FS_EnergySys_Ph2 | 12/12/2025 | 85% | SP-250417 | 100% | 

## Slide 4: FS_EnergySys_Ph2 Work Plan
Meeting | Date | Planned TUs | Actual Used TUs | Action plan
SA2#168 | Apr. 2025 | 1 | 1 | TR skeleton, scope, Terms, Architectural assumptions & Requirements Key Issues for all WTs.
SA2#169 | May 2025 | 2 | 2 | Key Issue updates (if necessary), New solutions for approved Key Issues.
SA2#170 | Aug. 2025 | 1 | 1 | New solutions and solution updates. Last meeting for new solutions.
SA#109 | Sep. 2025 | - | - | For information
SA2#171 | Oct. 2025 | 1 | 1 | Solution updates. Evaluation and conclusion.
SA2#172 | Nov.2025 | 1 | 1 | Conclusion.
SA#110 | Dec 2025 | - | - | For Approval
 | Total | 6 | 6 |