## Slide 1: FS_AIML_CN_Ph2 Status Report
vivo (Rapporteur) Samsung (Rapporteur)

## Slide 2: FS_AIML_CN_Ph2 status after SA#109
General:
  92 contributions were submitted, 20 contributions agreed.
    KI#1: 1 LS out on AI/ML UE sided data collection, 1 KI#1 conclusion, 1 terminology definition, 6 solutions update. some interim agreements reached, still 20 ENs are for further consideration, which are listed in the conclusions clause.
    KI#2: 1 KI#2 UC#1 conclusion, 1 KI#2 UC#2 conclusion, 1 reducing reporting load, 6 solutions updates and the study for KI#2 is 100% concluded.
  5.5 TU used and 0 TU left for the Study Phase.
Impacts and dependencies on other WGs:
  RAN impacts or dependencies identified for Key Issue #1
  Potential user consent and privacy enhancements are under SA3 scope, then SA2 may need to align with SA3. This study considers user consent and privacy as currently defined in SA2 specifications
Contentious Issue:
  None.
Next steps:
  For KI#1, wait for RAN/RAN2 response providing feedback on whether Option 2 UP is selected before starting normative work
  Normative work for KI#2
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070013 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML)_Ph2 | FS_AIML_CN_Ph2 | 09/12/2025 | 70% | SP-250810 | 89% | 

## Slide 3: FS_AIML_CN_Ph2 status after SA2#172 (1/2)
General:
  46 contributions were submitted, 7 contributions agreed.
    KI#1: 1 LS out on AI/ML UE sided data collection, 1 KI#1 conclusion, 1 solution update. some interim agreements reached, still 20 ENs are for further consideration, which are listed in the conclusions clause.
    KI#2: 1 KI#2 UC#1 conclusion, 1 KI#2 UC#2 conclusion, 1 reducing reporting load, 1 solution updates and the study for KI#2 is 100% concluded.
  5.5 TU used and 0 TU left for the Study Phase.
Impacts and dependencies on other WGs:
  RAN impacts or dependencies identified for Key Issue #1
  Potential user consent and privacy enhancements are under SA3 scope, then SA2 may need to align with SA3. This study considers user consent and privacy as currently defined in SA2 specifications
Contentious Issue:
  None.
Next steps:
  For KI#1, wait for RAN/RAN2 response providing feedback on whether Option 2 UP is selected before starting normative work
  Normative work for KI#2
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070013 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML)_Ph2 | FS_AIML_CN_Ph2 | 09/12/2025 | 85% | SP-250810 | 89% | 

## Slide 4: FS_AIML_CN_Ph2 status after SA2#172 (2/2)
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#168 | Apr 2025 | 1 | 1 | TR 23.700-04 TR Skeleton, Arch Assumptions, scope, Initial KIs use case(s)
SA2#169 | May 2025 | 2 | 2 | Final KI/use case updates + Solutions, Attempt to close new Key Issue and new UC.
SA2#170 | Aug 2025 | 1 | 1 | Solution updates to resolve ENs (with higher priority) and last chance for new solution(s)
SA2#171 | Oct 2025 | 0.5 | 0.5 | Solution updates to resolve ENs and interim agreement No new solutions(s) unless very strong clarification/reason
SA2#172 | Nov 2025 | 1 | 1 | Interim agreement update and conclusion No new solutions(s) No solution updates unless very strong clarification/reason
SA2#173 | Feb 2026 | 1 |  | Normative work for KI#2
Total Planned TU’s 5 + 5 TUs
  5.5 TUs for Study Phase
  4.5 TUs for Normative Work
Note: for KI#1, SA2 discuss and decide next step once receiving RAN/RAN2’s feedback (on whether Option 2 UP is selected)

## Slide 5: Substantial Issues
Issue # | Description | Identified in | Resolution | Resolved in
- | - | - | - | -

## Slide 6: Annex
Status report after SA2#168/169/170

## Slide 7: FS_AIML_CN_Ph2 status after SA2#171 (1/2)
General:
  46 contributions were submitted, 13 contributions agreed.
    KI#1: 5 solution updates, 1 terminology definition, (1 interim agreement is postponed)
    KI#2: 5 solution updates, 2 interim agreement for UC#1 & UC#2 respectively.
  4.5 TU used and 0.5 TU left for the Study Phase.
Impacts and dependencies on other WGs:
  RAN impacts or dependencies identified for Key Issue #1.
  Potential user consent and privacy enhancements are under SA3 scope, then SA2 may need to align with SA3. This study considers user consent and privacy as currently defined in SA2 specifications.
Contentious Issue:
  None.
Next steps:
  Interim agreement update and conclusion.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070013 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML)_Ph2 | FS_AIML_CN_Ph2 | 09/12/2025 | 70 | SP-250810 | 85 | 

## Slide 8: FS_AIML_CN_Ph2 status after SA2#170 (1/2)
General:
  TR 23.700-04 v.0.3.0 was created based on approved contributions.
  47 contributions were submitted, 25 contributions agreed. (including 1 LS out to RAN 2 for KI#1, 5 new solutions, 17 solution updates and 2 interim conclusions for KT#1 and KI#2).
    KI#1: 1 LS out, 1 new solution, 13 solution updates, 1 interim conclusion
    KI#2: 4 new solutions, 4 solution updates, 1 interim conclusion
  4 TU used and 1 TU left for the Study Phase.
Impacts and dependencies on other WGs:
  RAN impacts or dependencies identified for Key Issue #1.
  Potential user consent and privacy enhancements are under SA3 scope, then SA2 may need to align with SA3. This study considers user consent and privacy as currently defined in SA2 specifications.
Contentious Issue:
  None.
Next steps:
  Solution updates to resolve ENs and interim agreement update.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070013 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML)_Ph2 | FS_AIML_CN_Ph2 | 09/12/2025 | 50 | SP-250810 | 70 | 

## Slide 9: FS_AIML_CN_Ph2 status after SA2#169 (1/2)
General:
  TR 23.700-04 v.0.2.0 was created based on approved contributions.
  50 contributions were submitted, 31 contributions agreed, 1 contributions merged. (including 1 LS out for AI/ML UE sided data collection, TR skeleton, architecture assumptions, solutions for KT#1 and KI#2).
  3 TU used and 2 TU left for the Study Phase.
Impacts and dependencies on other WGs:
  RAN impacts or dependencies identified for Key Issue #1.
  Potential user consent and privacy enhancements are under SA3 scope, then SA2 may need to align with SA3. This study considers user consent and privacy as currently defined in SA2 specifications.
Contentious Issue:
  None.
Next steps:
  Solution updates
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070013 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML)_Ph2 | FS_AIML_CN_Ph2 | 09/12/2025 | 20 | SP-250413 | 50 | 

## Slide 10: FS_AIML_CN_Ph2 status after SA2#168 (1/2)
General
  TR 23.700-04 v.0.1.0 was created based on approved contributions.
  66 contributions were submitted, 11 contributions agreed (including TR skeleton, scope, architecture assumptions, use cases for WT#2, key issues and solutions for WT#1).
  1 TU used and 4 TU left for the Study Phase.
2 Key Issues agreed for the study:
  Key Issue #1: Transfer of data over UP for UE data collection
  Key Issue #2: AI/ML-assisted user plane traffic pattern and behaviour analysis to support efficient performance of User Plane
Other WG dependencies
  RAN impacts or dependencies identified for Key Issue #1
  Potential user consent and privacy enhancements are under SA3 scope, then SA2 may need to align with SA3. This study considers user consent and privacy as currently defined in SA2 specifications.
Contentious Issue:
  None.
Focus of the Next Meeting (SA2#169):
  Handle solutions for all Key Issues
  New use case(s) for WT#2 will only be handled with very good justification
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070013 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML)_Ph2 | FS_AIML_CN_Ph2 | 09/12/2025 | 0 | SP-250413 | 20 |