## AgendaWithTdocAllocation_2021-0
Tdoc List |  |  | Ready!
20-01-2021 13:00 CET
Agenda | Topic | TDoc | Title | Notes | Source | Type | For | Avail | Treated | Decision | Wdrn | Replaced-by | Replaces
1 | Agenda and Meeting Objectives | S3‑210000 | Agenda |  | SA WG3 Chair | agenda |  | Yes | No | approved | No
|  | S3‑210002 | Process for SA3#102e meeting |  | SA WG3 Chair | other |  | Yes | No | available | No
2 | Meeting Reports | S3‑210001 | Report from SA3#101e meeting |  | MCC | report |  | Yes | No | approved | No
|  | S3‑210003 | Report from last SA |  | SA WG3 Chair | report |  | Yes | No | available | No
3 | Reports and Liaisons from other Groups | S3‑210048 | TCG progress - report from TCG rapporteur |  | InterDigital, Inc. | other | Information | Yes | No | available | No
|  | S3‑210033 | TC CYBER Activities |  | ETSI TC CYBER | LS in |  | Yes | No | available | No
|  | S3‑210006 | User location identification from Carrier Aggregation secondary cell activation messages |  | GSMA FSAG | LS in |  | Yes | No | available | No
|  | S3‑210302 | Reply LS on SLIC |  | Ericsson Limited | LS out | Approval | Yes | No | available | No
|  | S3‑210293 | Reply LS on User location identification from Carrier Aggregation secondary cell activation messages |  | HUAWEI TECHNOLOGIES Co. Ltd. | LS out | Approval | Yes | No | available | No
|  | S3‑210013 | Independent evaluation of SNOW V |  | ETSI SAGE | LS in |  | Yes | No | available | No
|  | S3‑210014 | 256-bit algorithms based on SNOW 3G or SNOW V |  | ETSI SAGE | LS in |  | Yes | No | available | No
|  | S3‑210095 | Choice of cryptographic algorithm in 256-bit Milenage |  | ETSI SAGE | LS in |  | Yes | No | available | No
|  | S3‑210530 | Notes: SAGE/SA3 2nd joint conference call on the 256-bit topics |  | NTT DOCOMO INC. | other | Information | Yes | No | available | No
|  | S3‑210007 | LS on broadcasting gNB ID length in system information block |  | R3-207226 | LS in |  | Yes | No | available | No
|  | S3‑210008 | Reply LS on MuDe functionality |  | S1-204380 | LS in |  | Yes | No | available | No
|  | S3‑210010 | LS Response on Support of L2TP in PFCP |  | S2-2009331 | LS in |  | Yes | No | available | No
|  | S3‑210015 | LS on SG17 new work item 'Security Methodology for Zero-Touch Massive IoT Deployment' |  | ITU-T SG17 | LS in |  | Yes | No | available | No
|  | S3‑210016 | LS on Use of Inclusive Language in 3GPP |  | SP-201143 | LS in |  | Yes | No | available | No
|  | S3‑210023 | Reply LS on AUSF/UDM discovery based on SUCI information |  | S2-2009207 | LS in |  | Yes | No | available | No
|  | S3‑210024 | LS on Support of L2TP on SGi/N6 with Control and User Plane Separation |  | C4-205478 | LS in |  | Yes | No | available | No
|  | S3‑210019 | LS on propagation of user consent related information during Xn inter-PLMN handover |  | R3-204378 | LS in |  | No | Yes | withdrawn | Yes
|  | S3‑210031 | LS on Security Requirements for Sidelink/PC5 Relays |  | S2-2004750 | LS in |  | No | Yes | withdrawn | Yes
4 | Work areas
4.1 | Security aspects of 5G System - Phase 1 (Rel-15) | S3‑210065 | Error code details - Resolving ed note in 13.2.2.6 |  | Nokia, Nokia Shanghai Bell | CR | Agreement | No | Yes | withdrawn | Yes |  | S3‑201797
|  | S3‑210074 | Error code details - Resolving ed note in 13.2.2.6 |  | Nokia, Nokia Shanghai Bell | CR | Agreement | Yes | No | available | No |  | S3‑201797
|  | S3‑210075 | Error code details - Resolving ed note in 13.2.2.6 |  | Nokia, Nokia Shanghai Bell | CR | Agreement | Yes | No | available | No
|  | S3‑210102 | Optional registration of NF Service Consumer to NRF |  | Nokia, Nokia Shanghai Bell, Huawei, HiSilicon | CR |  | Yes | No | available | No
|  | S3‑210103 | Optional registration of NF Service Consumer to NRF |  | Nokia, Nokia Shanghai Bell, Huawei, HiSilicon | CR |  | Yes | No | available | No
|  | S3‑210104 | Optional registration of NF Service Consumer to NRF |  | Nokia, Nokia Shanghai Bell, Huawei, HiSilicon | CR |  | Yes | No | available | No
|  | S3‑210238 | Correction to the access token storage in NF service consumer |  | Huawei, HiSilicon | CR | Approval | Yes | No | available | No
|  | S3‑210239 | Correction to the access token storage in NF service consumer |  | Huawei, HiSilicon | CR | Approval | Yes | No | available | No
|  | S3‑210240 | Correction to the access token storage in NF service consumer |  | Huawei, HiSilicon | CR | Approval | Yes | No | available | No
|  | S3‑210339 | Typo correction in clause 6.9.9.4 |  | Xidian University | CR |  | Yes | No | available | No
|  | S3‑210382 | Align the JSON format on encryption IE with CT4 in Rel15 |  | Huawei, HiSilicon, Nokia, Nokia Shanghai Bell | CR | Approval | Yes | No | available | No
|  | S3‑210383 | Mirror: align the JSON format on encryption IE with CT4 in Rel16 |  | Huawei, HiSilicon, Nokia, Nokia Shanghai Bell | CR | Approval | Yes | No | available | No
|  | S3‑210384 | Mirror: align the JSON format on encryption IE with CT4 in Rel17 |  | Huawei, HiSilicon, Nokia, Nokia Shanghai Bell | CR | Approval | Yes | No | available | No
|  | S3‑210385 | Adding the security requirement with encBlockIndex in Rel15 |  | Huawei, HiSilicon, Nokia, Nokia Shanghai Bell | CR | Approval | Yes | No | available | No
|  | S3‑210386 | Mirror Adding the security requirement with encBlockIndex in Rel16 |  | Huawei, HiSilicon, Nokia, Nokia Shanghai Bell | CR | Approval | Yes | No | available | No
|  | S3‑210387 | Mirror Adding the security requirement with encBlockIndex in Rel17 |  | Huawei, HiSilicon, Nokia, Nokia Shanghai Bell | CR | Approval | Yes | No | available | No
|  | S3‑210395 | Clarification on PLMN ID verification in Rel15 |  | Huawei, HiSilicon | CR | Approval | Yes | No | available | No
|  | S3‑210396 | Clarification on PLMN ID verification in Rel16 |  | Huawei, HiSilicon | CR | Approval | Yes | No | available | No
|  | S3‑210397 | Discussion paper on TAU reject issue during MME handover |  | Huawei, HiSilicon | discussion | Discussion | Yes | No | available | No
|  | S3‑210398 | LS on TAU reject issue during MME handover |  | Huawei, HiSilicon | LS out | Approval | Yes | No | available | No
|  | S3‑210413 | OAuth 2.0 client registration and NF Service registration |  | Ericsson | discussion | Discussion | Yes | No | available | No
|  | S3‑210467 | Typo correction in clause 6.9.9.4 |  | Xidian University | CR |  | Yes | Yes | withdrawn | Yes
|  | S3‑210515 | Updated proposal to introduce draft-ietf-emu-rfc5448bis to TS 33.501 |  | Ericsson | discussion | Discussion | Yes | No | available | No |  | S3‑203322
|  | S3‑210532 | Typo correction in clause 6.9.4.4 |  | Xidian University | CR |  | Yes | No | available | No
|  | S3‑210545 | resolving ed note on protection policy mismatch |  | NTT DOCOMO INC. | CR |  | Yes | No | available | No
|  | S3‑210546 | Typo correction in clause 6.9.4.4 |  | Xidian University | CR |  | No | Yes | withdrawn | Yes
|  | S3‑210547 | Typo correction in clause 6.9.4.4 |  | Xidian University | CR |  | No | Yes | withdrawn | Yes
|  | S3‑210548 | Typo correction in clause 6.9.4.4 |  | Xidian University | CR |  | No | Yes | withdrawn | Yes
|  | S3‑210549 | Typo correction in clause 6.9.4.4 |  | Xidian University | CR |  | No | Yes | withdrawn | Yes
|  | S3‑210550 | Typo correction in clause 6.9.4.4 |  | Xidian University | CR |  | Yes | No | available | No
|  | S3‑210551 | resolving ed note on protection policy mismatch |  | NTT DOCOMO INC. | CR |  | Yes | No | available | No
|  | S3‑210552 | resolving ed note on protection policy mismatch |  | NTT DOCOMO INC. | CR | Agreement | Yes | No | available | No
4.2 | Security Assurance Specification for 5G (Rel-16) | S3‑210090 | gNB Cipher Security Policy Verification |  | Futurewei | CR | Agreement | Yes | No | available | No
|  | S3‑210091 | gNB Integrity Security Policy Verification |  | Futurewei | CR | Agreement | Yes | No | available | No
|  | S3‑210100 | SCAS Protection Policies - TBD updated |  | Nokia, Nokia Shanghai Bell | CR |  | Yes | No | available | No
|  | S3‑210101 | Protection policies test case |  | Nokia, Nokia Shanghai Bell, NTT Docomo, Huawei, HiSilicon | CR |  | Yes | No | available | No
|  | S3‑210364 | SCAS: Correction of incomplete test cases |  | Huawei, Hisilicon | CR | Approval | Yes | No | available | No
|  | S3‑210378 | Clarification on confidential IEs replacement handling in original N32-f message |  | Huawei, HiSilicon, Nokia, Nokia Shanghai Bell | CR | Approval | Yes | No | available | No
|  | S3‑210379 | Clarification on exposure of confidential IEs in N32-f message in TR 33.926 |  | Huawei, HiSilicon, Nokia, Nokia Shanghai Bell | CR | Approval | Yes | No | available | No
4.3 | Mission Critical security (Rel-16)
4.4 | Security Aspects of the 5G Service Based Architecture (Rel-16) | S3‑210096 | NF Service Consumer and Producer in Service Request Process |  | Nokia, Nokia Shanghai Bell | CR |  | Yes | No | available | No
|  | S3‑210097 | Access Token Misuse Prevention |  | Nokia, Nokia Shanghai Bell | CR |  | Yes | No | available | No
|  | S3‑210098 | NF Service Consumer and Producer in Service Request Process |  | Nokia, Nokia Shanghai Bell | CR |  | Yes | No | available | No
|  | S3‑210099 | Access Token Misuse Prevention |  | Nokia, Nokia Shanghai Bell | CR |  | Yes | No | available | No
|  | S3‑210241 | Correction to service request process in OAuth 2.0 based authorization rel16 |  | Huawei, HiSilicon | CR | Approval | Yes | No | available | No
|  | S3‑210242 | Correction to service request process in OAuth 2.0 based authorization rel17 |  | Huawei, HiSilicon | CR | Approval | Yes | No | available | No
|  | S3‑210347 | Clarification on the format of NF type in the NF certification |  | Huawei, Hisilicon | CR | Approval | Yes | No | available | No
|  | S3‑210381 | Resolving the EN on the authorization between SCPs |  | Huawei, HiSilicon | CR | Approval | Yes | No | available | No
|  | S3‑210411 | Corrections for the NRF token request service |  | Ericsson | CR | Agreement | Yes | No | available | No
|  | S3‑210412 | Corrections for the NRF token request service |  | Ericsson | CR | Agreement | Yes | No | available | No
4.5 | Authentication and key management for applications based on 3GPP credential in 5G (Rel-16) | S3‑210151 | AAnF checks AKMA service for UE and AF in clause 6.3 |  | ZTE Corporation | CR | Agreement | Yes | No | available | No
|  | S3‑210152 | AAnF selection in AF |  | ZTE Corporation | CR | Agreement | Yes | No | available | No
|  | S3‑210153 | Add Application Key Get service in clause 7.1 |  | ZTE Corporation | CR | Agreement | Yes | No | available | No
|  | S3‑210154 | Kakma invalid and Kausf invalid in clause 6.2 |  | ZTE Corporation | CR | Agreement | Yes | No | available | No
|  | S3‑210155 | Resolution of EN on other parameter in clause 6.3 |  | ZTE Corporation | CR | Agreement | Yes | No | available | No
|  | S3‑210156 | the KAF lifetime expiration in clause 5.2 |  | ZTE Corporation | CR | Agreement | Yes | No | available | No
|  | S3‑210157 | Discussion paper on KAUSF invalid and KAKMA invalid |  | ZTE Corporation | discussion | Endorsement | Yes | No | available | No
|  | S3‑210158 | UDM notifies AAnF AKMA context removal |  | ZTE Corporation | CR | Agreement | Yes | No | available | No
|  | S3‑210253 | Clarification on A-KID generation |  | Huawei, HiSilicon | CR | Approval | Yes | No | available | No
|  | S3‑210254 | Clarification on AAnF Selection |  | Huawei, HiSilicon | CR | Approval | Yes | No | available | No
|  | S3‑210447 | Network provides authorization to AF/UE for KAF key refresh |  | Samsung | CR | Approval | Yes | No | available | No
|  | S3‑210489 | Sending UE identifier to the AKMA AF |  | Qualcomm Incorporated, China Mobile | CR | Agreement | Yes | No | available | No |  | S3‑203191
|  | S3‑210496 | UE Sending GPSI (if available) to the AF |  | Samsung | CR | Approval | Yes | No | available | No
4.6 | Evolution of Cellular IoT security for the 5G System (Rel-16) | S3‑210017 | LS on 5G-GUTI reallocation after paging of a UE in 5GMM-IDLE mode with suspend indication |  | C1-200967 | LS in |  | Yes | No | available | No
|  | S3‑210480 | 5G GUTI re-allocation |  | Qualcomm Incorporated, Huawei, Hisilicon | CR | Agreement | Yes | No | available | No
|  | S3‑210481 | 5G CIoT K_NG-RAN derivation |  | Qualcomm Incorporated | CR | Agreement | Yes | No | available | No
4.7 | Security of the Wireless and Wireline Convergence for the 5G system architecture (Rel-16) | S3‑210342 | Authentication method selection for N5CW |  | Ericsson,Lenovo, Motorola Mobility, Cablelabs | CR | Agreement | Yes | No | available | No
|  | S3‑210345 | Authentication method selection for N5CW |  | Ericsson,Lenovo, Motorola Mobility, Cablelabs | CR | Agreement | Yes | No | available | No
|  | S3‑210452 | CR to correct figure 7A.2.4-1 |  | Samsung | CR | Approval | Yes | No | available | No
|  | S3‑210453 | [Mirror]CR to correct figure 7A.2.4-1 |  | Samsung | CR | Agreement | Yes | No | available | No
4.9 | Security aspects of Enhancement of Network Slicing (Rel-16) | S3‑210138 | Discussion on NSSAA Editor note for sending S-NSSAI to the AAA-S. |  | Nokia | discussion | Endorsement | Yes | No | available | No
|  | S3‑210139 | 2. CR to delete the EN (rel-16) in NSSAA clause |  | Nokia | CR |  | Yes | No | available | No
|  | S3‑210140 | CR to dete the NSSAA Editor Note (Rel-17) |  | Nokia | CR | Approval | Yes | No | available | No
|  | S3‑210197 | Discussion on SN-ID in NSSAA |  | Huawei, HiSilicon | discussion | Discussion | Yes | No | available | No
|  | S3‑210198 | Serving network ID in NSSAA |  | Huawei, HiSilicon | CR | Agreement | Yes | No | available | No
|  | S3‑210199 | validity peirod of NSSAA result |  | Huawei, HiSilicon | CR | Agreement | Yes | No | available | No
|  | S3‑210243 | Slice privacy protection in NSSAA related procedure |  | Huawei, HiSilicon | CR | Approval | Yes | No | available | No
4.10 | Security Aspects of 3GPP support for Advanced V2X Services (Rel-16) | S3‑210027 | Reply LS on the re-keying procedure for NR SL |  | R2-2010963 | LS in |  | Yes | No | available | No
|  | S3‑210066 | TS 33.536 - overall clean-up |  | LG Electronics Inc. | CR | Approval | Yes | No | available | No
|  | S3‑210135 | Clarifications regarding Authentication procedure for V2X PC5 unicast link |  | Nokia, Nokia Shanghai Bell | CR | Approval | Yes | No | available | No
|  | S3‑210250 | Clarification on key derivation |  | Huawei, HiSilicon | CR | Approval | Yes | No | available | No
|  | S3‑210251 | Reply LS about the layer to provide security |  | Huawei, HiSilicon | LS out | Approval | Yes | No | available | No
|  | S3‑210380 | Clarification on a figure and the key activation |  | Huawei, HiSilicon | CR | Approval | Yes | No | available | No
4.11 | Integration of GBA into 5GC (Rel-17) | S3‑210127 | Living document for TS 33.220: addition of UDM |  | THALES | draftCR | Approval | Yes | No | available | No
|  | S3‑210128 | Living document for TS 33.223: addition of UDM |  | THALES | draftCR | Approval | Yes | No | available | No
|  | S3‑210519 | Living document for TS 33.220: SBA support for Zh and Zn interfaces |  | Ericsson | draftCR | Approval | Yes | No | available | No
|  | S3‑210520 | Living document for TS 33.223: SBA support for Zpn |  | Ericsson | draftCR | Approval | Yes | No | available | No
|  | S3‑210521 | pCR to living document for TS 33.220: Support GBA in UDM |  | Ericsson | draftCR | Approval | Yes | No | available | No
|  | S3‑210522 | pCR to living document for TS 33.223: Support GBA in UDM |  | Ericsson | draftCR | Approval | Yes | No | available | No
|  | S3‑210523 | [DRAFT] LS on the SBA for GBA |  | Ericsson | LS out | Approval | Yes | No | available | No
4.12 | Security Assurance Specification for IMS (Rel-17) | S3‑210297 | Adding a new threat related with biding down attack in the threats |  | China Telecom, Huawei, HiSilicon | CR | Approval | Yes | No | available | No
|  | S3‑210300 | Resolving the ENs related with abort operation in the test case |  | China Telecom, Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210325 | Adding test case on the confidentiality configuration in P-CSCF |  | China Telecom, Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210355 | Assets and threats specific of encryption in network hiding in the I-CSCF |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210356 | New test case on encryption in network hiding in the I-CSCF |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210357 | Assets and threats specific of network hiding in the IBCF |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210358 | New test case on network hiding in the IBCF |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210375 | IMS SCAS: living doc for the threats |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210376 | Resolving the ENs related with biding down attacker in the test case |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210377 | Resolving the Ens related with biding down attack in the threats |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210399 | IMS SCAS: Adding the assets and threats of the AS |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210400 | Adding test cases on the authorization and privacy in AS |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210401 | IMS SCAS: Adding the assets and threats of the MRFC |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
4.13 | Security Assurance Specification Enhancements for 5G (Rel-17) | S3‑210234 | Threat analysis related to RRCConnectionReestablsihment in CP CIoT 5GS Optimization |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210235 | Draft CR on New Test Case on RRCConnectionReestablsihment in CP CIoT 5GS Optimization |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210262 | Threat to trigger condition on NSSAA procedure |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210263 | Living document for TS 33.511 |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210264 | Living document for TS 33.512 |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210265 | Living document for TS 33.514 |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210266 | Living document for TS 33.517 |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210267 | Living document for TS 33.117 |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210268 | Living document for TR 33.926 |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210348 | Threats related to session establishment procedure |  | Huawei, Hisilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210349 | New test case on validation of S-NSSAIs in PDU session establishment request |  | Huawei, Hisilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210359 | eSCAS:Add a new test case for GUTI allocation |  | Huawei, Hisilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210361 | eSCAS:Add a new test case for NSSAA |  | Huawei, Hisilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210362 | eSCAS: Updating the security threat to user privacy |  | Huawei, Hisilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210363 | eSCAS: Add a new threat on unauthorized slice access |  | Huawei, Hisilicon | draftCR | Approval | Yes | No | available | No
4.14 | Security Assurance Specification for Service Communication Proxy (SECOP) (Rel-17)
4.15 | Security Assurance Specification for 5G NWDAF (Rel-17) | S3‑210236 | Critical Assets for NWDAF |  | Huawei, HiSilicon, China Mobile | draftCR | Approval | Yes | No | available | No
|  | S3‑210237 | Network Product Class Description for NWDAF |  | Huawei, HiSilicon, China Mobile | draftCR | Approval | Yes | No | available | No
|  | S3‑210276 | Threat analysis on finding the right NF insances are serving this UE |  | Huawei, HiSilicon, China Mobile | draftCR | Approval | Yes | No | available | No
|  | S3‑210323 | Find the right NF instance are serving the UE |  | China Mobile, Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
4.16 | Security Assurance Specification for Non-3GPP InterWorking Function (N3IWF) (Rel- 17) | S3‑210221 | Threat to send EAP-Identity Request by N3IWF |  | China Unicom | CR |  | Yes | No | available | No
|  | S3‑210222 | Check whether the N3IWF sends the EAP-Identity Request message |  | China Unicom | pCR |  | Yes | No | available | No
|  | S3‑210269 | Threat analysis on the ability to create different child Sas |  | Huawei, HiSilicon, China Unicom | pCR | Approval | Yes | No | available | No
|  | S3‑210270 | Check whether the N3IWF has the ability to create different child Sas |  | Huawei, HiSilicon, China Unicom | pCR | Approval | Yes | No | available | No
|  | S3‑210271 | Threat analysis on mixing CP and UP into main SA |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210272 | Check whether the N3IWF creats a child SA for PDU session |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
4.17 | Security Assurance Specification for Inter PLMN UP Security (Rel-17) | S3‑210159 | New security functional requirement and related test case on validating of user data transported |  | ZTE Corporation | draftCR | Agreement | Yes | No | available | No
|  | S3‑210360 | SCAS IPUPS: Add a new test |  | Huawei, Hisilicon | draftCR | Approval | Yes | No | available | No
4.18 | eSCAS_5G for Network Slice-Specific Authentication and Authorization Function (NSSAAF) (Rel-17) | S3‑210273 | Threat analysis on select AAA-P and AAA-S |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210274 | NSSAAF route the S-NSSAI to the right place |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
4.19 | Mission critical security enhancements phase 2 (Rel-17) | S3‑210049 | Limited service state for missioncritical services |  | BDBOS | CR | Agreement | Yes | No | available | No
|  | S3‑210051 | Discussion – R17 Group regroup and user regroup security |  | Motorola Solutions Danmark A/S | discussion | Information | Yes | No | available | No
|  | S3‑210052 | [33.180] R17 Group regroup and user regroup security |  | Motorola Solutions Danmark A/S | CR | Agreement | Yes | No | available | No
4.20 | Enhancements to User Plane Integrity Protection Support in 5GS (Rel-17) | S3‑210223 | Draft CR on Clarification for UP integrity Mechanisms between the UE and the ng-eNB |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210224 | Draft CR on Clarification for Handling for indication of UE supports UPIP |  | Huawei, HiSilicon | draftCR | Approval | Yes | No | available | No
|  | S3‑210490 | Extend UPIP support in 5GS for all 5GC connected RAN architecture (NG-RAN) options |  | Qualcomm Incorporated | draftCR | Approval | Yes | No | available | No |  | S3‑203511
|  | S3‑210491 | pCR to UP IP draft CR to TS 33.501 |  | Qualcomm Incorporated | other | Approval | Yes | No | available | No
|  | S3‑210529 | Draft CR on algorithm selection |  | Ericsson | draftCR | Approval | Yes | No | available | No
4.21 | Adapting BEST for use in 5G networks (Rel-17) | S3‑210064 | 5G architecture enhancements for BEST |  | KPN N.V. | draftCR | Approval | Yes | No | available | No
4.22 | New work item proposals | S3‑210142 | New WID for supporting NSWO in 5G |  | ATT, Nokia, Nokia Shanghai Bell | WID new | Approval | Yes | No | available | No
|  | S3‑210211 | New WID on 5GFBS |  | Apple, AT&T, Deutsche Telekom, Charter Communication, China Unicom, NIST, CableLabs, Interdigital, Ericsson, Samsung, CAICT, CATT, Intel, vivo, MITRE, Philips | WID new | Approval | Yes | No | available | No
|  | S3‑210479 | New WID on AKMA Ua protocol profiles |  | Qualcomm Incorporated | WID new | Agreement | Yes | No | available | No
|  | S3‑210499 | New WID on 3GPP profiles for cryptographic algorithms and security protocols |  | Ericsson | WID new | Agreement | Yes | No | available | No
|  | S3‑210544 | New WID on normative changes for User Plane Integrity Protection for LTE options |  | VODAFONE Group Plc | WID new | Agreement | Yes | No | available | No
4.23 | Other work areas (no release restrictions) | S3‑210472 | Discussion on K_AUSF handling |  | Qualcomm Incorporated | discussion | Endorsement | Yes | No | available | No
|  | S3‑210144 | DISC Handling of latest Kasuf |  | NEC | discussion | Agreement | Yes | No | available | No
|  | S3‑210146 | Maintaining latest Kausf |  | NEC | CR | Agreement | Yes | No | available | No
|  | S3‑210005 | LS on Storage of KAUSF |  | C1-207764 | LS in |  | Yes | No | available | No
|  | S3‑210459 | LS on Reply LS on Storage of KAUSF from CT1 |  | Samsung | LS out | Approval | Yes | No | available | No
|  | S3‑210460 | Handling of KAUSF upon successful primary authentication |  | Samsung, Nokia, Nokia Shanghai Bell, Intel | CR | Approval | Yes | No | available | No
|  | S3‑210477 | Profiling the GBA TLS protocols for use with AKMA |  | Qualcomm Incorporated | CR | Agreement | Yes | No | available | No
|  | S3‑210478 | Adding references to AKMA profiles of Ua protocols |  | Qualcomm Incorporated | CR | Agreement | Yes | No | available | No
|  | S3‑210030 | LS on integrity and confidentiality protection of xcap-diff and pidf documents in MCPTT (TS 24.379) |  | R5- 206273 | LS in |  | Yes | No | available | No
|  | S3‑210053 | [33.180] R14 RFC3830 reference correction |  | Motorola Solutions Danmark A/S | CR | Agreement | Yes | No | available | No
|  | S3‑210054 | [33.180] R15 RFC3830 reference correction (mirror) |  | Motorola Solutions Danmark A/S | CR | Agreement | Yes | No | available | No
|  | S3‑210055 | [33.180] R16 RFC3830 reference correction (mirror) |  | Motorola Solutions Danmark A/S | CR | Agreement | Yes | No | available | No
|  | S3‑210056 | [33.180] R17 RFC3830 reference correction (mirror) |  | Motorola Solutions Danmark A/S | CR | Agreement | Yes | No | available | No
|  | S3‑210057 | [33.180] R14 XML encryption correction |  | Motorola Solutions Danmark A/S | CR | Agreement | Yes | No | available | No
|  | S3‑210058 | [33.180] R15 XML encryption correction (mirror) |  | Motorola Solutions Danmark A/S | CR | Agreement | Yes | No | available | No
|  | S3‑210059 | [33.180] R16 XML encryption correction (mirror) |  | Motorola Solutions Danmark A/S | CR | Agreement | Yes | No | available | No
|  | S3‑210060 | [33.180] R17 XML encryption correction (mirror) |  | Motorola Solutions Danmark A/S | CR | Agreement | Yes | No | available | No
|  | S3‑210141 | Authentication procedure during Xn handover procedure |  | NEC | CR | Agreement | Yes | No | available | No
|  | S3‑210073 | Correct NAS uplink COUNT for KgNB/KeNB derivation |  | MediaTek Inc. | CR | Agreement | Yes | No | available | No |  | S3‑202947
|  | S3‑210279 | Authentication procedure during Xn handover procedure |  | NEC | CR | Agreement | Yes | No | available | No
|  | S3‑210294 | Clarification on security protection in AMF reallocation(direct NAS reroute) |  | Huawei, HiSilicon | CR | Approval | Yes | No | available | No
|  | S3‑210326 | Correct current uplink EPS NAS COUNT used at derivation of a mapped 5G security context |  | MediaTek Inc. | CR |  | Yes | No | available | No
|  | S3‑210415 | Correcting notation used for inter-AMF mobility key derivation |  | MediaTek Inc. | CR | Agreement | Yes | No | available | No |  | S3‑202948
|  | S3‑210004 | AMF transparency for SOR |  | C1-207736 | LS in |  | Yes | No | available | No
|  | S3‑210025 | LS on Changes to SoR Delivery Mechanism |  | C4-205696 | LS in |  | Yes | No | available | No
|  | S3‑210367 | LS reply on changes to SoR delivery mechanims |  | Huawei, Hisilicon | LS out | Approval | Yes | No | available | No
|  | S3‑210351 | LS on loop registration in CAG |  | Huawei, Hisilicon | LS out | Approval | Yes | No | available | No
|  | S3‑210350 | DP on loop registration in CAG |  | Huawei, Hisilicon | discussion | Endorsement | Yes | No | available | No
|  | S3‑210449 | Discussion on MitM attack |  | Samsung | discussion | Discussion | Yes | No | available | No
|  | S3‑210450 | CR for identification of MitM attack |  | Samsung | CR | Agreement | Yes | No | available | No
|  | S3‑210445 | Correction to FC values in range for future use in 3GPP specifications |  | Samsung | CR | Agreement | Yes | No | available | No
|  | S3‑210451 | CR for correction in SEAL |  | Samsung | CR | Agreement | Yes | No | available | No
5 | Studies areas
5.1 | Study on 5G security enhancement against false base stations | S3‑210050 | Update to solution #17 (6.17.2) of TR 33.809 |  | Deutsche Telekom AG | pCR | Approval | Yes | No | available | No
|  | S3‑210092 | pCR Signing solutions and cell selection in TR 33.809 |  | VODAFONE Group Plc | pCR | Approval | Yes | No | available | No
|  | S3‑210133 | New solution FBS KI#2 |  | Philips International B.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210541 | New annex of TR 33.809 – analysis of KI#2 and recommendations |  | CableLabs, Deutsche Telekom AG, InterDigital | pCR | Approval | Yes | No | available | No
|  | S3‑210131 | Additions to FBS Solution #23 |  | Philips International B.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210132 | Additions to FBS Solution #24 |  | Philips International B.V., CableLabs, Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210193 | Detection of MitM FBS |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210018 | Reply LS to SA3 on FBS detection |  | R2-1914224 | LS in |  | Yes | No | available | No
|  | S3‑210194 | Reply LS on FBS detection |  | Huawei, HiSilicon | LS out | Approval | Yes | No | available | No
|  | S3‑210488 | Reply LS on False Base Station Detection |  | Qualcomm Incorporated | LS out |  | Yes | No | available | No
|  | S3‑210518 | pCR to 33.809 - addition of evaluation for solution 8 |  | VODAFONE Group Plc | pCR | Approval | Yes | No | available | No
|  | S3‑210143 | Enhanced description for KI#7 |  | Nokia, Nokia Shanghai Bell, Philips | pCR | Approval | Yes | No | available | No
|  | S3‑210212 | 5GFBS-Edotorial change After EditHelp |  | Apple | pCR | Approval | Yes | No | available | No
5.2 | Study on SECAM and SCAS for 3GPP virtualized network products | S3‑210160 | Update the clause 5.2.5.5.7 |  | ZTE Corporation, China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210303 | Clarifying the scope |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210304 | Clarifying for types of virtualised network product class |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210305 | Clarifying for Generic virtualised network product model class description |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210306 | Clarifying for Generic assets and threats for GVNP of type 1 |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210307 | Clarifying for Generic assets and threats for GVNP of type 2 and type 3 |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210308 | Adding comparison |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210309 | Modifying test case in clause 5.2.5.5.7.2 |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210310 | clarifying the content in clause 5.2.5.6.6.1 and clause 5.2.5.6.7 |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210311 | Clarifying for the security requirements and test cases in clause 5.2.5.7.7.1 and 5.2.5.7.7.2 |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210312 | Adding hardening requirements for GVNP of type 3 |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210313 | Adding vendor development and product lifecycle processes and test laboratory accreditation into Clause 6 |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210314 | Adding evaluation and SCAS instantiation into clause 7 |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210315 | new proposal for way forward v2 |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210316 | editorial correction on TR33818-coversheet |  | China Mobile | pCR | Approval | Yes | No | available | No
5.3 | Study on User Plane Integrity Protection | S3‑210225 | New Solution for UPIP for EPS | [Ericsson] contribution requires clarification and updates [Huawei] provides clarification [Ericsson] provides further comments [Qualcomm] proposes to note this contribution. [Huawei] provides clarification | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210433 | Update to Solution #24: Interworking handover from 5GS to EPS | [Qualcomm] Clarifications and modifications are required. [Ericsson] provides clarifications [Ericsson] provides r1 | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210434 | Update to Solution #21: Interworking handover from EPS to 5GS | [Qualcomm] Clarifications and modifications are required. [Ericsson] provides r1 | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210435 | Update to Solution #22: S1 handover | [Qualcomm] Clarifications and modifications are required. [Ericsson] provides r1 | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210436 | Update to Solution #23: X2 handover | [Qualcomm] Clarifications and modifications are required. [Ericsson] provides r1 | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210437 | Discussion paper on UP IP policy in EPS |  | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210438 | Conclusion on UE connects to EPC via eUTRA |  | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210474 | Addressing the EN in solution #18 |  | Qualcomm Incorporated | pCR | Approval | Yes | No | available | No
|  | S3‑210475 | Addressing some ENs in solution #20 |  | Qualcomm Incorporated | pCR | Approval | Yes | No | available | No
|  | S3‑210476 | Proposed partial conclusion to key issues #1 and #2 |  | Qualcomm Incorporated | pCR | Approval | Yes | No | available | No
|  | S3‑210497 | pCR to TR 33.853 – New Best Effort solution for EPS using UE Radio Access capabilities | [Ericsson] have some questions for clarification [Vodafone] provides clarifications [Qualcomm] provides comments [Vodafone] provides clarifications [Nokia] asks question for clarification [Apple] Clarification is needed [Vodafone] provides clarifications [Vodafone] provides clarification to Apple | VODAFONE Group Plc | pCR | Approval | Yes | No | available | No
|  | S3‑210500 | pCR to TR 33.853 - Updates to Solution#13 - MME and IoDT test impacts | [Qualcomm] contribution should be noted without changes. [Vodafone] provides clarification | VODAFONE Group Plc | pCR | Approval | Yes | No | available | No
|  | S3‑210502 | pCR to TR 33.853 - Updates to Solution#14 – optional use of security mode command |  | VODAFONE Group Plc | pCR | Approval | Yes | No | available | No
|  | S3‑210503 | pCR to TR 33.853 - Updates to Solution#15 – 5GC control concept |  | VODAFONE Group Plc | pCR | Approval | Yes | No | available | No
|  | S3‑210504 | pCR to TR 33.853 - Updates to Solution#18 – small corrections | [Qualcomm] OK with the changes proposed. Suggests merger with S3-210474 [Vodafone] suggest merge of S3-210504 into S3-210474 | VODAFONE Group Plc | pCR | Approval | Yes | No | available | No
|  | S3‑210513 | pCR to TR 33.853 - Updates to Solution #20 – small corrections | [Qualcomm] changes are needed to make it acceptable [Vodafone] provides clarification | VODAFONE Group Plc | pCR | Approval | Yes | No | available | No
|  | S3‑210514 | pCR to TR 33.853 - Updates to Solution #21 EPS to 5GS handover– evaluation | [Ericsson] asks question for clarification [Vodafone] provides clarification | VODAFONE Group Plc | pCR | Approval | Yes | No | available | No
|  | S3‑210516 | pCR to TR 33.853 – New Solution #AC Handover from EPS to 5GS using unmodified R15/16 messages and procedures |  | VODAFONE Group Plc | pCR | Approval | Yes | No | available | No
|  | S3‑210536 | Presentation of Specification/Report to TSG: TR33.853, Version |  | VODAFONE Group Plc | TS or TR cover | Approval | Yes | No | available | No
|  | S3‑210540 | pCR to TR 33.853 – Conclusion on UE connects to EPC via eUTRA |  | VODAFONE Group Plc | pCR | Approval | Yes | No | available | No
|  | S3‑210542 | [DRAFT] LS on User Plane Integrity Protection for eUTRA connected to EPC |  | VODAFONE Group Plc | LS out | Approval | Yes | No | available | No
5.4 | Study on Security Impacts of Virtualisation | S3‑210087 | TR 33.848 Jan 2021 Refresh |  | BT plc | pCR | Agreement | Yes | No | available | No
5.5 | Study on authentication enhancements in 5GS | S3‑210129 | TR 33.846: conclusion for key issue #2.1 |  | THALES | pCR | Approval | Yes | No | available | No
|  | S3‑210164 | Update solution#2.1 in TR 33.846 |  | ZTE Corporation | pCR | Approval | Yes | No | available | No
|  | S3‑210327 | Linkability by distinguishing MAC failure and synchronization failure |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210332 | Evaluation of solution 2.3 |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210148 | SUCI Linkability attack |  | NEC | pCR | Agreement | Yes | No | available | No
|  | S3‑210163 | Solution of Mitigation against the SUPI replay attack |  | ZTE Corporation | pCR | Approval | Yes | No | available | No
|  | S3‑210321 | Solution to address the Key issue #2.2 in TR 33.846 |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210328 | Update KI on SUPI guessing |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210130 | TR 33.846: conclusion for key issue #4.1 |  | THALES | pCR | Approval | Yes | No | available | No
|  | S3‑210161 | Conclusion for Key Issue #4.1 |  | ZTE Corporation | pCR | Approval | Yes | No | available | No
|  | S3‑210162 | New solution for key issue# 4.1 in TR 33.846 |  | ZTE Corporation | pCR | Approval | Yes | No | available | No
|  | S3‑210165 | Update the evaluation for solution# 4.1 |  | ZTE Corporation | pCR | Approval | Yes | No | available | No
|  | S3‑210166 | Update the evaluation for solution# 4.2 |  | ZTE Corporation | pCR | Approval | Yes | No | available | No
|  | S3‑210167 | Update the evaluation for solution# 4.3 |  | ZTE Corporation | pCR | Approval | Yes | No | available | No
|  | S3‑210168 | Update the evaluation for solution# 4.4 |  | ZTE Corporation | pCR | Approval | Yes | No | available | No
|  | S3‑210169 | Update the key issue 4.1 |  | ZTE Corporation | pCR | Approval | Yes | No | available | No
|  | S3‑210331 | EN resolution on SQNms protection |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210333 | EN related note to solution 4.4 |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210337 | AUTS SQNMS solution for EPS |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210338 | AUTS SQNMS solution for 5GS |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210282 | new solution to mitigate supi guessing and suci replay attack |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210022 | Reply to LS on Resynchronisations |  | ETSI SAGE | LS in |  | Yes | No | available | No
|  | S3‑210336 | SQNms protection by concealment in ME |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No |  | S3‑203330
|  | S3‑210329 | KI on linkability by SUCI |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210330 | Assuring SUCI generation by legitimiate SUPI owner |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210501 | Home network triggered reauthentication |  | NTT DOCOMO INC. | pCR | Approval | Yes | No | available | No
|  | S3‑210334 | Evaluation criterias |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210517 | TR 33.846: comparison of candidate solutions |  | THALES | discussion | Discussion | Yes | No | available | No
|  | S3‑210335 | Editorial changes to TR |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210322 | Discussion on enlarging the length of truncated MACs for 5G systems |  | China Mobile | pCR | Discussion | Yes | No | available | No
5.6 | Study on storage and transport of 5GC security parameters for ARPF authentication | S3‑210037 | Update of clause 4.2 |  | KPN N.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210038 | New KI: Protection of TUAK TOPc value during storage in UDR |  | KPN N.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210039 | New KI: Protection of TUAK TOPc value during transfer out of UDR |  | KPN N.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210040 | New Solution: Protection of SQN during storage in UDR |  | KPN N.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210041 | New Solution: Protection of SQN during transfer out of UDR |  | KPN N.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210042 | New Solution: Protection of TUAK TOPc value during storage in UDR |  | KPN N.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210043 | New Solution: Protection of TUAK TOPc value during transfer out of UDR |  | KPN N.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210044 | Updated Solution #8: Encrypted transfer of OPc between UDR and UDM/ARPF |  | KPN N.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210045 | Updated Solution #9: Encrypted transfer of OP between UDR and UDM/ARPF |  | KPN N.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210046 | Updated Solution #10: Encrypted strorage of OPc in UDR |  | KPN N.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210047 | Updated Solution #11: Encrypted storage of OP in UDR |  | KPN N.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210076 | Evaluation of solution 6 |  | NCSC | pCR |  | Yes | No | available | No
|  | S3‑210077 | Evaluation of solution 7 |  | NCSC | pCR |  | Yes | No | available | No
|  | S3‑210078 | Evaluation of solution 8 |  | NCSC | pCR |  | Yes | No | available | No
|  | S3‑210079 | Evaluation of solution 9 |  | NCSC | pCR |  | Yes | No | available | No
|  | S3‑210080 | Evaluation of solution 10 |  | NCSC | pCR |  | Yes | No | available | No
|  | S3‑210081 | Evaluation of solution 11 |  | NCSC | pCR |  | Yes | No | available | No
|  | S3‑210082 | New solution for KI#8 |  | NCSC | pCR |  | Yes | No | available | No
|  | S3‑210083 | New solution for KI#9 |  | NCSC | pCR |  | Yes | No | available | No
|  | S3‑210084 | Some conclusions for TR 33.845 |  | NCSC | pCR |  | Yes | No | available | No
|  | S3‑210085 | Editorial corrections |  | NCSC | pCR |  | Yes | No | available | No
|  | S3‑210464 | Conclusions for TR 33.845 |  | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210468 | removal of Editor’s Notes |  | Ericsson | pCR | Approval | Yes | No | available | No
5.7 | Study on security aspects of Unmanned Aerial Systems | S3‑210093 | TR 33.854 Update for solution#5 | [Huawei] request clarification. [Qualcomm] asks clarification question | InterDigital, Europe, Ltd. | pCR | Approval | Yes | No | available | No
|  | S3‑210201 | Remove EN1-align SA2 procedure |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210202 | Remove EN2-align AF defined by SA2 |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210203 | Remove EN3-revocation | [Ericsson] provides comment and request clarification. [Huawei] provides r1 | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210204 | Remove EN1-exchange ID with USS | [Ericsson] request clarification. [Huawei] provides r1 [InterDigital] comments [Huawei] provides r2 | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210205 | Remove EN2- revocation | [Ericsson] request clarification. [Huawei] provide clarification [Huawei] provides r1 [InterDigital] comments [Huawei] provides r2 | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210443 | Evaluation update of solution 7 |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210466 | Update to solution #2 | [InterDigital] ask questions for clarifications [Ericsson] provides updates | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210469 | Some clarifications to solution #10 | [InterDigital] comments | Qualcomm Incorporated | pCR | Approval | Yes | No | available | No
|  | S3‑210470 | Proposed solution for pairing authorisation in 5G | [Huawei] comments | Qualcomm Incorporated | pCR | Approval | Yes | No | available | No
|  | S3‑210471 | Proposed solution for UAV authorisation when connected to 4G | [Huawei] suggest an editorial correction | Qualcomm Incorporated | pCR | Approval | Yes | No | available | No
|  | S3‑210537 | Update to Solution #7 |  | Lenovo, Motorola Mobility | pCR | Approval | Yes | No | available | No
|  | S3‑210538 | Solution on UAV and UAV-C Pairing Authorization | [InterDigital] comments [Lenovo] provides clarifications [Nokia] request clarifications [Lenovo] provides clarifications | Lenovo, Motorola Mobility | pCR | Approval | Yes | No | available | No
|  | S3‑210094 | Solution for UAV location privacy | [Ericsson] propose to note the contribution. [InterDigital] provides clarifications [Qualcomm] comments [InterDigital] provides clarifications [Nokia] request clarification | InterDigital, Europe, Ltd. | pCR | Approval | Yes | No | available | No
|  | S3‑210200 | Addressing EN in KI#7: scope of C2 Security | [Ericsson] propose to note the contribution or update required [Huawei] provide clarification [Qualcomm] contribution should be noted | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210535 | Updates to Key Issue #7 |  | Lenovo, Motorola Mobility | pCR | Approval | Yes | No | available | No
|  | S3‑210444 | DHIES encryption to avoid UAV spoofing | [Huawei] comments [Qualcomm] proposes to note this contribution with changes. | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210442 | Mapping table | [Huawei] mapping table can be revised at the end of the week [Nokia] Propose to approve without modification. | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
5.8 | Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC | S3‑210170 | AMF selection in multiple NAS connections in solution#6.7 in TR 33.839 |  | ZTE Corporation | pCR | Approval | Yes | No | available | No
|  | S3‑210171 | LBO roaming scenario should be supported in solution#6.7 in TR 33.839 | [Huawei] proposes editorial changes [ZTE] r1 available [Huawei] fine with r1 | ZTE Corporation | pCR | Approval | Yes | No | revised | No | draft_S3-210171-r1
|  | S3‑210181 | Add new solution in TR 33.839 | [Huawei] proposes to note [CATT] comments | CATT | pCR | Approval | Yes | No | available | No
|  | S3‑210183 | Remove the EN in solution #5 | [Ericsson] asks for clarifications on the solution prerequisite [CATT] r1 available | CATT | pCR | Approval | Yes | No | revised | No | draft_S3-210183-r1
|  | S3‑210185 | Remove EN in Solution #6 in TR 33.839 | [Ericsson] asks for clarifications as on 183 | CATT | pCR | Approval | Yes | No | available | No
|  | S3‑210190 | Updates to solution 4: evaluation | [Huawei] proposes to postpone evaluation and points to discussion on 190 [Ericsson] proposes to postpone as well | Intel Corporation (UK) Ltd | pCR |  | Yes | No | available | No
|  | S3‑210191 | Updates to solution 4 | [Huawei] asks for clarifications | Intel Corporation (UK) Ltd | pCR | Approval | Yes | No | available | No
|  | S3‑210389 | EC: Resolving the En and adding evalution of solution #16 | [Ericsson] requires updates | Huawei, Hisilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210430 | Update of Solution #7 | [Ericsson] proposes to note [Huawei] comments and argues this is misusing the registration procedure [Lenovo] comments [Samsung] asks for clarifications on EEC ID | Lenovo, Motorola Mobility | pCR | Approval | Yes | No | available | No
|  | S3‑210458 | Updates to solution#7 to identify the appropriate AMF by the NEF | [Lenovo] proposes to note [Ericsson] requires clarifications [Huawei] requires for clarifications [Samsung] comments [ZTE] proposes EN on GPSI availability | Samsung | pCR | Approval | Yes | No | available | No
|  | S3‑210011 | Reply LS on IP address to GPSI translation | [chair] proposes to postpone [Qualcomm] ok to postpone [Nokia] we need to provide feedback as we are in the to list, SA2 did we conclude [Qualcomm] they are no awaiting feedback [Nokia] to hold the pen [Docomo] clarify the use of the term "session" [Apple] not sure about stating no security issues and require more discussion in email [Docomo] does the AF need to be authorized, maybe could be clarified by rewording to be replied to in 10011-r1 | S2-2009339 | LS in |  | Yes | Yes | open | No | draft_S3-210011-r1
|  | S3‑210465 | Update to solution #17 | [Huawei] asks for clarifications [Ericsson] comments | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210505 | Evaluation of Solution #7 | [Ericsson] proposes to note and points to thread 430 [Lenovo] comments | Lenovo, Motorola Mobility | pCR | Approval | Yes | No | available | No
|  | S3‑210180 | Updates to solution 18: Removal EN related to EEC ID | [Ericsson] requires clarifications [Huawei] points to NAS SM transparency to AMF | Intel Corporation (UK) Ltd | pCR | Approval | Yes | No | available | No
|  | S3‑210182 | Updates to solution 18: Removal EN related to identification of serving AMF | [Huawei] raises concerns | Intel Corporation (UK) Ltd | pCR | Approval | Yes | No | available | No
|  | S3‑210186 | Updates to solution 18: Removal EN related to roaming | [Huawei] proposes to note | Intel Corporation (UK) Ltd | pCR |  | Yes | No | available | No
|  | S3‑210192 | Updates to solution 12: Removing EN | [Ericsson] requires updates related to trust relationships [Intel] comments [Huawei] comments | Intel Corporation (UK) Ltd | pCR | Approval | Yes | No | available | No
|  | S3‑210393 | EC: skeleton of clause 7 and conclusion of KI #4 | [Ericsson] requires updates | Huawei, Hisilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210388 | EC: Editorial changes and Resolving the ENs of solution #13 |  | Huawei, Hisilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210172 | Update the key issue#7 in TR 33.839 | [Huawei] requires updates related to the use of N6 | ZTE Corporation | pCR | Approval | Yes | No | available | No
|  | S3‑210173 | Update the solution#14 in TR 33.839 | [Huawei] requires updates related to the use of N6 | ZTE Corporation | pCR | Approval | Yes | No | available | No
|  | S3‑210390 | EC: Evaluation of solution #20 and conclusion of KI #8 | [Ericsson] proposes to note [Huawei] provides r1 | Huawei, Hisilicon | pCR | Approval | Yes | No | revised | No | draft_S3-210390-r1
|  | S3‑210216 | MEC-Evaluation on solution#1 | [Ericsson] requires updates [Apple] comments | Apple | pCR | Approval | Yes | No | available | No
|  | S3‑210391 | EC: Evaluation of solution #21 |  | Huawei, Hisilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210217 | MEC-Modification on solution#22 | [Huawei] proposes to note [Apple] comments | Apple | pCR | Approval | Yes | No | available | No
|  | S3‑210392 | EC: Resolving the Editor’s notes and evaluation of solution #22 | [Ericsson] proposes to note due to missing details [Huawei] comments | Huawei, Hisilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210184 | Key issue on authorization revocation in TR 33.839 | [Ericsson] proposes to note | CATT | pCR | Approval | Yes | No | available | No
|  | S3‑210365 | EC: New key issue on N4 protection for UPF in customer network | [Ericsson] proposes to note [Huawei] r1 available | Huawei, Hisilicon | pCR | Approval | Yes | No | revised | No | draft_S3-210365-r1
|  | S3‑210366 | EC: New solution to th ekey issue on N4 security | [Ericsson] proposes to note | Huawei, Hisilicon | pCR | Approval | Yes | No | available | No
5.9 | Study on Security Aspects of Enhancement for Proximity Based Services in 5GS | S3‑210020 | LS on Security Requirements for Sidelink/PC5 Relays | [chair] proposes to postpone [Huawei] no need to reply [Nokia] proposes to reply working on solutions for both [CATT] agrees with Nokia [Nokia] will hold the pen, r1 available [Huawei] requires more time [KPN] proposes changes and to point out to the agreed requirements [Nokia] isn't it enough to refer to the whole TR? LS purpose is not to stall progress in SA2 [Qualcomm] agrees with Nokia [Apple] SA3 need more time to discuss to be replied to in 210020-r1 | S2-2004750 | LS in |  | Yes | Yes | open | No | draft_S3-210020-r1
|  | S3‑210067 | TR 33.847 - Remove ENs in KI1 | [InterDigital] requires changes [LGE] comments [Qualcomm] not sure about the privacy threat | LG Electronics Inc. | pCR | Approval | Yes | No | available | No
|  | S3‑210070 | TR 33.847 - New KI on security protection misalignment in L3 UE2NW relay | [Ericsson] disagrees with suggested impact on Uu and requires changes [InterDigital] comments [Qualcomm] comments [Nokia] asks for clarifications [Huawei] proposes to merge with 482 or modify to avoid overlap [CATT] proposes to merge in 482 [Xiaomi] proposes changes [Apple] comments [LGE] r1 available | LG Electronics Inc. | pCR | Approval | Yes | Yes | revised | No | draft_S3-210070-r1
|  | S3‑210086 | TR 33.847 Update for KI #4 |  | InterDigital, Inc. | pCR | Approval | Yes | Yes | revised | No | S3‑210149
|  | S3‑210149 | TR 33.847 Update for KI #4 | [CATT] comments no need to revise KI [LGE] comments | InterDigital, Inc., LG Electronics | pCR | Approval | Yes | No | available | No |  | S3‑210086
|  | S3‑210246 | Propose to resolve EN in KI#16 |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210247 | Propose to resolve ENs in the clause of KI detail of KI#12 |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210255 | Update Key issue #11 | [InterDigital] requires changes and justification [CATT] comments | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210482 | New Key Issue on security policy handling for 5G Prose services | [InterDigital] requires changes [CATT] comments [Xiaomi] asks for further clarifications [Apple] requires clarifications and changes | Qualcomm Incorporated, Huawei, Hisilicon, Ericsson | pCR | Approval | Yes | Yes | open | No
|  | S3‑210068 | TR 33.847 - Resolve ENs in Sol13 | [InterDigital] requires changes and Ens [LGE] comments | LG Electronics Inc. | pCR | Approval | Yes | No | available | No
|  | S3‑210069 | TR 33.847 - Evaluation of Sol13 | [InterDigital] requires EN and points to discussion on 068 [LGE] comments | LG Electronics Inc. | pCR | Approval | Yes | No | available | No
|  | S3‑210071 | Updated Solution #22: Representation of identities during broadcast | [Philips] requests clarifications [KPN] comments | KPN N.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210072 | Updated Solution #23: Initial key with validity time |  | KPN N.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210122 | TR 33.847 Update for solution #10 | [Huawei] requires clarifications [Apple] asks for clarifications | InterDigital, Inc. | pCR | Approval | Yes | No | available | No
|  | S3‑210123 | Solution for NSSAA procedure for Remote UE with L3 UE-to-Network relay | [Huawei] requires changes [Philips] asks for clarifications | InterDigital, Inc. | pCR | Approval | Yes | No | available | No
|  | S3‑210124 | Solution for secondary authentication Remote UE with L3 UE-to-Network relay | [LGE] requires clarifications [InterDigital] comments [LGE] comments [Qualcomm] proposes ENs [LGE] how does the relay determine that secondary auth is required for remote UE | InterDigital, Inc. | pCR | Approval | Yes | Yes | open | No
|  | S3‑210125 | TR 33.847 Update for solution #12 |  | InterDigital, Inc. | pCR | Approval | Yes | No | available | No
|  | S3‑210174 | Update to Solution #3 |  | ZTE Corporation | pCR | Approval | Yes | No | available | No
|  | S3‑210175 | Update to Solution #4 |  | ZTE Corporation | pCR | Approval | Yes | No | available | No
|  | S3‑210206 | Remove EN1:security of group management |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210207 | Remove EN2: Time synchronization |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210208 | Adding Evalaution |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210244 | Address Editor's Note in solution 15 | [LGE] requires clarifications and proposes minor correction | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210245 | A solution to protect PDU session related parameters for L2 relay | [InterDigital] what is new? [Huawei] solution is more like a discussion on how to reuse existing mechanisms to address KI [Qualcomm] need more time for the evaulation | Huawei, HiSilicon | pCR | Approval | Yes | Yes | open | No
|  | S3‑210248 | Propose to mitigate policy confliction using match report |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210249 | Propose to mitigate policy conflication using restricted discovery |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210252 | Update evaluation to Solution#7 |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210256 | Evaluation on Solution#3 |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210257 | Evaluation on Solution#4 |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210258 | Evaluation on Solution#5 | [Thales] there is ongoing work on GBA in 5GC so proposes to postpone [Huawei] proposes SUPI protection in GBA in 5GC work but was considered not in scope [InterDigital] 4G related aspects should not be considered. How is this related to solution #5 evaluation [Qualcomm] this is innacurate since there are mechanisms to protect identifiers in GBA [Huawei] agree partly but there are privacy issues during initial authentication | Huawei, HiSilicon | pCR | Approval | Yes | Yes | open | No
|  | S3‑210259 | Evaluation on solution #11 |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210261 | Address Editor's Note in solution 14 | [InterDigital] comments | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210281 | pCR to TR33.847- New solution on L3 UE-to-Network Relay | [InterDigital] proposes changes [Huawei] comments and proposes Ens | CATT | pCR | Approval | Yes | No | available | No
|  | S3‑210296 | pCR to TR33.847- New solution on UE-to-Network Relay based on primary authentication | [InterDigital] proposes Ens [Huawei] proposes Ens [Xiaomi] asks for clarifications [Apple] asks for clarifications | CATT | pCR | Approval | Yes | No | available | No
|  | S3‑210299 | Evaluation on solution #14 | [InterDigital] proposes EN and points to ongoing thread 261 | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210394 | ProSe: Resolving the ENs of solution #16 |  | Huawei, Hisilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210439 | ProSe: Update to solution #21 | [InterDigital] proposes changes and EN on UDM aspects [Huawei] proposes to note [Ericsson] comments | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210440 | ProSe: New solution for the use of authorization token in UE-to-UE relay |  | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210441 | ProSe: Update to solution #6 | [InterDigital] asks for clarifications on differences w.r.t. Sol #21 [Ericsson] comments [Huawei] comments and points to thread 439 | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210448 | [ProSe] pCR for resolving ENs in solution#1 | [Qualcomm] asks for clarifications [Samsung] comments | Samsung | pCR | Approval | Yes | No | available | No
|  | S3‑210483 | Solution 18 EN resolution | [InterDigital] proposes changes [Qualcomm] comments [Huawei] proposes EN | Qualcomm Incorporated | pCR | Approval | Yes | No | available | No
|  | S3‑210484 | Solution 19 EN resolution |  | Qualcomm Incorporated | pCR | Approval | Yes | No | available | No
|  | S3‑210485 | Solution 20 EN resolution |  | Qualcomm Incorporated | pCR | Approval | Yes | No | available | No
|  | S3‑210486 | Update of solution #18 to add authorization for the UE-to-Network relay | [InterDigital] asks for clarifications [Qualcomm] comments | Qualcomm Incorporated | pCR | Approval | Yes | No | available | No
|  | S3‑210543 | Solution to mitigate privacy issues of relay service codes and PDU parameters for L3 UE-to-NW relays | [Ericsson] asks for clarifications [Philips] comments [Ericsson] proposes EN on dependency on SA2 conclusion | Philips International B.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210260 | Conclusion on PC3 protection | [Thales] there is ongoing work on GBA in 5GC so proposes to postpone [InterDigital] too early to conclude | Huawei, HiSilicon | pCR | Approval | Yes | Yes | open | No
5.10 | Study on security for enhanced support of Industrial IoT | S3‑210291 | Add evaluation to solution 1 | [Nokia] proposed to merge into S3-210511 [Huawei] provides r1 (merged version) [Nokia] provides r2 (co-signed the r1) | Huawei, HiSilicon | pCR | Approval | Yes | No | revised | No | draft_S3-210291-r2
|  | S3‑210292 | Add evaluation to solution 3 | [Nokia] proposed to merge into S3-210512 [Huawei] provides r1 (merged version) [Nokia] provides r2 (co-signed the r1) | Huawei, HiSilicon | pCR | Approval | Yes | No | revised | No | draft_S3-210292-r2
|  | S3‑210354 | New requirement on key issue #2 of TR 33.851 | Ericsson: Propose to note the contribution. [Huawei] provides clarification [Nokia] supports to add the requirement. | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210506 | TR editorials |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | Yes | approved | No
|  | S3‑210507 | Mapping table |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | Yes | approved | No
|  | S3‑210508 | Annex on Security considerations for integration with TSN | [Ericsson] requires updates [Nokia] provides clarifications | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210509 | KI details Attacks based on asymmetric channel delay | [Ericsson] Propose to note the contribution. [Nokia] provides clarifications | Nokia, Nokia Shanghai Bell, Deutsche Telekom | pCR | Approval | Yes | No | available | No
|  | S3‑210510 | Authorization of incoming time synchronization messages based on policies | [Ericsson] propose to note the contribution. [Nokia] provides clarifications [Thales] proposes to note the contribution. [Nokia] agrees with Thales | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210511 | Evaluation to solution 1 | [Nokia] proposed to merge into S3-210291. Thread closed to be merged in 291 | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | merged | No
|  | S3‑210512 | Evaluation to solution 3 | [Huawei] merge is needed [Nokia] proposed to merge into S3-210292. Thread closed to be merged in 292 | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | merged | No
5.11 | Study on Security Aspects of Enhancements for 5G Multicast-Broadcast Services | S3‑210290 | Update the terms in TR 33.850 |  | Huawei, HiSilicon | pCR | Approval | Yes | Yes | approved | No
|  | S3‑210369 | 5MBS: Adding overview |  | Huawei, Hisilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210036 | New Key Issue: MBS Location Privacy | [Huawei] clarification is needed [MITRE] provides clarification [Huawei] asks further questions | MITRE | pCR | Approval | Yes | No | available | No |  | S3‑210034
|  | S3‑210288 | New solution for traffic protection in service layer |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210215 | MBS-Modification on solution#1 | [Huawei] provides r1 Apple: provides clarification [Huawei] comments [Qualcomm] asks question | Apple | pCR | Approval | Yes | No | revised | No | draft_S3-210215-r1
|  | S3‑210286 | Addressing the EN on solution1 |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210289 | New solution to support the UE mobility in MBS |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210463 | Addition to support key update in Solution 1 | [Huawei] update is needed [Qualcomm] propose to submit this as a separate solution [Philips] provides r1 | Philips International B.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210487 | Security for MBS traffic during handover | [Huawei] propose to merge S3-210487 into S3-210289 and use S3-210289 as baseline [Qualcomm] prefer to use 487 as a baseline [Huawei] fine to use 487 as baseline. Provides further comments [Qualcomm] provides clarifications [Huawei] provides r1 | Qualcomm Incorporated | pCR |  | Yes | No | available | No
|  | S3‑210134 | Additions to MBS Solution #2 | [Qualcomm] asks a question [Philips] provides clarification [Qualcomm] asks further question for clarifications [Philips] provides clarification | Philips International B.V. | pCR | Approval | Yes | No | available | No
|  | S3‑210287 | Addressing the EN on solution2 |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210368 | 5MBS: Updats to solution #3 |  | Huawei, Hisilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210370 | 5MBS: Updates to solution #4 |  | Huawei, Hisilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210371 | 5MBS: Updates to solution #5 |  | Huawei, Hisilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210285 | Conclusion on key issue 4 | Nokia: propose to note this document. | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210034 | New Key Issue: MBS Location Privacy |  | MITRE | pCR | Approval | No | Yes | revised | No | S3‑210035
|  | S3‑210035 | New Key Issue: MBS Location Privacy |  | MITRE | pCR | Approval | No | Yes | withdrawn | Yes |  | S3‑210034
5.12 | Study on enhanced security support for Non-Public Networks | S3‑210009 | Reply LS on security issue for on-boarding and remote provisioning from SA3 | [Nokia] to hold the pen to be replied to in 210137 | S2-2009132 | LS in |  | Yes | Yes | open | No
|  | S3‑210137 | [DRAFT] Reply-LS on security issue for on-boarding and remote provisioning. |  | Nokia, Nokia Shanghai Bell | LS out | Approval | Yes | Yes | open | No
|  | S3‑210230 | Reply LS on Security issue for On-boarding and Remote Provisioning | to be merged in 210137 | Huawei, HiSilicon | LS out | Approval | Yes | Yes | merged | No
|  | S3‑210343 | draft LS on Feedback on function supporting primary authentication and authorization of SNPN UEs that use credentials from the AAA Server | [Nokia] requires updates [Ericsson] r1 available based on offline discussion [Nokia] proposes further changes [Ericsson] we cannot mandate SUPI privacy [Vfe] what is the point of this why can't they use what we already standardized [Ericsson] this is about the architecture, what is missing is how to use the external entity | Ericsson | LS out | Approval | Yes | Yes | open | No | draft_S3-210343-r1
|  | S3‑210344 | Resolving EN on SUPI privacy in solution #1 |  | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210406 | LS on Feedback on Key Issue #4 "UE onboarding and remote provisioning" | [Ericsson] r1 available based on offline discussion [Vfe] requires more time [Orange] proposes to wait before approval [Ericsson] intention is to agree on some feedback before the end of the meeting | Ericsson | LS out | Approval | Yes | Yes | open | No | draft_S3-210406-r1
|  | S3‑210232 | Solution Update for Solution #5 |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210346 | High-level conclusions for KI#1 (Credentials owned by an external entity) | [Nokia] requires clarifications [Huawei] requires clarifications and prefers 494 [CableLabs] objects [Lenovo] questions the use of extra NF for proxying AAA messages | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210233 | System Impact and Evaluation for solution #5 |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210372 | NPN: New solution to key issue #1 | [Nokia] asks for clarifications | Huawei, Hisilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210340 | High-level conclusions for KI#1 (Credentials owned by an external entity) |  | Ericsson | discussion | Discussion | Yes | No | available | No
|  | S3‑210431 | Update of solution #6 |  | Lenovo, Motorola Mobility | pCR | Approval | Yes | No | available | No
|  | S3‑210341 | Resolving EN in KI#1 |  | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210432 | Evaluation of solution #6 |  | Lenovo, Motorola Mobility | pCR | Approval | Yes | No | available | No
|  | S3‑210493 | Addressing the EN in solution #4 | [Huawei] requires modification and clarifications | Qualcomm Incorporated | pCR | Approval | Yes | No | available | No
|  | S3‑210494 | pCR: Security architecture conclusion for KI #1 | [Ericsson] proposes to merge with 346 and requires clarifications [CableLabs] objects and points to thread 346 | Qualcomm Incorporated | pCR | Approval | Yes | No | available | No
|  | S3‑210402 | Adding details to provisioning key issue | [Ericsson] proposes for preliminary decision during cc [Orange] 1st req ok but second one ok if we are not define any mechanism. It will be difficult to define a particular protocol that can cover all the use cases [Philips] we need at least one solution that works [Huawei] we discussed this in the past and the point is not to define a new protocol but how to secure it [Orange] we need to have a dedicated call [Ericsson] agrees with Huawei comment [Philips] SA1 addresses the enterprise requirement not SA3 [ZTE] we need to define the requirement this is not about the solution [Orange] we need to define the boundary for the requirement but still the second requirement is not really in scope [Ericsson] we need to progress this to provide feedback to SA2 [Vfe] supports Orange comments | Ericsson, China Mobile, Huawei, InterDigital, Lenovo, Motorola Mobility, Nokia, Nokia Shanghai Bell, Philips, Samsung, ZTE | pCR | Approval | Yes | Yes | open | No
|  | S3‑210318 | Solution to provisioning of PNI-NPN credentials |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210403 | Use case for KI#3 (Supporting IMS in SNPNs) not yet covered by existing specifications | [Huawei] proposes to note comments this is not inline with SA2 conclusion [Thales] proposes to note [Ericsson] disagrees and argues such a conclusion is in SA3 remits | Ericsson | discussion | Endorsement | Yes | No | available | No
|  | S3‑210404 | New Solution to KI#3: Authentication to IMS Core using credentials generated with AKMA | [Huawei] proposes to note as commented on 403 [Thales] proposes to note | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210405 | New Solution to KI#3: Authentication to IMS Core using credentials generated from the KAUSF | [Huawei] proposes to note as commented on 403 [Thales] proposes to note | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210136 | Solution for protecting the privacy of the UE identity. | [Ericsson] proposes editorials and requires clarifications on the trust relationships [Nokia] comments [Huawei] requires clarifications and changes [Nokia] revision available | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | revised | No | draft_S3-210136-r1
|  | S3‑210176 | Evaluation of Solution #8 | [Ericsson] proposes changes to the evaluation clause [Huawei] requires changes [ZTE] r1 available | ZTE Corporation | pCR | Approval | Yes | No | revised | No | draft_S3-210176-r1
|  | S3‑210177 | Evaluation of Solution #9 | [Ericsson]proposes additions in the evaluation clause [Huawei] requires changes [ZTE] r1 available | ZTE Corporation | pCR | Approval | Yes | No | revised | No | draft_S3-210177-r1
|  | S3‑210220 | New solution on UE onboarding for SNPN with the interaction between PS and DCS | [Ericsson] requires updates [Alibaba] r1 available | Alibaba Group | pCR | Approval | Yes | No | revised | No | draft_S3-210220-r1
|  | S3‑210231 | New Solution on Authentication for UE onboarding for SNPN | [Ericsson] requires changes and clarifications [Huawei] comments | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210277 | Solution to UE onboarding for non-public networks | [Ericsson] requires updates [Intel] comments [Huawei] asks for clarifications on the use of EAP-TTLS [Thales] asks for clarifications | Intel Corporation (UK) Ltd | pCR | Approval | Yes | No | available | No
|  | S3‑210280 | Solution to UE onboarding for non-public networks using PA and SA | [Huawei] requires clarifications and updates [Intel] comments [Thales] asks for clarifications | Intel Corporation (UK) Ltd | pCR | Approval | Yes | No | available | No
|  | S3‑210407 | Resolving SUPI privacy EN in solution #10 |  | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210408 | Resolving prerequisite EN in solution #10 | [Huawei] proposes to note | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210409 | Resolving indication EN in solution #10 |  | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210410 | Resolving CP provisioning EN in solution #10 |  | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210495 | Addressing some ENs in solution #11 |  | Qualcomm Incorporated | pCR | Approval | Yes | No | available | No
|  | S3‑210218 | New Key Issue on UE preferred SNPN information update | [Ericsson] requires updates | Alibaba Group | pCR | Approval | Yes | No | available | No
|  | S3‑210219 | New solution on preferred SNPN information update | [Ericsson] objects and requires updates | Alibaba Group | pCR | Approval | Yes | No | available | No
|  | S3‑210352 | New KI on service authorization for SNPNs | [Ericsson] proposes changes | Huawei, Hisilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210353 | New solution on service authorization for SNPNs | [Ericsson] proposes Ens | Huawei, Hisilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210126 | TR 33.857: scope | [Ericsson] agrees and proposes minor editorials [Thales] r1 available [Ericsson] fine r1 for approval against 2nd challenge | THALES | pCR | Approval | Yes | Yes | approved | No | draft_S3-210126-r1
5.13 | Study on security aspects of the Disaggregated gNB Architecture | S3‑210061 | Discussion on Conclusion to TR 33.840 |  | Futurewei | discussion | Endorsement | Yes | No | available | No
|  | S3‑210062 | Conclusion to TR 33.840 | [Samsung] Disagree with the reasoning proposed for concluding the SID [Futurewei] propose a simpler text for conclusion [Nokia] Original #62 is not agreeable. A proper reasoning to close the study need to be captured. [Lenovo] conclusion proposed in S3-210062 is not acceptable with its current text [Futurewei] provides clarification [Lenovo] provides further comments [Nokia] provides minor correction to the conclusion text [Mavenir] provides comments [Nokia] comments [Futurewei] provides clarification [Mavenir] disagree with this very high level generalization and over simplification [Samsung] agrees with Mavenir and suggest minor updates to the final statement [China Telecom] need to inform RAN3 [Lenovo] proposes the following minor update over Samsung’s proposal | Futurewei | pCR | Approval | Yes | No | available | No
|  | S3‑210063 | LS on conclusion of security study of disaggregated gNB architecture |  | Futurewei | LS out | Approval | Yes | No | available | No
|  | S3‑210278 | Conclusions to TR33.840 | [Samsung] Disagree with the reasoning proposed for concluding the SID [China Telecom] fine with the changes proposed, if everyone is fine [Nokia] Disagree with the reasoning proposed for conclusion. Proposes amendments to the text on reasoning. [China Telecom] Provides r1 [Lenovo] Not acceptable with the earlier proposal. Fine with r1. [Samsung] find with r1 [Huawei] concern about the second sentence of r01 | China Telecommunications | pCR | Approval | Yes | No | revised | No | draft_S3-210278-r1
5.14 | Study on User Consent for 3GPP services | S3‑210088 | Discussion on user versus subscriber in relation to the U3C study |  | Futurewei | discussion | Endorsement | Yes | No | available | No
|  | S3‑210089 | KI on U3C User Identification |  | Futurewei | pCR | Approval | Yes | No | available | No
|  | S3‑210117 | TR 33.867 – New KI – Confidentiality Protection |  | InterDigital, Inc. | pCR | Approval | Yes | No | available | No
|  | S3‑210118 | TR 33.867 – New KI – User Authentication |  | InterDigital, Inc. | pCR | Approval | Yes | No | available | No
|  | S3‑210119 | TR 33.867 – New KI – Replay Protection |  | InterDigital, Inc. | pCR | Approval | Yes | No | available | No
|  | S3‑210120 | TR 33.867 – New KI – Integrity Protection |  | InterDigital, Inc. | pCR | Approval | Yes | No | available | No
|  | S3‑210121 | TR 33.867 – New KI – Non-Repudiation |  | InterDigital, Inc. | pCR | Approval | Yes | No | available | No
|  | S3‑210187 | Add new key issue for user consent | [Huawei] proposes to revise | CATT | pCR | Approval | Yes | No | available | No
|  | S3‑210324 | New Use Case for eNA |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210226 | New Use Case for MEC |  | Huawei, HiSilicon, Samsung | pCR | Approval | Yes | No | available | No
|  | S3‑210227 | Add Terms for UC3S |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210228 | Analysis for UC3S |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210275 | New skeleton to TR 33867 |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210028 | LS on propagation of user consent related information during Xn inter-PLMN handover |  | R3-204378 | LS in |  | Yes | Yes | open | No
|  | S3‑210026 | Reply LS on the user consent for trace reporting | [chair] proposes to note [Huawei] we are in the cc only so we can note | R2-2010894 | LS in |  | Yes | Yes | open | No
|  | S3‑210301 | Reply LS on propagation of user consent related information during Xn inter-PLMN handover | [Huawei] proposes to note | Ericsson Limited | LS out | Approval | Yes | Yes | open | No
5.15 | Study on security aspects of the 5GMSG Service | S3‑210319 | Authentication and Authorization between 5GMSGS Client and MSGin5G server based on AKMA |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210320 | Overview of MSGin5G Service |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210454 | Update to KI#4 in TR 33.862 | [Huawei] provides comments [Samsung] fine with the suggested text [Samsung] provides r1 [Huawei] r1 looks fine | Samsung | pCR | Approval | Yes | No | available | No
|  | S3‑210455 | Authentication and authorization for MSGin5G UE | [Huawei] provides comments [Samsung] fine with the suggested Editor's Note [Samsung] provides r1 [Huawei] r1 looks fine | Samsung | pCR | Approval | Yes | No | available | No
|  | S3‑210456 | Authentication and authorization for legacy UE | [Huawei] provides comments [Samsung] fine with the suggested Editor's Note [Huawei] provides further comments [Samsung] provides r1 [Huawei] suggest updates | Samsung | pCR | Approval | Yes | No | available | No
|  | S3‑210457 | Authentication and authorization for Non-3GPP UE | [Huawei] provides comments [Samsung] fine with the suggested Editor's Note [Samsung] provides r1 [Huawei] suggest updates. Fine if updates are included | Samsung | pCR | Approval | Yes | No | available | No
5.16 | Study on security aspects of enablers for Network Automation (eNA) for the 5G system (5GS) Phase 2 | S3‑210105 | TR 33866-020_update on formats and typos | [Ericsson] to propose editorials [Nokia] proposes to merge with 188, in 188 thread [Nokia] provides r1 | Nokia, Nokia Shanghai Bell, China Mobile | pCR | Approval | Yes | Yes | revised | No | draft_S3-210105-r1
|  | S3‑210106 | Abbreviations.doc | [Huawei] there might be mistakes [Ericsson] proposes editorials [Nokia] provides r1 [Huawei] proposes more editorials | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | Yes | revised | No | draft_S3-210106-r1
|  | S3‑210188 | Add references in TR 33.866 | [Nokia] formatting issues [CMCC] proposes to be merged into S3-210105 [Nokia] proposes to merge into S3-210105 [CATT] agrees to merge into 105 to be merged in 105? | CATT | pCR | Approval | Yes | Yes | open | No
|  | S3‑210012 | Reply-LS on user consent requirements for analytics | [chair] proposes to postpone [Docomo] we can't reply this [Ericsson] we need to reply on this juridiction aspects [Docomo] to hold the pen to be replied to in 210012 | S2-2009383 | LS in |  | Yes | Yes | open | No
|  | S3‑210021 | LS on method for collection of data from the UE | [Nokia] we need the feedback on the solutions to be replied to in 210492 | S2-2006292 | LS in |  | Yes | Yes | open | No
|  | S3‑210032 | Reply on method for collection of data from the UE | [chair] proposes to note [CMCC] ok to note since no actions to SA3 | S4-201584 | LS in |  | Yes | Yes | open | No
|  | S3‑210492 | Reply LS method for collection of data from the UE | [Ericsson] proposed rewording but no reply yet | Qualcomm Incorporated | LS out | Approval | Yes | Yes | open | No
|  | S3‑210112 | KI on UE data collection protection |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210113 | Threats and requirements to KI on UE data collection protection |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210114 | Solution on UE data collection protection.docx |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210115 | Requirements to KI on Processing of tampered data |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210116 | KI on Authorization of consumers for data access via DCCF.doc | [Huawei] asks for clarifications on how this is different compared to indirect communication in eSBA [Nokia] unlike SCP DCCF does not relay responses as well [Huawei] let's discuss more and if existing mechanisms are sufficient then there is no need for a KI [Nokia] but that is the point of a study | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | Yes | open | No
|  | S3‑210189 | Add new key issue in TR 33.866 |  | CATT | pCR | Approval | Yes | No | available | No
|  | S3‑210446 | [eNA]Updates to KI #1.1 |  | Samsung | pCR | Approval | Yes | No | available | No
|  | S3‑210498 | Key issue on security of data via Messaging Framework | [Lenovo] what kind of framework is this? [Huawei] is this defined in SA2 [Ericsson] yes and it is already in the conclusion [Docomo] if this is not standardized then the requirement should be clarified in terms of what need to be standardized [Apple] not aware of this framework bt the requirments imply impact on this framework or? [Docomo] is it expected to hide the message for the DCCF? [Nokia] it seems that this is not known to everybody, the DCCF is doing "coordination" functionalities between consumers and producers [Lenovo] the requirement addresses the transport of data so is the intention to study solutions for that | Ericsson | pCR | Approval | Yes | Yes | open | No
|  | S3‑210109 | KI details on Anomalous NF behaviour detection by NWDAF |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210110 | Threats on KI Anomalous NF behavior detection by NWDAF |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210111 | Requirements on KI Anomalous NF behavior detection by NWDAF | [Huawei] requires clarification | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210229 | New Solution for Network Framework for DDoS Attack |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210317 | Solution to botnet terminal detection |  | China Mobile | pCR | Approval | Yes | No | available | No
|  | S3‑210419 | Analytics for MitM Attack Detection |  | Lenovo, Motorola Mobility | pCR | Approval | Yes | No | available | No
|  | S3‑210107 | KI on protection of data in transfer | [Huawei] proposes to revise [Ericsson] proposes to revise as Huawei suggested [Nokia] replies [Huawei] proposes to remove aspects not realted to data transfer [Nokia] we can have a spearate key issue [Huawei] prefers a separate key issue | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | Yes | open | No
|  | S3‑210108 | Usage of current SBA mechanisms to protect data in transfer | [Huawei] proposes to add EN [Ericsson] requires clarification [Nokia] replies with clarification to both Ericsson and Huawei | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
5.17 | Study on the security of AMF re-allocation | S3‑210525 | Discussion paper on the shared network entity assumptions for the AMF re-allocation security study |  | Ericsson | discussion | Endorsement | Yes | No | available | No
|  | S3‑210526 | Shared network entity assumptions for the purpose of AMF re-allocation | [Lenovo] contribution requires clarifications and update [Ericsson] merge with 0531? [Lenovo] can merge 0531(r1) in 0526 [Nokia] propose to Note 0526 [Ericsson] withdraw the proposal to merge 0526 and 0531. | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210531 | Resolving EN in Clause 4.3 Architecture and Security Assumptions | [Lenovo] provides r1 | Lenovo, Motorola Mobility | pCR | Approval | Yes | No | revised | No | draft_S3-210531-r1
|  | S3‑210473 | Update of solution #1 in TR 33.864 | [Huawei] provides comments [Lenovo] Requires clarification and update [Ericsson] contribution needs some changes | Qualcomm Incorporated | pCR | Approval | Yes | No | available | No
|  | S3‑210524 | AMF reallocation: Update to solution #2 | [Huawei] provides comments [Lenovo] contribution requires clarification and update [Qualcomm] thinks solution requires update | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210373 | AMFReal: Updates to solution #3 | [Lenovo] Requires clarification and update [Huawei] provides r1 [Ericsson] few more changes needed [Lenovo] r1 does not fully captures the required updates [Huawei] provides clarifications | Huawei, Hisilicon | pCR | Approval | Yes | No | revised | No | draft_S3-210373-r1
|  | S3‑210150 | AMF re-allocation Solution#4 | [Lenovo] provides clarification [Nokia] concern not addressed [Lenovo] agrees to have the Nokia proposed ENs. | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210533 | Update to Solution#4 on enabling security during AMF reallocation via RAN | [Huawei] provides comments [Ericsson] provides comments [Lenovo] provides r1 [Nokia] propose Editor's Notes [Huawei] provides clarifications [Lenovo] provides r2 [Huawei] provides comments [Ericsson] provides further comments [Lenovo] provides clarification [Ericsson] proposed EN is fine with me. Yet to check r2. [Lenovo] provides r3 | Lenovo, Motorola Mobility | pCR | Approval | Yes | No | revised | No | draft_S3-210533-r2
|  | S3‑210178 | New solution on security of AMF re-allocation using Registration Reject message | [Huawei] provides comments [Lenovo] Requires clarification and update [Ericsson] indicates solution needs clarifications and provide comments/questions [ZTE] contribution to be noted | ZTE Corporation | pCR | Approval | Yes | No | available | No
|  | S3‑210179 | New solution on security of AMF re-allocation using RRC Release message | [Lenovo] Requires clarification and update [Huawei] provides comments [Ericsson] comments [ZTE] contribution to be noted | ZTE Corporation | pCR | Approval | Yes | No | available | No
|  | S3‑210461 | pCR: AMF re-allocation by re-directing UE to new AMF | [Huawei] provides comments [Samsung] provides clarifications [Lenovo] provides comments and ask questions for clarification [Huawei] suggest inclusion of the Editor's Notes [Samsung] provides r1 [Lenovo] fine with r1 [Huawei] fine with r1 | Samsung | pCR | Approval | Yes | No | available | No
|  | S3‑210527 | New solution for NAS re-route via RAN and the use of a well-connected network function | [Lenovo] contribution requires clarification and update [Nokia] propose to Note the contribution [Ericsson] provides clarification | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210528 | New solution for AMF re-allocation using a well-connected network function | [Huawei] disagrees with the solution and proposes to note [Lenovo] current version of the solution is not agreeable and requires further clarification [Ericsson] provides clarification [Huawei] provides further comments [Ericsson] provides clarification [Lenovo] comments | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210534 | Solution to ensure system availability for indirect AMF reallocation | [Ericsson] have concerns about this contribution and proposes to note it. [Lenovo] provides clarification [Ericsson] asks a question [Lenovo] provides clarification [Qualcomm] provides comments [Lenovo] provides clarification [Ericsson] comments | Lenovo, Motorola Mobility | pCR | Approval | Yes | No | available | No
|  | S3‑210374 | AMFReal: Updates to TR 33.864 | [Lenovo] we have comments so let's wait with the decision [Lenovo] Requires clarification and update. [Huawei] provides clarifications | Huawei, Hisilicon | pCR | Approval | Yes | Yes | open | No
5.18 | Study on Security for NR Integrated Access and Backhaul | S3‑210283 | F1 interface security for IAB in NR-DC mode |  | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210284 | updating the scope in TR33.824 | [Qualcomm] requires clarification [Samsung] this is fine (as a rapporteur) maybe with a clear indication as this is for Rel-17 [Nokia] agrees this needs some discussion to record the release/scope relation | Huawei, HiSilicon | pCR | Approval | Yes | Yes | open | No
5.19 | Study on the security of the system enablers for devices having multiple Universal Subscriber Identity Modules | S3‑210029 | Reply LS on System support for Multi-USIM devices | [chair] proposes to note [Intel] fine to note and we have sent a similar LS indicating we will study and provide feedback once conclusions are made | R3-207207 | LS in |  | Yes | Yes | open | No
|  | S3‑210145 | Key Issue on privacy issues relating to Paging Cause exposure | [Intel] proposes to revise [Huawei] proposes to merge into 418 [Nokia] proposes to merge 418 with this one. [Huawei] is fine to merge 418 into 145 | Nokia, Nokia Shangahi Bell, Samsung | other | Approval | Yes | No | available | No
|  | S3‑210147 | Secure Busy indication |  | Nokia, Nokia Shanghai Bell | other | Approval | Yes | No | available | No
|  | S3‑210209 | Security Solution for Busy Indication using NAS signaling |  | Intel Corporation (UK) Ltd | other | Approval | Yes | No | available | No
|  | S3‑210210 | Updates to key issue 2 |  | Intel Corporation (UK) Ltd | other | Approval | Yes | No | available | No
|  | S3‑210213 | MUSIM-key issue on BUSY indication |  | Apple | pCR | Approval | Yes | No | available | No
|  | S3‑210214 | MUSIM-Solution to protect BUSY indication | [Intel] proposes to merge into 209 | Apple | pCR | Approval | Yes | No | available | No
|  | S3‑210418 | New key issue for Paging Cause protection | [Intel] proposes to note or merged into 145 to be merged in 145? | Huawei, HiSilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210462 | Key Issue on Authorization for MUSIM optimizations |  | Samsung | pCR | Approval | Yes | No | available | No
5.20 | Study on enhanced Security Aspects of the 5G Service Based Architecture | S3‑210414 | New KI: Roaming case for token-based authorization in indirect communication |  | Ericsson | pCR | Approval | Yes | No | available | No
|  | S3‑210416 | KI on Verification of UE in subscription and notification in the delegated "Subscribe-Notify" scenarios |  | Huawei, Hisilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210417 | KI on Verification of UE in subscription and notification in the non-delegated "Subscribe-Notify" scenarios |  | Huawei, Hisilicon | pCR | Approval | Yes | No | available | No
|  | S3‑210420 | Skeleton of TR eSBA SEC | [Huawei] proposes to add mapping table [Vfe] maybe this table could be brought later [Nokia] no solutions yet [Docomo] let's put ths as an action to the rapporteur and go ahead with the skeleton | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | Yes | approved | No
|  | S3‑210421 | Introduction | [Ericsson] comments on cross certification-related statements | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | Yes | open | No
|  | S3‑210422 | Scope | [Vfe] wrong tense | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | Yes | open | No
|  | S3‑210423 | Authentication of NRF and NFp in indirect communication |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210424 | End-to-end authentication in roaming case |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210425 | SCP deployment models |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210426 | Verification of URI in subscription and notification |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210427 | Dynamic authorization between SCPs or between NF and SCP |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210428 | End-to-End Critical HTTP headers and body parts integrity protection |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
|  | S3‑210429 | NRF service management |  | Nokia, Nokia Shanghai Bell | pCR | Approval | Yes | No | available | No
5.21 | New study item proposals | S3‑210195 | Discussion paper for Rel17 SID on network slicing security |  | Huawei, HiSilicon, Lenovo, Motorola Mobility, CableLab, CATT, CAICT, China Unicom, China Mobile, InterDigital, NEC | discussion | Discussion | Yes | No | available | No
|  | S3‑210196 | Rel17 SID on network slice security |  | Huawei, HiSilicon, Lenovo, Motorola Mobility, CableLab, CATT, CAICT, China Unicom, China Mobile, InterDigital, NEC | SID new | Approval | Yes | Yes | withdrawn | Yes
|  | S3‑210295 | UC3S_SID_revision |  | Huawei, HiSilicon | SID revised | Approval | Yes | No | available | No
|  | S3‑210298 | New SID on security aspects on PAP/CHAP protocols in 5GS |  | China Telecom, Huawei, HiSilicon | SID new | Approval | Yes | No | available | No
|  | S3‑210539 | Rel17 SID on network slice security |  | Huawei, HiSilicon, Lenovo, Motorola Mobility, CableLab, CATT, CAICT, China Unicom, China Mobile, InterDigital, NEC | SID new | Approval | Yes | No | available | No
5.22 | Other study areas (no release restrictions)
6 | CVD and research
7 | Any Other Business | S3‑210553 | SA3 meeting calendar |  | WG Chair | other | Information | No | No | reserved | No
|  | S3‑210554 | Draft agenda for SA3 102bis-e |  | WG Chair | agenda | Discussion | No | No | reserved | No