## AgendaWithTdocAllocation_2020-0
Tdoc List |  |  | Ready!
2020-04-17 16:41
Agenda | Topic | TDoc | Title | Notes | Source | Type | For | Avail | Treated | Decision | Wdrn | Replaced-by | Replaces
1 | Agenda and meeting objectives | S3‑200600 | Agenda | deadline: 1st challenge | WG Chair | agenda |  | Yes | No | approved | No
|  | S3‑200793 | Process for SA3#98bis-e meeting | actions: change source to WG Chair | Ericsson LM | other | Information | Yes | No | noted | No
2 | Main work areas
2.1 | Mission Critical security (Rel-16) | S3‑200628 | Reply LS on how the IWF obtains key material for interworking group and private communications | actions: [MSI] reply in 649 | S6-192194 | LS in |  | Yes | Yes | replied to | No
|  | S3‑200644 | [33.180] R16 Fix first-to-answer | comments: [Samsung] not pursued | Motorola Solutions UK Ltd. | CR | Agreement | Yes | Yes | not pursued | No
|  | S3‑200645 | [33.179] R13 token scope fix | actions: convert to a draftCR | Motorola Solutions UK Ltd. | CR | Agreement | Yes | Yes | not pursued | No | draft_S3-200645-r1
|  | draft_S3-200645-r1 | [33.179] R13 token scope fix | deadline: 1st challenge | Motorola Solutions UK Ltd. | draftCR | Agreement | Yes | Yes | approved | No |  | S3‑200645
|  | S3‑200646 | [33.180] R16 Fix IdM client terminology | actions: convert to a draftCR | Motorola Solutions UK Ltd. | CR | Agreement | Yes | Yes | not pursued | No | draft_S3-200646-r1
|  | draft_S3-200646-r1 | [33.180] R16 Fix IdM client terminology | deadline: 1st challenge | Motorola Solutions UK Ltd. | draftCR | Agreement | Yes | Yes | approved | No |  | S3‑200646
|  | S3‑200647 | [33.180] R16 Fix XML references | actions: convert to a draftCR | Motorola Solutions UK Ltd. | CR | Agreement | Yes | Yes | not pursued | No | draft_S3-200647-r1
|  | draft_S3-200647-r1 | [33.180] R16 Fix XML references | deadline: 1st challenge | Motorola Solutions UK Ltd. | draftCR | Agreement | Yes | Yes | approved | No |  | S3‑200647
|  | S3‑200648 | [33.180] R16 TrK-ID and InK-ID indication | actions: convert to a draftCR | Motorola Solutions UK Ltd. | CR | Agreement | Yes | Yes | not pursued | No | draft_S3-200648-r1
|  | draft_S3-200648-r1 | [33.180] R16 TrK-ID and InK-ID indication | deadline: 1st challenge | Motorola Solutions UK Ltd. | draftCR | Agreement | Yes | Yes | approved | No |  | S3‑200648
|  | S3‑200649 | SA3 Reply LS on how the IWF obtains key material for interworking group and private communications | deadline: 1st challenge | Motorola Solutions UK Ltd. | LS out | Agreement | Yes | Yes | approved | No
2.2 | Security of the enhancement to the 5GC location services | S3‑200621 | Response LS on Enhancing Location Information Reporting with Dual Connectivity | actions: note | R3-201249 | LS in |  | Yes | Yes | noted | No
|  | S3‑200626 | LS on enhancing location information reporting with Dual Connectivity | actions: note | S2-2002422 | LS in |  | Yes | Yes | noted | No
|  | S3‑200641 | eLCS NOTE Clarification | comments: [DCM] note | Futurewei | other | Approval | Yes | Yes | noted | No
|  | S3‑200698 | Draft CR as a living baseline for 5GS LCS normative work |  | CATT | draftCR | Approval | Yes | No | approved | No
|  | S3‑200702 | Removing ENs in Draft CR as a living baseline for 5GS LCS normative work | actions: [Hw] merge with 720 [DCM] note | CATT | draftCR | Approval | Yes | Yes | noted | No
|  | S3‑200720 | Add clarifications to the living CR | comments: [DCM, Orange, BRCM] do not agree (should) [QC, BRCM] concerns (emergency) | Huawei, Hisilicon | draftCR | Approval | Yes | No | noted | No
|  | S3‑200732 | Draft LS on security of eLCS | comments: [DCM] postpone | Huawei, Hisilicon | LS out | Approval | Yes | Yes | noted | No
|  | S3‑200750 | Resolving ENs in Draft CR | actions: [Hw] merge with 720 [DCM] note | Ericsson | draftCR | Agreement | Yes | Yes | noted | No
|  | S3‑200751 | [DRAFT] LS on security of eLCS | comments: [DCM] postpone | Ericsson | LS out | Approval | Yes | Yes | noted | No
|  | S3‑200791 | eLCS privacy discussion on way forward | comments: [Hw] concerns [E///] p1, p2, p3 not ok [CATT] concerns | NTT DOCOMO | discussion | Endorsement | Yes | Yes | noted | No
2.3 | Security Aspects of the 5G Service Based Architecture (Rel-16) | S3‑200613 | Authentication between network functions and the NRF in indirect communication | comments: [Mav, CableLabs] not pursued | Ericsson | draftCR | Approval | Yes | Yes | noted | No
|  | S3‑200614 | Token-based authorization in Scenario D | comments: [Mav, CableLabs] not pursued | Ericsson | draftCR | Approval | Yes | Yes | noted | No
|  | S3‑200616 | LS on Misalignment on HTTP connections for N32-c and on N32-f contexts termination |  | C4-200781 | LS in |  | Yes | Yes | withdrawn | Yes
|  | S3‑200617 | LS on Misalignments on N32-f context Id |  | C4-200782 | LS in |  | Yes | Yes | withdrawn | Yes
|  | S3‑200660 | Way forward on authentication and authorization in SBA | comments: [E///] note [CableLabs] withdraw | CableLabs | discussion | Endorsement | Yes | Yes | noted | No
|  | S3‑200662 | Validation of Access Token ownership requirement | comments: [E///] not pursued | Mavenir,Deutsche Telekom | CR | Approval | Yes | Yes | not pursued | No
|  | S3‑200663 | Discussion End-2-End Access Token ownership validation | comments: [E///] note | Mavenir,Deutsche Telekom | discussion | Endorsement | Yes | Yes | noted | No
|  | S3‑200664 | end-2-end client authentication during Indirect communication | comments: [E///] note | Mavenir,Deutsche Telekom | discussion | Endorsement | Yes | Yes | noted | No
|  | S3‑200665 | Clarification of Token-based authorization | comments: [E///] not pursued | Mavenir,Deutsche Telekom | CR | Approval | Yes | Yes | not pursued | No
|  | S3‑200666 | Clarification of Indirect Communication Mutual Authentication | comments: [E///] merge with 613 [Hw, CableLabs] merge with 686 agreement: NF to NRF auth could be based on direct mutual TLS or hop-by-hop TLS | Mavenir,Deutsche Telekom | CR | Approval | Yes | Yes | noted | No
|  | S3‑200686 | Trust mode in the eSBA | comments: [E///] merge with 613 [Hw] merge with 666 | Huawei, Hisilicon | CR | Approval | Yes | Yes | not pursued | No
|  | draft_S3-200686-r2 | Trust mode in the eSBA |  | Huawei, Hisilicon | draft CR | Approval | Yes | Yes | left for email approval | No
|  | S3‑200687 | eSBA: Discussion on the subscribe/notify issue | comments: [E///] note [Mav] concerns [Nokia, Mav] supports the threat | Huawei, Hisilicon | discussion | Endorsement | Yes | Yes | noted | No
|  | S3‑200688 | Authorization in the Subscribe-Notify interaction scenarios | comments: [E///] not pursued | Huawei, Hisilicon | CR | Approval | Yes | Yes | not pursued | No
|  | S3‑200689 | Clarification on NF consumer instance ID verification | comments: [E///] not pursued | Huawei, Hisilicon | CR | Approval | Yes | Yes | not pursued | No
|  | S3‑200792 | Token based authorization in model D - Scenario 1 | comments: [E///] merge with 614 [Mav] not pursued | Nokia, Nokia Shanghai Bell | draftCR | Approval | Yes | Yes | not pursued | No
|  | S3‑200794 | Token based authorization in model D - Scenario 2 | comments: [E///] revise [Mav] not pursued | Nokia, Nokia Shanghai Bell | draftCR | Approval | Yes | Yes | not pursued | No
|  | S3‑200795 | Authentication between Network Functions | comments: [E///] merge with 613 [Mav] not pursued | Nokia, Nokia Shanghai Bell | draftCR | Approval | Yes | Yes | noted | No
|  | S3‑200796 | Authentication between NRF and NF | comments: [E///] merge with 613 [Mav] not pursued | Nokia, Nokia Shanghai Bell | draftCR | Approval | Yes | Yes | noted | No
|  | S3‑200797 | Access token ownership in Direct communication scenarios | comments: [E///] note | Nokia, Nokia Shanghai Bell | draftCR | Approval | Yes | Yes | noted | No
|  | S3‑200798 | Access token ownership in Indirect communication scenarios | comments: [E///] note [Mav] not pursued | Nokia, Nokia Shanghai Bell | draftCR | Approval | Yes | Yes | noted | No
|  | S3‑200799 | Token based authorization in model D |  | Nokia, Nokia Shanghai Bell | draftCR | Approval | Yes | No | withdrawn | No
|  | S3‑200800 | SBA Network Function certificate profile | comments: [DCM] revise [Hw] not pursued | Nokia, Nokia Shanghai Bell | draftCR | Approval | Yes | Yes | noted | No
|  | S3‑200801 | Discussion paper on authentication for indirect communication | comments: [E///] note | Nokia, Nokia Shanghai Bell | discussion | Endorsement | Yes | Yes | noted | No
2.4 | Authentication and key management for applications based on 3GPP credential in 5G (Rel-16) | S3‑200606 | AKMA-Derivation of the KAF | comments: [CMCC] merge with 774 [QC] note | Apple | pCR | Approval | Yes | Yes | noted | No
|  | S3-209999 | draft TS 33.535 |  | China Mobile | draft TS |  |  |  | left for email approval
|  | S3‑200607 | AKMA-KAF refreshment | comments: [CMCC, Hw] merge with 719 [QC] note | Apple | pCR | Approval | Yes | Yes | merged | No | draft_S3-200719-r7
|  | S3‑200608 | AKMA-Editorial on the 6.2 | comments: [QC] note | Apple | pCR | Agreement | Yes | Yes | noted | No
|  | S3‑200609 | AKMA-AAnF definition | comments: [QC] note | Apple | pCR | Information | Yes | Yes | noted | No
|  | S3‑200610 | AKMA-AKMA capability indication between UE and AF | comments: [E///] concerns [QC] concerns, note | Apple | pCR | Information | Yes | Yes | noted | No
|  | S3‑200640 | AKMA Application Key Requirement |  | Futurewei | pCR | Approval | Yes | No | approved | No
|  | S3‑200661 | TS 33.535 - Corrections |  | InterDigital, Inc. | pCR | Approval | Yes | No | approved | No
|  | S3‑200669 | Update clause 4.1 |  | ZTE Corporation | pCR | Approval | Yes | No | approved | No
|  | S3‑200670 | Update the figure in clause 6.1 | comments: [Samsung] concerns, [E///] concerns, note | ZTE Corporation | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200671 | Update the procedure in clause 6.2 | comments: [E///] concerns, note [QC] note | ZTE Corporation | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200672 | Store AUSF instance ID in UDM | comments: [E///, Thales] note | ZTE Corporation | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200673 | Defining AKMA key identifier for AKMA Anchor Key on demand procedures | comments: [E///, QC] do not agree | ZTE Corporation | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200674 | AKMA anchor Key push | comments: [E///] concerns [QC, HW, CMCC] do not agree | ZTE Corporation | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200675 | AKMA anchor Key update notification | comments: [Hw] note | ZTE Corporation | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200676 | Processing of KAKMA failure from AUSF to AAnF | comments: [E///, QC] note | ZTE Corporation | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200677 | Expire time in UE | comments: [QC] note | ZTE Corporation | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200678 | Derivation of KAF | comments: [CMCC] merge with 774 [QC] note | ZTE Corporation | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200679 | KAF update | comments: [Samsung, CMCC] do not agree [Apple] supports [QC] note | ZTE Corporation | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200703 | Discussion paper to support AKMA progress |  | Samsung | discussion |  | Yes | Yes | noted | No
|  | S3‑200704 | AKMA key ID derivation | comments: [E///] concerns [HW, ZTE] supports [QC, DCM, E///] does not agree | Samsung | pCR |  | Yes | Yes | noted | No
|  | S3‑200705 | Key update procedure | comments: [E///, CMCC] concerns [QC] note [ZTE] supports | Samsung | pCR |  | Yes | Yes | noted | No
|  | S3‑200706 | KAF derivation and refresh | comments: [Hw] partially merge in 719 [Samsung] ok will revise [CMCC] merge with 774 [QC] note | Samsung | pCR |  | Yes | Yes | noted | No
|  | S3‑200707 | Authorization of AF in AKMA | comments: [E///] concerns [Hw] supports [QC] note | Samsung | pCR |  | Yes | Yes | noted | No
|  | S3‑200709 | Adding additional AF functionality in clause 4.2.2 | comments: [Fw, QC] concerns on 2nd req [CATT] ok will revise | CATT | pCR | Approval | Yes | Yes | revised | No | draft_S3-200709-r1
|  | draft_S3-200709-r1 | Adding additional AF functionality in clause 4.2.2 |  | CATT | pCR | Approval | Yes | Yes | approved | No |  | S3‑200709
|  | S3‑200710 | Adding UDM functionality in clause 4.2 | comments: [QC] note | CATT | pCR |  | Yes | Yes | noted | No
|  | S3‑200711 | Adding UE functionality in clause 4.2 | comments: [QC] note | CATT | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200712 | The details of the AKMA service subscription information confirmation | comments: [Samsung] revise [CATT] ok will revise [QC, E///] concerns | CATT | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200713 | Update Requirement on clause 4.3.1 | comments: [QC] note [Hw] note | Huawei, Hisilicon | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200714 | Lifetime of Kakma ID |  | Huawei, Hisilicon | pCR | Approval | Yes | No | approved | No
|  | S3‑200715 | Kakma ID format | comments: [QC, E///] revise [HW] ok to revise [Apple] concerns [Samsung] objects, ok | Huawei, Hisilicon | pCR | Approval | Yes | Yes | revised | No | draft_S3-200715-r4
|  | draft_S3-200715-r4 | Kakma ID format |  | Huawei, Hisilicon | pCR | Approval | Yes | Yes | approved | No |  | S3‑200715
|  | S3‑200716 | Kakma and Kakma ID derivation | comments: [E///, CMCC, QC] revise [ZTE] support [CMCC] note [Hw] note | Huawei, Hisilicon | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200717 | Store Kakma ID in the UDM | comments: [E///] concerns, note [Hw] note | Huawei, Hisilicon | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200718 | AUSF selection | comments: [E///] concerns, note, [Hw] note | Huawei, Hisilicon | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200719 | Add a new clause on AKMA key re-keying | comments: [Apple, CATT, Samsung, QC] revise | Huawei, Hisilicon | pCR | Approval | Yes | No | revised | No | draft_S3-200719-r7
|  | draft_S3-200719-r7 | Add a new clause on AKMA key re-keying |  | Huawei, Hisilicon | pCR | Approval | Yes | No | approved | No |  | S3‑200719
|  | S3‑200724 | Deriving AKMA Application key for a specific AF via NEF | comments: [E///] merge with 739 | Huawei, Hisilicon | pCR | Approval | Yes | No | merged | No | draft_S3-200739-r5
|  | S3‑200725 | Update to deriving AKMA Application key for a specific AF | comments: [E///] revise, ok [Hw] ok will revise | Huawei, Hisilicon | pCR | Approval | Yes | Yes | revised | No | draft_S3-200725-r1
|  | draft_S3-200725-r1 | Update to deriving AKMA Application key for a specific AF |  | Huawei, Hisilicon | pCR | Approval | Yes | Yes | approved | No |  | S3‑200725
|  | S3‑200726 | AUSF function in AKMA | comments: [E///] revise, ok [Hw] ok will revise | Huawei, Hisilicon | pCR | Approval | Yes | Yes | revised | No | draft_S3-200726-r1
|  | draft_S3-200726-r1 | AUSF function in AKMA |  | Huawei, Hisilicon | pCR | Approval | Yes | Yes | approved | No |  | S3‑200726
|  | S3‑200739 | AKMA AF key request via NEF | comments: [Hw] merge with 724, ok | Ericsson | pCR | Approval | Yes | Yes | revised | No | draft_S3-200739-r5
|  | draft_S3-200739-r5 | AKMA AF key request via NEF |  | Ericsson | pCR | Approval | Yes | Yes | approved | No |  | S3‑200739
|  | S3‑200740 | AKMA Architecture considerations |  | Ericsson | discussion | Discussion | Yes | Yes | noted | No
|  | S3‑200741 | pCR to TS 33.535: Update of the AKMA procedures | comments: [QC, ZTE] objects [HW] objects, revise [E///] note | Ericsson | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200769 | pCR : Requirements on AKMA Key Identifier | comments: [Apple] concerns [Orange, Samsung] revise [QC] ok will revise | Qualcomm Incorporated | pCR | Approval | Yes | Yes | revised | No | draft_S3-200769-r2 | S3‑200365
|  | draft_S3-200769-r2 | pCR : Requirements on AKMA Key Identifier |  | Qualcomm Incorporated | pCR | Approval | Yes | Yes | approved | No |  | S3‑200769
|  | S3‑200770 | pCR : AKMA Temporary UE Identifier | comments: [E///, DCM, Samsung] concerns [HW] supports partially [E///] note [QC] note | Qualcomm Incorporated | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200771 | Correction of FC values | comments: [QC, E///] revise | China Mobile | pCR | Approval | Yes | Yes | revised | No | draft_S3-200771-r1
|  | draft_S3-200771-r1 | Correction of FC values |  | China Mobile | pCR | Approval | Yes | Yes | approved | No |  | S3‑200771
|  | S3‑200772 | CR to TS 33.220-FC value allocations for AKMA | actions: convert to a draftCR [QC] note [Apple] supports [CMCC] | China Mobile | CR | Approval | Yes | Yes | not pursued | No
|  | S3‑200773 | Removing obsolete Editor’s Notes in TS 33.535 |  | China Mobile | pCR | Approval | Yes | No | approved | No
|  | S3‑200774 | Derivation of KAF | comments: [Samsung] revise [CMCC] ok will revise [Apple] supports [QC] note | China Mobile | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200775 | Meeting minutes of AKMA conference call on 31st March |  | China Mobile | other | Information | Yes | No | noted | No
2.5 | Evolution of Cellular IoT security for the 5G System (Rel-16) | S3‑200615 | LS on 5G-GUTI reallocation after paging of a UE in 5GMM-IDLE mode with suspend indication |  | C1-200967 | LS in |  | Yes | Yes | postponed | No
|  | S3‑200625 | Reply LS on 5G-S-TMSI Truncation Procedure |  | S2-2001248 | LS in |  | Yes | Yes | noted | No
|  | S3‑200667 | Procedure to transfer UE capability for UEs without AS Security | comments: [E///, QC] does not agree | Intel Corporation (UK) Ltd | discussion |  | Yes | Yes | noted | No
|  | S3‑200668 | Security of RRC UE capability transfer procedure in 5G for CIoT optimisation | comments: [E///, Nokia] does not agree | Intel Corporation (UK) Ltd | draftCR |  | Yes | Yes | noted | No
|  | S3‑200701 | Reply LS on 5G-GUTI reallocation after paging of a UE in 5GMM-IDLE mode with suspend indication | comments: [E///] does not agree [QC, HW, Nokia, InterDigital] supports | Samsung | LS out |  | Yes | Yes | noted | No
|  | S3‑200722 | Security handling for UP data protection for UP CIoT 5GS Opmitization | comments: [E///, Nokia] does not agree | Huawei, Hisilicon | draftCR | Approval | Yes | Yes | noted | No
|  | S3‑200723 | Discussion on protection of UE radio capability | comments: [E///] p1 ok, p2 and p3 not | Huawei, Hisilicon | discussion | Discussion | Yes | Yes | noted | No
|  | S3‑200733 | way forward on Calculation of shortResumeMAC-I | comments: [E///] does not agree [Nokia] concerns | Huawei, Hisilicon | discussion | Decision | Yes | Yes | noted | No
|  | S3‑200734 | Address EN for Calculation of ShortResumeMAC-I for UP 5GS CIoT Optimisation | comments: [E///, Nokia, QC] does not agree [Hw] ok to revise | Huawei, Hisilicon | draftCR | Approval | Yes | Yes | noted | No
|  | S3‑200735 | Draft LS to RAN2 and RAN3 inputs for ShortResumeMAC-I Calculation for UP 5GS CIoT Optimisation | comments: [E///] note | Huawei, Hisilicon | LS out | Approval | Yes | Yes | noted | No
|  | S3‑200736 | Draft Reply LS on 5G-S-TMSI Truncation Procedure |  | Huawei, Hisilicon | LS out | Approval | Yes | Yes | noted | No
|  | S3‑200744 | [Draft CR] Input to MESSAGE when calculating ShortResumeMAC-I in RRC Connection Suspend and Resume | comments: [Hw, QC] does not agree | Ericsson | draftCR | Agreement | Yes | Yes | noted | No
|  | S3‑200747 | Way forward for UE caps protection and NB-IoT Ues | comments: note | Ericsson | discussion | Endorsement | Yes | Yes | noted | No
|  | S3‑200748 | UE caps protection using AS security in EPS Rel-16 | comments: [Intel] does not agree [Hw, QC] note [Nokia] supports | Ericsson | CR | Agreement | Yes | Yes | noted | No
|  | S3‑200749 | UE caps protection using AS security in 5GS Rel-16 | comments: [Intel] does not agree [Hw, QC] note [Nokia] supports | Ericsson | CR | Agreement | Yes | Yes | noted | No
|  | S3‑200764 | Protection of UE radio capability transfer for UEs without AS security | comments: [E///] does not agree | Qualcomm Incorporated | other | Approval | Yes | Yes | noted | No |  | S3‑200357
|  | S3‑200765 | Way forward for UE radio capability protection without AS security | comments: [E///, Nokia] p1 ok, p2 not | Qualcomm Incorporated | discussion | Approval | Yes | Yes | noted | No
|  | S3‑200778 | DraftCR – Living document for supporting 5G CIoT security | comments: [E///] note | Ericsson | draftCR | Approval | Yes | Yes | noted | No
2.6 | Security of the Wireless and Wireline Convergence for the 5G system architecture (Rel-16) | S3‑200619 | Clarification on encryption requirements for AGF interfaces (N1, N2, N3) [WWC] | actions: postpone [Juniper] reply to [Hw, BT] postpone | BBF | LS in |  | Yes | Yes | postponed | No
|  | S3‑200627 | LS on uniqueness of PEI in certain FN-RG configurations | actions: postpone | S3i200069 | LS in |  | Yes | Yes | postponed | No
|  | S3‑200652 | AGF in 5GC trust domain |  | Juniper Networks, Ericsson | draftCR | Approval | Yes | No | approved | No
|  | S3-209999 | Living CR for 5WWC |  | Huawei | draftCR | Approval | Yes | No | left for email approval | No
|  | S3‑200752 | ERP for TNAP mobility | comments: [E///, Nokia] note [QC] revise | Lenovo, Motorola Mobility | CR | Approval | Yes | Yes | not pursued | No
|  | S3‑200779 | N5CW: editorial correction | comments: [E///, BRCM] note | THALES, ORANGE | draftCR | Approval | Yes | Yes | noted | No
|  | S3‑200783 | UE pre-configuration for non-3GPP access networks | comments: [Lenovo] revise deadline: 3rd challenge | THALES, ORANGE | draftCR | Approval | Yes | Yes | approved | No
2.7 | Security aspects of Enhancement of Network Slicing (Rel-16) | S3‑200622 | Reply LS on AUSF role in slice specific authentication | actions: replied to in 785 | S2-1910668 | LS in |  | Yes | Yes | replied to | No | draft_S3-200785-r4
|  | S3‑200657 | eNS Living CR Re-submission |  | Nokia, Nokia Shanghai Bell | draftCR | Approval | Yes | No | noted | No
|  | S3‑200658 | Slice Specific Authentication and Authrorization clauses | comments: [E///] concerns, ok | Nokia, Nokia Shanghai Bell | draftCR | Approval | Yes | Yes | revised | No | draft_S3-200658-r3
|  | draft_S3-200658-r3 | Slice Specific Authentication and Authrorization clauses |  | Nokia, Nokia Shanghai Bell | draftCR | Approval | Yes | Yes | left for email approval | No |  | S3‑200658
|  | S3‑200659 | draft_Reply LS to SA2 on AUSF role | actions: merge in 785 | Nokia, Nokia Shanghai Bell | LS out | Approval | Yes | Yes | merged | No | draft_S3-200785-r4
|  | S3‑200776 | Addessing EN on transmitting NSSAI to AAA | comments: [Nokia, E///] objects [QC] agrees with Nokia | China Mobile | draftCR | Approval | Yes | Yes | noted | No
|  | S3‑200777 | LS on transformation of S-NSSAI during NSSAA | comments: [Nokia] objects | China Mobile | LS out | Approval | Yes | Yes | noted | No
|  | S3‑200780 | [DRAFT] Reply LS on AUSF role in slice specific authentication | actions: merge in 785 | Ericsson | LS out | Approval | Yes | Yes | merged | No | draft_S3-200785-r4
|  | S3‑200781 | DraftCR – Replacing AUSF with AAA-IWF for NSSAA procedures | comments: [Nokia] concerns actions: merge in 658 | Ericsson, Hewlett-Packard Enterprise, China Mobile, CATT | draftCR | Approval | Yes | Yes | merged | No | draft_S3-200658-r3
|  | S3‑200782 | Discussion paper on the role of AUSF during NSSAA | agreement: new NF for NSSAA | Ericsson, Hewlett-Packard Enterprise, China Mobile, CATT | discussion | Endorsement | Yes | Yes | noted | No
|  | S3‑200784 | AUSF role in slice-specific authentication |  | Huawei, HiSilicon | discussion | Endorsement | Yes | Yes | noted | No
|  | S3‑200785 | draft LS to SA2 on AUSF roles | comments: [Hw] revise as merger of 780, 785 and 659 [E///] ok | Huawei, HiSilicon | LS out | Approval | Yes | Yes | revised | No | draft_S3-200785-r4
|  | draft_S3-200785-r4 | draft LS to SA2 on AUSF roles |  | Huawei, HiSilicon | LS out | Approval | Yes | Yes | left for email approval | No |  | S3‑200785
|  | S3‑200786 | draft CR on AUSF roles | comments: [E///] concerns actions: merge in 658 | Huawei, HiSilicon | draftCR | Agreement | Yes | Yes | merged | No | draft_S3-200658-r3
|  | S3‑200787 | draft CR on sending NSSAI to AAA | comments: [Nokia, E///] objects [QC] agrees with Nokia | Huawei, HiSilicon | draftCR | Agreement | Yes | Yes | noted | No
|  | S3‑200788 | draft CR on miscellaneous items | actions: merge in 658 | Huawei, HiSilicon | draftCR | Agreement | Yes | Yes | merged | No | draft_S3-200658-r3
2.8 | Security for NR Integrated Access and Backhaul (Rel-16) | S3‑200680 | Adding a definition for IAB-UE | comments: [Nokia] revise [ZTE] ok will revise actions: to be converted to a draft CR | ZTE Corporation | CR | Agreement | Yes | Yes | not pursued | No | draft_S3-200680-r1
|  | draft_S3-200680-r1 | Adding a definition for IAB-UE |  | ZTE Corporation | draft CR | Agreement | Yes | Yes | approved | No |  | S3‑200680
|  | S3‑200681 | Update the Annex M.2.4 | comments: [Thales] not pursued [ZTE] note | ZTE Corporation | CR | Agreement | Yes | Yes | not pursued | No
|  | S3‑200694 | F1 interface security set-up procedure | comments: [QC, intel, E///] note [T-Mobile, Thales, Mav, Lenovo] supports | Samsung, Thales, Nokia, Nokia Shanghai Bell, ZTE | CR | Agreement | Yes | Yes | not pursued | No
|  | S3‑200721 | editorial change to IAB architecture |  | Huawei, Hisilicon | draftCR | Approval | Yes | No | approved | No
|  | S3‑200731 | Add requirement for OAM to IAB ENDC |  | Huawei, Hisilicon | draftCR | Approval | Yes | No | approved | No
|  | S3‑200762 | F1 security setup with certificate based IKEv2 authentication | comments: [Samsung, Nokia] not pursued | Qualcomm Incorporated, Ericsson, Intel | CR | Agreement | Yes | Yes | not pursued | No
|  | S3‑200763 | F1 security setup with PSK based IKEv2 authentication | comments: [Samsung] not pursued | Qualcomm Incorporated, Ericsson, Intel | CR | Agreement | Yes | Yes | not pursued | No
2.9 | Security aspects of SEAL (Rel-16) | S3‑200650 | SEAL Key Management procedure | comments: [Samsung] Minor, revise | Motorola Solutions UK Ltd. | pCR | Agreement | Yes | Yes | revised | No | draft_S3-200650-r1
|  | draft_S3-200650-r1 | SEAL Key Management procedure | deadline: 2nd challenge | Motorola Solutions UK Ltd. | pCR | Agreement | Yes | Yes | approved | No |  | S3‑200650
|  | S3‑200651 | SEAL Key Management Request and Response messages | comments: [Samsung] Minor, revise [MSI] ok will revise | Motorola Solutions UK Ltd. | pCR | Agreement | Yes | Yes | revised | No | draft_S3-200651-r1
|  | draft_S3-200651-r1 | SEAL Key Management Request and Response messages |  | Motorola Solutions UK Ltd. | pCR | Agreement | Yes | Yes | approved | No |  | S3‑200651
|  | S3-209999 | draft TS 33.434 |  | Samsung | draft TS |  |  |  | left for email approval
2.10 | Security Aspects of 3GPP support for Advanced V2X Services (Rel-16) | S3‑200601 | eV2XARC-Security policy for unicast message in PC5 | comments: [LGE] concerns [Apple] ok will revise [Hw] concerns | Apple | pCR | Approval | Yes | Yes | revised | No | draft_S3-200601-r2
|  | draft_S3-200601-r2 | eV2XARC-Security policy for unicast message in PC5 |  | Apple | pCR | Approval | Yes | Yes | approved | No |  | S3‑200601
|  | S3‑200602 | eV2XARC-Security policy provisioning | comments: [LGE] merge with 655 [Hw, Samsung] revise to use NOT NEEDED [Apple] ok | Apple | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200603 | eV2XARC-Security establishment for user plane bearer | comments: [LGE] merge with 655 [Apple] ok | Apple | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200604 | eV2XARC-LCID clairification | comments: [LGE] concerns, supports [E///] does not agree | Apple | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200605 | eV2XARC-Correction in 5.3.3.1.3.2 and 5.3.3.2.2 | comments: [LGE] depends on 756 | Apple | pCR | Approval | Yes | Yes | approved | No
|  | S3‑200612 | TS 33.536 - Corrections | deadline: 2nd challenge | InterDigital, Inc., Nokia, Nokia Shanghai Bell, Ericsson | pCR | Approval | Yes | Yes | approved | No
|  | S3‑200620 | LS to SA3 on NR V2X Security issues | actions: [LGE] reply to in 708 | R2-2001980 | LS in |  | Yes | Yes | replied to | No | draft_S3-200708-r3
|  | S3‑200623 | Reply LS on LS on PC5S and PC5 RRC unicast message protection | actions: note | S2-1912002 | LS in |  | Yes | Yes | noted | No
|  | S3‑200624 | Reply LS on PC5 unicast and groupcast security protection | actions: note | S2-2000971 | LS in |  | Yes | Yes | noted | No
|  | S3‑200642 | Emergency Services in eV2X | comments: [LGE, QC] concerns, revise [InterDigital] supports | Futurewei | other | Approval | Yes | Yes | revised | No | draft_S3-200642-r2
|  | draft_S3-200642-r2 | Emergency Services in eV2X |  | Futurewei | other | Approval | Yes | Yes | approved | No |  | S3‑200642
|  | S3‑200653 | TS 33.536 - Clean up | deadline: 2nd challenge | LG Electronics Inc. | pCR | Approval | Yes | Yes | approved | No
|  | S3‑200654 | TS 33.536 - Common Security over NR PC5 | comments: [Hw] concerns [LGE] ok will revise [Hw] ok | LG Electronics Inc. | pCR | Approval | Yes | Yes | revised | No | draft_S3-200654-r1
|  | draft_S3-200654-r1 | TS 33.536 - Common Security over NR PC5 | deadline: 2nd challenge | LG Electronics Inc. | pCR | Approval | Yes | Yes | approved | No |  | S3‑200654
|  | S3‑200655 | TS 33.536 - Security Policy for NR PC5 | comments: [Samsung] concerns [LGE] ok will revise [Apple] ok [QC] doesn't agree [Hw] note | LG Electronics Inc. | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200656 | TS 33.536 - Group ID conversion on NR PC5 | comments: [Lenovo, Hw] note | LG Electronics Inc. | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200682 | Adding some abbreviations to V2X TS | deadline: 2nd challenge | ZTE Corporation | pCR | Approval | Yes | Yes | approved | No
|  | S3‑200683 | Update the clause 5.3.3.1.2.3 | comments: [Hw] concerns, revise actions: delete part related to KNRP | ZTE Corporation | pCR | Approval | Yes | Yes | revised | No | draft_S3-200683-r1
|  | draft_S3-200683-r1 | Update the clause 5.3.3.1.2.3 |  | ZTE Corporation | pCR | Approval | Yes | Yes | approved | No |  | S3‑200683
|  | S3‑200684 | Update clause 5.3.3.2.2 | comments: [QC] revise | ZTE Corporation | pCR | Approval | Yes | Yes | revised | No | draft_S3-200684-r2
|  | draft_S3-200684-r2 | Update clause 5.3.3.2.2 | deadline: 2nd challenge | ZTE Corporation | pCR | Approval | Yes | Yes | approved | No |  | S3‑200684
|  | S3‑200685 | Clean up of V2X TS | deadline: 2nd challenge | ZTE Corporation | pCR | Approval | Yes | Yes | approved | No
|  | S3‑200690 | eV2X: Resolving EN on policy definition | comments: [LGE] concerns [QC] revise deadline: 3rd challenge | Huawei, Hisilicon | pCR | Approval | Yes | Yes | approved | No
|  | S3‑200691 | eV2X: Resolving EN on security policy handling | comments: [LGE] concerns [Samsung, QC] does not agree [Hw] note | Huawei, Hisilicon | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200692 | eV2X: Resolving EN on the choice of security notification message | comments: [LGE, QC] concerns [LGE] merge with 655 | Huawei, Hisilicon | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200693 | eV2X: Clarification on the security policy provisioning | comments: [LGE] concerns [Apple] merge in 655 [QC] concerns | Huawei, Hisilicon | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200708 | LS reply to RAN WG2 LS on NR V2X Security issues | comments: [LGE] depends on 727 and 755 | CATT | LS out | Approval | Yes | Yes | revised | No | draft_S3-200708-r3
|  | draft_S3-200708-r3 | LS reply to RAN WG2 LS on NR V2X Security issues |  | CATT | LS out | Approval | Yes | Yes | approved | No |  | S3‑200708
|  | S3‑200727 | Discussion on the functionality of Key ID in PDCP header for NR PC5 unicast communication | comments: [LGE] note [QC, InterDigital] don't agree | Huawei, Hisilicon | discussion | Endorsement | Yes | Yes | noted | No
|  | S3‑200728 | V2X signalling security mandatory activation for unicast | comments: [LGE] concerns, [QC] against | Huawei, Hisilicon | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200729 | Draft LS on the security context index field in PDCP header for NR PC5 unicast | comments: [LGE] depends on 727 and 755 | Huawei, Hisilicon | LS out | Approval | Yes | Yes | noted | No
|  | S3‑200730 | Clarification for V2X layer passing security configurations to AS layer | comments: [Apple] concerns, ok [Hw] ok will revise | Huawei, Hisilicon | pCR | Approval | Yes | Yes | revised | No | draft_S3-200730-r1
|  | draft_S3-200730-r1 | Clarification for V2X layer passing security configurations to AS layer |  | Huawei, Hisilicon | pCR | Approval | Yes | Yes | approved | No |  | S3‑200730
|  | S3‑200742 | Discussion paper on eV2X groupcast privacy | comments: [LGE] note | Huawei, HiSilicon | discussion | Endorsement | Yes | Yes | noted | No
|  | S3‑200743 | Adding privacy procedures for V2X group cast communication | comments: [LGE] concerns [QC] does not agree | Huawei, HiSilicon, Lenovo, Motorola Mobility | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200753 | Resolving the Editors’ Note on policy name in V2X TS |  | Qualcomm Incorporated | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200754 | Proposal to finalise UP security policy in V2X | comments: [LGE] concerns, merge with 655 | Qualcomm Incorporated | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200755 | Proposal to resolve the Editor’s note of the size of COUNT | comments: [LGE] concerns, fine [InterDigital] revise actions: add reference to relevant spec/clause [QC] note | Qualcomm Incorporated | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200756 | Privacy of K_NRP ID | comments: [LGE] depends on confirmation from InterDigital | Qualcomm Incorporated | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200757 | Resolving the editor’s note on the protection of messages | comments: [CATT, Hw] note [QC] note, create LS to CT1 | Qualcomm Incorporated | pCR | Approval | Yes | Yes | noted | No
|  | draft_S3-200757-r2 | LS title TBD |  | Qualcomm Incorporated | LS out | Approval | Yes | Yes | approved | No
|  | S3-209999 | draft TS 33.536 |  | LG Electronics Inc. |  |  |  |  | left for email approval
|  | S3‑200758 | Using the old security context for processing received re-transmissions | comments: [Hw] does not agree [LGE] note [QC] note | Qualcomm Incorporated | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200759 | Proposal for the Editor’s note on groupcast privacy | comments: [LGE] depends on 656 [Lenovo, Hw, LGE] note | Qualcomm Incorporated | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200789 | Destination L2 privacy | comments: [LGE] concerns [Lenovo] note | Ericsson | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200790 | Discussion paper on security policy |  | Apple | pCR | Approval | Yes | Yes | withdrawn | Yes
2.11 | Study on User Plane Integrity Protection (Rel-16) | S3‑200611 | UPIP-Update for solution#10 |  | Apple | pCR | Approval | Yes | No | approved | No
|  | S3‑200618 | Mandatory User Plane Integrity for 5G | actions: postpone [Vfe] note | GSMA | LS in |  | Yes | Yes | noted | No
|  | S3-209999 | draft TR 33.853 |  | VODAFONE Group Plc | draftTR |  |  |  | left for email approval
|  | S3‑200629 | pCR to TR 33.853 move of network options from introduction to section 4 | comments: [QC] note | VODAFONE Group Plc | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200630 | pCR to TR33.853 (UPIP) - Addition of conclusions to section 7.2 |  | VODAFONE Group Plc | pCR | Approval | No | Yes | withdrawn | Yes
|  | S3‑200631 | pCR to TR 33.853 (UPIP): addition of new solution - used NR PDCP for LTE | comments: [CMCC, QC] note [CableLabs] support | VODAFONE Group Plc | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200632 | draft WID - Normative changes for UPIP | comments: [TIM, DT] support [QC] note | VODAFONE Group Plc | WID new | Approval | Yes | Yes | noted | No
|  | S3‑200633 | CR to 33.501 - Update to User Plane Integrity Protection | comments: [TIM, Fw, CableLabs, Hw, CMCC] support [Samsung, QC, OPPO] not pursued [E///] concerns | VODAFONE Group Plc | CR | Approval | Yes | Yes | noted | No
|  | S3‑200634 | LS to RAN3 and CT1 on Updated User Plane Integrity Protection advice | comments: [CMCC] concerns [TIM, CableLabs] supports [QC] note | VODAFONE Group Plc | LS out | Approval | Yes | Yes | noted | No
|  | S3‑200635 | Cover sheet for TR 33.853 for Information | comments: [QC] note | VODAFONE Group Plc | TS or TR cover | Approval | Yes | Yes | noted | No
|  | S3‑200636 | minutes of UPIP confcall #1 on 2 April 2020 | comments: [Vfe] note | VODAFONE Group Plc | report | Information | Yes | Yes | noted | No
|  | S3‑200637 | minutes of confcall 2 on UPIP held 3 April 2020 | comments: [Vfe] note | VODAFONE Group Plc | report | Information | Yes | Yes | noted | No
|  | S3‑200638 | Discussion docuemnt on the approval of TR33.853 |  | VODAFONE Group Plc | discussion | Information | No | Yes | withdrawn | Yes
|  | S3‑200639 | pCR to 33.853 (UPIP) - Correction to Key Issue 5 | comments: [QC, Samsung] note | VODAFONE Group Plc | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200643 | UPIP Way Forward Discussion | comments: [Nokia] not endorse p1 and p2 not ok p3 ok [OPPO, Spreadtrum, QC, Samsung] not endorse [TIM, Vfe, Hw, Orange, DT, CMCC, NIST, BT] support [E///] partially disagree (gNB) | Futurewei | discussion | Endorsement | Yes | Yes | noted | No
|  | S3‑200695 | Proposed solution for UP IP issues in GSMA LS |  | Samsung, Nokia, Nokia Shanghai Bell | discussion |  | Yes | Yes | noted | No
|  | S3‑200696 | UP integrity protection for UP Signalling messages | comments: [Hw] not pursued | Samsung | CR |  | Yes | Yes | noted | No
|  | S3‑200697 | Integrity protection of DNS messages | comments: [Hw] not pursued [Vfe, NCSC] concerns | Samsung | CR |  | Yes | Yes | noted | No
|  | S3‑200699 | Reduced overhead for UP IP for 5G RAN_conclusion | comments: [CMCC, Nokia, Spreatrum] note | Philips International B.V. | pCR | Approval | Yes | Yes | noted | No
|  | S3‑200700 | Conclusion to Key Issue #5 | comments: [Fw] note [Hw, NCSC] concerns | Samsung | pCR |  | Yes | Yes | noted | No
|  | S3‑200737 | Discussion on endorsement for UP IP | comments: [QC, Nokia, Samsung] don't agree [TIM, DCM] support full rate for all UE [TIM, DT, Broadcom, E///] does not agree | Huawei, Hisilicon | discussion | Endorsement | Yes | Yes | noted | No
|  | S3‑200738 | Draft LS on UP IP | comments: [TIM] objects [E///] revise | Huawei, Hisilicon | LS out | Approval | Yes | Yes | noted | No
|  | S3‑200745 | UPIP: pCR for new solution of UP IP in EPS | comments: [CMCC, Fw] concerns [E///] ok will revise | Ericsson | pCR | Approval | Yes | Yes | revised | No | draft_S3-200745-r2
|  | draft_S3-200745-r2 | UPIP: pCR for new solution of UP IP in EPS |  | Ericsson | pCR | Approval | Yes | Yes | approved | No |  | S3‑200745
|  | S3‑200746 | UPIP: pCR for new solution for option 5 | comments: [QC] concerns, ok [E///] ok will revise | Ericsson | pCR | Approval | Yes | Yes | revised | No | draft_S3-200746-r1
|  | draft_S3-200746-r1 | UPIP: pCR for new solution for option 5 |  | Ericsson | pCR | Approval | Yes | Yes | approved | No |  | S3‑200746
|  | S3‑200760 | Interworking between EPS and 5GS when UP IP is supported in EPS |  | Qualcomm Incorporated | pCR | Approval | Yes | No | approved | No
|  | S3‑200761 | Using existing algorithm IEs to indicate support UP IP with an eNB | comments: [CMCC] concerns | Qualcomm Incorporated | pCR | Approval | Yes | Yes | approved | No
|  | S3‑200766 | On the GSMA LS on UP IP | actions: open for further email discussion. In general no opposition to o1, o2. split on o3. | Qualcomm Incorporated, vivo, Nokia, Nokia Shanghai Bell | discussion | Approval | Yes | Yes | noted | No
|  | S3‑200767 | Proposed solution for UP IP issues in GSMA LS | actions: no objections to m1 but split on m2 [NCSC] concerns [Hw] concerns | Qualcomm Incorporated, vivo | discussion | Approval | Yes | Yes | noted | No
|  | S3‑200768 | Proposed conclusion for Key Issue #6 in TR 33.853 | comments: [E///] concerns, ok | Qualcomm Incorporated | pCR | Approval | Yes | Yes | approved | No |  | S3‑194338