## Slide 1: Summary
WI Title | SA3 rapporteur | WI code | Current % completion | New % completion | Current target | New target | Current WID | TR/TS | Rel
Normative work on Lawful Interception Rel-16 | Alex Leadbeater (BT) | LI16 | 100% |  | Mar 21 | Jun 21 |  |  | 16
Normative work on Lawful Interception Rel-17 | Alex Leadbeater (BT) | LI17 | 10% | 20% | Mar 22 |  |  |  | 17
Security Assurance Specification for 5G NWDAF | Minpeng Qi (China Mobile) | SCAS_5G_NWDAF | 70% | 85% | Mar 21 | Dec 21 | SP-200147 | TS 33.521 CRs to TR 33.926 | 17
Security Assurance Specification for Service Communication Proxy | Anja Jerichow (Nokia) | SCAS_5G_SECOP | 20% | 70% | Mar 21 | Dec 21 | SP-200148 | TS 33.522 CRs to TR 33.926 | 17
Study on security aspects of Unmanned Aerial Systems | Adrian Escott (Qualcomm) | FS_UAS_SEC | 65% | 90% | Mar 21 | Dec 21 | SP-200352 | TR 33.854 | 17
Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC | Bo Zhang (Huawei) | FS_eEDGE_SEC | 60% | 75% | Mar 21 | Dec 21 | SP-200347 | TR 33.839 | 17
Study on Security Aspects of Enhancement for Proximity Based Services in 5GS | Wei Zhou (CATT) | FS_5G_ProSe_Sec | 65% | 75% | Jun 21 | Dec 21 | SP-200350 | TR 33.847 | 17
Study on security for enhanced support of Industrial IoT | Anja Jerichow (Nokia) | FS_IIoT_SEC | 90% | 100% | Jun 21 | Dec 21 | SP-201015 | TR 33.851 | 17
Adapting BEST for use in 5G networks | Iko Keesmaat (KPN) | BEST_5G | 40% | 70% | Jun 21 | Dec 21 | SP-201135 | CRs to tS 33.163 | 17

## Slide 2: Summary
WI Title | SA3 rapporteur | WI code | Current % completion | New % completion | Current target | New target | Current WID | TR/TS | Rel
Security Assurance Specification for IMS | Bo Zhang (Huawei) | SCAS_IMS | 80% | 90% | Mar 21 | Jun 21 | SP-191128 | TS 33.226 CRs to TR 33.926 | 17
Study on 5G security enhancements against false base stations | Ivy Guo (Apple) | FS_5GFBS | 87% |  | Jun 21 |  | SP-180690 | TR 33.809 | 17
SECAM and SCAS for 3GPP virtualized network products | Minpeng Qi (China Mobile) | FS_VNP_SECAM_SCAS | 75% | 90% | Jun 21 | Dec 21 | SP-180696 | TR 33.818 | 17
Security aspects of Enhanced Network Slicing | Suresh Nair (Nokia) | eNS_SEC | 97% | 100% | Jun 20 | Jun 21 | SP-190712 | CRs to TS 33.501 | 16
Security Assurance Specification for Non-3GPP InterWorking Function (N3IWF) | Feng Gao (China Unicom) | SCAS_5G_N3IWF | 20% |  | Mar 21 | Dec 21 | SP-200146 | TS 33.520 CRs to TR 33.926 | 17
Study on Security Aspects of Enhancements for 5G Multicast-Broadcast Services | Longhua Guo (Huawei) | FS_5MBS_SEC | 60% | 75% | Mar 21 | Dec 21 | SP-200351 | TR 33.850 | 17
Study on security aspects of enablers for Network Automation (eNA) for the 5G system (5GS) Phase 2 | Xiaoting Huang (China Mobile) | FS_eNA_SEC | 40% | 50% | Jun 21 | Dec 21 | SP-200722 | TR 33.866 | 17

## Slide 3: Summary
WI Title | SA3 rapporteur | WI code | Current % completion | New % completion | Current target | New target | Current WID | TR/TS | Rel
Study on User Plane Integrity Protection | Tim Evans (Vodafone) | FS_UP_IP_Sec | 99% | 100% | Mar 21 |  | SP-181035 | TR 33.853 | 17
Study on Security Impacts of Virtualisation | Alex Leadbeater (BT) | FS_SIV | 50% | 55% | Jun 21 | Dec 21 | SP‑181236 | TR 33.848 | 17
Study on authentication enhancements in 5GS | Vlasios Tsiatsis (Ericsson) | FS_AUTH_ENH | 80% | 85% | Mar 21 | Dec 21 | SP-190713 | TR 33.846 | 17
Study on Security for NR Integrated Access and Backhaul | Rajavelsamy Rajadurai (Samsung) | FS_NR_IAB_Sec | 75% | 78% | Jun 21 | Dec 21 | SP-201016 | TR 33.824 | 17
integrating GBA to 5GC | Vlasios Tsiatsis (Ericsson) | GBA_5G | 55% | 55% | Mar 21 | Dec 21 | SP-190714 | CRs to TS 33.220 TS 33.222 TS 33.223 TS 33.501 | 17
Security Assurance Specification Enhancements for 5G | Rong Wu (Huawei) | eSCAS_5G | 65% | 65% | Mar 21 | Dec 21 | SP-200149 | CRs to TR 33.926, TS 33.117, TS 33.511, TS 33.512, TS 33.513, TS 33.514, TS 33.515, TS 33.516, TS 33.517, TS 33.518, TS 33.519 | 17
Study on enhanced security support for Non-Public Networks | Christine Jost (Ericsson) | FS_eNPN_SEC | 65% | 75% | Mar 21 | Dec 21 | SP-200620 | TR 33.857 | 17
Study on User Consent for 3GPP services | Rong Wu (Huawei) | FS_UC3S | 40% | 50% | Mar 21 | Dec 21 | SP-200885 | TR 33.867 | 17

## Slide 4: Summary
WI Title | SA3 rapporteur | WI code | Current % completion | New % completion | Current target | New target | Current WID | TR/TS | Rel
Study on storage and transport of 5GC security parameters for ARPF authentication | Tim Evans (Vodafone) | FS_5GC_SEC_ARPF | 98% | 100% | Mar 21 |  | SP-190708 | TR 33.845 | 17
Authentication and key management for applications based on 3GPP credential in 5G | Xiaoting Huang (China Mobile) | AKMA | 98% | 98% | Jun 20 |  | SP-190711 | TS 33.535 | 17
Security Assurance Specification for Inter PLMN UP Security | Jin Peng (ZTE) | SCAS_5G_IPUPS | 70% | 90% | Jun 21 | Dec 21 | SP-200348 | CRs to TR 33.926 TS 33.513 | 17
Mission critical security enhancements phase 2 | Tim Woodward (Motorola Solutions) | MCXSec2 | 25% | 80% | Jun 21 | Dec 21 | SP-200718 | CRs to TS 33.180 | 17
Study on security aspects of the MSGin5G Service | Xiaoting Huang (China Mobile) | FS_SEC_5GMSG | 40% | 45% | Jun 21 | Dec 21 | SP-200878 | TR 33.862 | 17
Study on the security of AMF re-allocation | Vlasios Tsiatsis (Ericsson) | FS_AMFREAL_SEC | 50% | 70% | Mar 21 | Dec 21 | SP-200721 | TR 33.864 | 17
Study on the security of the system enablers for devices having multiple Universal Subscriber Identity Modules (USIM) | Abhijeet Kolekar (Intel Corporation) | FS_MUSIM_SEC | 35% | 96% | Mar 21 | Dec 21 | SP-201018 | TR 33.873 | 17
Study on non-seamless WLAN Offload in 5GS using 3GPP credentials | Mavureddi Dhanasekaran, Ranganathan (Nokia) | FS_NSWO_5G | 0% | 25% | Dec 21 | Dec 21 | SP-210262 | TR 33.881 | 17

## Slide 5: Summary
WI Title | SA3 rapporteur | WI code | Current % completion | New % completion | Current target | New target | Current WID | TR/TS | Rel
Security Assurance Specification for Network Slice-Specific Authentication and Authorization Function | Rong Wu (Huawei) | SCAS_5G_NSSAAF | 40% | 45% | Jun 21 | Dec 21 | SP-200720 | TS 33.326 CRs to TR 33.926 | 17
Study on enhanced Security Aspects of the 5G Service Based Architecture | Anja Jerichow (Nokia) | FS_eSBA_SEC | 45% | 70% | Sep 21 | Dec 21 | SP-201129 | TR 33.875 | 17
Study on enhanced security for network slicing Phase 2 | Zander Lei (Huawei) | FS_eNS2_SEC | 10% | 15% | Sep 21 | Dec 21 | SP-210106 | TR 33.874 | 17
User Plane Integrity Protection for LTE | Tim Evans (Vodafone) | UPIP_SEC_LTE | 0% | 85% | Jun 21 | Dec 21 | SP-210105 | CRs to TS 33.501, TS 33.401 | 17
Enhancements of 3GPP profiles for cryptographic algorithms and security protocols | Pinar Comak (Ericsson) | eCryptPr | 0% | 35% | Sep 21 | Dec 21 | SP-210107 | CRs to TS 33.141, TS 33.203, TS 33.210, TS 33.220, TS 33.222, TS 33.310, TS 33.328, TS 33.501 | 17