3GPP TSG-SA WG4 adhoc post #134	S4aR250221

Online, 17 December 2025

________________________________________________________________________

3GPP TSG-SA WG4 Meeting #135	S4-26xxxx

Goa, IN, 9 – 13 February 2026

# Source:	Nokia (Rapporteur)

# Title:	Draft Work Plan for FS_Q4RTC-MED

# Document for:	Agreement

# Agenda Item:	17.1

# Introduction

This contribution contains a draft work plan for the Rel-20 Study on QUIC-based media delivery for real-time communication (FS_Q4RTC_MED) agreed in SA4#134 [S4-252139] and approved in SA#110 [SP-251661].

# 2	Objectives

The study has the following objectives:

- Identify existing and emerging QUIC-based media delivery protocols suitable for real-time communication and document their features, benefits, limitations and current applications.

- Define an evaluation framework for QUIC-based media delivery protocols in the context of the RTC System as defined in TS 26.506 and TS 26.113.

- Define application scenarios for which the evaluation of QUIC-based media delivery protocols is carried out, in particular including existing 3GPP services or service enablers such as split rendering.

- For the identified application scenarios, define appropriate performance metrics, requirements and evaluate the performance of the QUIC-based media delivery protocols against existing architectures and protocols as defined in TS 26.506 and TS 26.113 (in particular WebRTC and (S)RTP-based frameworks) under realistic 3GPP network conditions. Consider existing performance evaluation from e.g. academia and other SDOs for realistic 3GPP network conditions, which needs to be verified independently by SA4. This may consist of SA4 analytically verifying the results and confirming their validity without conducting new simulations.

c)	Document potential impact of deploying QUIC-based technologies on the delivery architecture defined in TS 26.506, taking into account: current architectures, the 3GPP core network architecture defined in TS 23.501 and UE implementations; and identify advantages and disadvantages for deployments. For example, efficiency, scalability, ability to provide a distributed deployment, impact on radio optimizations, flow control and management, security/privacy versus traffic management, and readiness of general-purpose implementations.

NOTE 1: The evaluation framework may be based on an open-source network simulator such as ns3.

NOTE 2: The evaluation scenarios may involve real-time communication of audio and video in the context of 3GPP real-time communications services. For audio, EVS and IVAS, and for video H.264/AVC and H.265/HEVC can be considered, as specified in TS 26.114.

- If sufficient evidence of benefits for the selected QUIC-based media delivery protocols in the context of RTC are identified

a)	Study integration of the beneficial QUIC-based media delivery protocols identified in objective #1 and #2 and the SA2 MRI solutions (as defined in TS 23.501, clause 5.37.9) into the RTC System.

NOTE 3: The study of integration includes consideration of potential architectural enhancements, signaling and collaboration scenarios required for QUIC-based media delivery protocols.

b)	Identify gaps and potential normative work on the architecture and procedures (TS 26.506) of the RTC System as well as on its protocols and APIs (TS 26.113 and TS 26.510).

NOTE 4: The study will take into account potential changes in the media delivery architecture as identified in other ongoing 3GPP studies.

- Coordinate work with other 3GPP groups and the IETF as needed.

# 3	Proposed Work Plan

| Meeting | Study Item on QUIC-based media delivery for RTC |
| --- | --- |
| SA4#134 (17–21 November 2025, Dallas, US) | - Agree study item description - Discuss potential work plan |
| SA#110 (9–12 December 2025, Baltimore, US) | - Approve new study Item |
| SA4#134 RTC SWG call (Dec 17, 2025, 14:00-16:00 CET, Host Nokia) | - Discuss work plan |
| SA4#134 RTC SWG call (Jan 28, 2026, 15:00-17:00 CET, Host Nokia) | - Discuss specification skeleton for TR 26.8xx - Initiate work on: - Identification of QUIC-based media delivery protocols suitable for RTC and documentation of their features, benefits, limitations and current applications. |
| SA4#135 (9–13 February 2026, Goa, India) | - Agree work plan - Agree specification skeleton for TR 26.8xx - Progress work on: - Identification of QUIC-based media delivery protocols suitable for RTC and documentation of their features, benefits, limitations and current applications. - Initiate work on: - Definition of application scenarios for evaluation of the identified protocols - Definition of performance metrics and requirements for the evaluation - Performance evaluation of the QUIC-based media delivery protocols - Documentation of existing evaluation from academia and other SDOs - Document potential impact of deploying QUIC-based technologies - Communicate with other 3GPP WG and external organizations if necessary NOTE: Coordinate with FS_QStream_MED on the evaluation framework. |
| Post SA4#135 RTC SWG calls (date/time TBD, submission deadline: TBD, Host Nokia) | - TBD |
| SA4#135-bis-e (13–17 April 2026, online) | - Complete work on: - Identification of QUIC-based media delivery protocols suitable for RTC and documentation of their features, benefits, limitations and current applications. - Progress work on: - Definition of application scenarios for evaluation of the identified protocols - Definition of performance metrics and requirements for the evaluation - Performance evaluation of the QUIC-based media delivery protocols - Documentation of existing evaluation from academia and other SDOs - Document potential impact of deploying QUIC-based technologies. - Initiate identification of potential stage-2 normative work for 5GA. - Communicate with other 3GPP WG and external organizations if necessary |
| Post SA4#135-bis-e AHG calls (date/time TBD, submission deadline: TBD, Host Nokia) | - TBD |
| SA4#136 (11–15 May 2026, Montreal, Canada) | - Progress work on: - Definition of application scenarios for evaluation of the identified protocols - Definition of performance metrics and requirements for the evaluation - Documentation of existing evaluation from academia and other SDOs - Performance evaluation of the QUIC-based media delivery protocols - Document potential impact of deploying QUIC-based technologies. - Complete identification of potential stage-2 normative work for 5GA. NOTE: Stage-2 normative work item for 5GA may be proposed here. - Communicate with other 3GPP WG and external organizations if necessary |
| Post SA4#136 AHG calls (date/time TBD, submission deadline: TBD, Host Nokia) | - TBD |
| SA4#137-e (24–28 August 2026, online) | - Complete work on: - Definition of application scenarios for evaluation of the identified protocols - Definition of performance metrics and requirements for the evaluation - Documentation of existing evaluation from academia and other SDOs - Progress work on: - Performance evaluation of the QUIC-based media delivery protocols - Document potential impact of deploying QUIC-based technologies. - Initiate identification of potential stage-3 normative work for 5GA. - Communicate with other 3GPP WG and external organizations if necessary |
| Post SA4#137-e AHG calls (date/time TBD, submission deadline: TBD, Host Nokia) | - TBD |
| SA4#138 (16–20 November 2026, Calgary, Canada) | - Progress work on: - Performance evaluation of the QUIC-based media delivery protocols - Document potential impact of deploying QUIC-based technologies. - Complete identification of potential stage-3 normative work for 5GA. NOTE: Stage-3 normative work item for 5GA may be proposed here. - Send TR 26.8xx for information to SA |
| SA#114 (8–11 December 2026, US) | - Presentation of TR 26.8xx to SA for information |
| SA4#139 (22–26 February 2027, South Korea) | - Complete work on: - Performance evaluation of the QUIC-based media delivery protocols - Document potential impact of deploying QUIC-based technologies. - Finalize TR conclusions and recommendations for future work. - Send TR 26.8xx for approval to SA |
| SA#115 (16–19 March 2027, Europe) | - Approval of TR 26.8xx in SA |