3GPP SA4-e (AH) MBS SWG post 127	S4aI240032

Online, 22nd February 2024–23th March 2024

Agenda item: 	3.7

Source: 	Orange

Title: 	[FS_MediaEnergyGREEN] Work Plan v0.1

Document for	Discussion

# Introduction

The FS_MediaEnergyGREEN study aims to identify sustainable media metrics, architectural impacts (APIs), functional extensions required for SA4 service enablers and evaluate the feasibility of an evaluation framework to facilitate efficient energy use and energy saving for media services.

The main objectives of this study include:

- Refine relevant SA1 use cases (5.5, 5.8, 5.9, 5.10 and 5.14) in TR 22.882 in the SA4 context.

- Document existing APIs, metrics, and mechanisms inside or outside 3GPP that could be used for energy measurement, reporting and exposure of media services. This includes whether and what information is exposed, how it is exposed, and at what granularity (QoE measurement and reporting, QoS measurement and reporting, audience measurement and reporting, event exposure, CMCD reporting, etc.).

- Study the feasibility of having implementation-independent metrics and a framework to evaluate the energy usage/savings of multimedia standards features and proposals.

NOTE 1: The study will consider the work done by SA WG2 and WG5 regarding energy consumption measurement, information collection and energy saving, and reuse it as much as possible.

NOTE 2: Exchanges with other 3GPP WGs, CTA WAVE and DVB may be needed, e.g., via formal Liaison Statements.

# Time Plan

The following time plan for the execution of the FS_MediaEnergyGREEN study item objectives is proposed in the following table.

| Meeting | Study on Media enerGy consumption exposuRE and EvaluatioN framework |
| --- | --- |
| SA4#127 (29 January - 2 February 2024, Sophia-Antipolis, FR) | - Agree New Study Item FS_MediaGREEN in S4-240438. |
| SA#103 (19 - 22 March 2024, FR) | - Approve New Study Item FS_MediaEnergyGREEN in in SP-240491. |
| 3GPP SA4 MBS SWG Telco (28 March, 2024, 15:30 – 17:30 CET, Host Qualcomm) | - Define and agree initial workplan. - Agree Specification skeleton for TR 26.942. |
| SA4#127-bis-e (08 - 12 April 2024, online) | - Initiate work on: - Description of scenarios, including identified scenarios from TR 22.882. - Communicate with other 3GPP working groups and external organizations, if necessary. |
| Post SA4#127-bis-e AHG calls | - Progress work on the above. |
| SA4#128 (20 - 24 May 2024, Korea) | - Progress work on the above. - Initiate work on: - Document relevant requirements. - Review SA2/SA5 work. - Document existing relevant API and metrics. - Identify existing mechanisms that could be reused (e.g. QoE, QoS, Audience, CMCD). - Communicate with other 3GPP working groups and external organizations, if necessary. |
| Post SA4#128 AHG calls | - Progress work on the above |
| SA4#129-e (19 - 23 August 2024, online) | - Progress work on the above. - Initiate work on: - Identifying gaps in existing mechanisms, APIs and metrics. - Feasibility of having implementation-independent metrics and a framework to evaluate the energy usage/savings - Communicate with other 3GPP working groups and external organizations, if necessary. |
| Post SA4#129 AHG calls | - Progress work on the above. |
| SA4#130 (18 - 22 November 2024, Orlando) | - Progress work on the above. - Initiate work on: - Identify recommendations to enhance or enable media energy consumption exposure and measurement. - Draft initial conclusions in the TR. - Communicate with other 3GPP working groups and external organizations, if necessary. - Agree on TR 26.942 v1.0.0 to be sent to SA plenary for information. |
| SA#106 (10 - 13 December 2024, Madrid) | - Present TR 26.942 v1.0.0 to SA for information. |
| SA4#131 (17 - 21 February 2025, Geneva) | - Complete all remaining open issues. - Communicate with other 3GPP working groups and external organizations, if necessary. - Agree on TR 26.942 to be sent to SA plenary for approval |
| SA#107 (11 - 14 March 2025, Korea) | - Send TR 26.942 v2.0.0 to SA for Approval |

# Proposal

We propose the above Work Plan for the SA4 team's consideration.