Source:	Editor (HEAD acoustics GmbH)

Title:	Time Plan for FS_AnTEM

Version:	0.3

Agenda Item:	9.7

# 1. Introduction

This document describes the time plan for the “Study on ambient noise test methodology for evaluation of acoustic UE performance”. Section 2 lists the permanent documents, section 3 describes the schedule of the study item. This document will be continuously updated as necessary.

# 2. List of FS_AnTEM permanent documents

| Document number | Title | Current version | Editor |
| --- | --- | --- | --- |
| S4-190681 | Time Plan of study item | 0.3 | HEAD acoustics GmbH |
| S4-190683 | Round-robin test plan for handset mode | 1.1 | HEAD acoustics GmbH, Intel |

# 3. Schedule

| Month | Meeting / date | Activity |
| --- | --- | --- |
| Nov-18 | SA4#101 (19 Nov 2018) | Proposal and approval of Study Item (S4-181500) |
| Dec-18 | SA#82 (12 Dec 2018) | Approval of FS_AnTEM Study Item at SA plenary (SP-180986) |
| Feb-19 | SA4#102 (01 Feb 2019) | Initial inputs for TR 26.921 (study on handheld hands-free devices) |
| Mar-19 | SA#83 (22 Mar 2019) | - |
| Apr-19 | SA4#103 (12 Apr 2019) | Review additional inputs Proposal and discussion round-robin test plan for handset mode Agreement on test plan Update of TR 26.921 Discussion, if telcos are necessary |
| Jun-19 | SA#84 (07 Jun 2019) | - |
| Jul-19 | SA4#104 (05 Jul 2019) | Review additional inputs Discuss results of noise field simulation check pCR to TR 26.921 Discuss first conclusions on possible ways forward (continue SI, new WI, …) |
| Aug-19 | SA4#105 (16 August 2019) | Review additional inputs Discuss results of round robin test Report results to CTIA CPWG for provided devices Conclude on possible ways forward (continue SI, new WI, …) |
| Sep-19 | SA#85 (20 Sep 2019) | Present TR 26.921 for information |
| Oct-19 | SA4#106 (25 Oct 2019) | Review additional inputs and progress Finalize and agree on TR 26.921 Conclude FS_AnTEM, if necessary Liaise with ETSI TC STQ, ITU-T SG12, GSMA, if necessary. |
| Dec-19 | SA#86 (13 Dec 2019) | Approval of TR 26.921 |