Source:	Editor (HEAD acoustics GmbH)

Title:	Time Plan for FS_AnTEM

Version:	0.4

Agenda Item:	9.7

# 1. Introduction

This document describes the time plan for the “Study on ambient noise test methodology for evaluation of acoustic UE performance”. Section 2 lists the permanent documents, section 3 describes the schedule of the study item. This document will be continuously updated as necessary.

# 2. List of FS_AnTEM permanent documents

| Document number | Title | Current version | Editor |
| --- | --- | --- | --- |
| S4-190976 | Time Plan of study item | 0.4 | HEAD acoustics GmbH |
| S4-190683 | Round-robin test plan for handset mode | 1.1 | HEAD acoustics GmbH, Intel |

# 3. Schedule

| Month | Meeting / date | Activity |
| --- | --- | --- |
| Nov-18 | SA4#101 (19 Nov 2018) | Proposal and approval of Study Item (S4-181500) |
| Dec-18 | SA#82 (12 Dec 2018) | Approval of FS_AnTEM Study Item at SA plenary (SP-180986) |
| Feb-19 | SA4#102 (01 Feb 2019) | Initial inputs for TR 26.921 (study on handheld hands-free devices) |
| Mar-19 | SA#83 (22 Mar 2019) | - |
| Apr-19 | SA4#103 (12 Apr 2019) | Review additional inputs Proposal and discussion round-robin test plan for handset mode Agreement on test plan Update of TR 26.921 Discussion, if telcos are necessary |
| Jun-19 | SA#84 (07 Jun 2019) | - |
| Jul-19 | SA4#104 (05 Jul 2019) | Review additional inputs Discuss results of noise field simulation check pCR to TR 26.921 Discuss first conclusions on possible ways forward (continue SI, new WI, …) |
| Aug-19 | SA4#105 (16 August 2019) | Review additional inputs Status report of round robin test pCR to TR 26.921 on lab description Discuss possible ways forward (continue SI, new WI, …) |
| Sep-19 | Telco (Tuesday, 17th September 2019, 4 – 5:30 pm CEST, Host: ETSI, Deadline for contributions: 16th September, 4 pm CEST) | Present and discuss results of round robin test |
| Sep-19 | SA#85 (20 Sep 2019) | Present TR 26.921 for information |
| Oct-19 | SA4#106 (25 Oct 2019) | Review additional inputs and progress Agree pCR on results of round robin test Finalize and agree on TR 26.921 Liaise with CTIA CPWG reporting additional results for provided devices Liaise with ETSI TC STQ, ITU-T SG12, GSMA |
| Dec-19 | SA#86 (13 Dec 2019) | Approval of TR 26.921 |