Agenda Item:		10.5

Source:		Facebook Japan K.K. (Rapporteur)

Title:			Time & Work Plan for WI iRTCW

Version:		0.01

Document for:	Discussion

Introduction

It is proposed to proceed Rel-18 WI iRTCW with the following deliverables:

- TS 26.113 Enabler for Immersive Real-time Communication V18.0.0

- (If any) files to be attached to TS 26.113

- A source file (e.g., of Visio) including all figures in TS 26.113 (for facilitating maintenance and enhancement of the specification)

- A permanent document including key contents, tentatively agreed texts, and open issues that may necessitate further works in RTC or other SA4 SWG/3GPP WGs, or other technical/standard organizations.

Detailed schedules including telcos will be introduced and aligned with other Rel-18 works. It is suggested to update the WID after related WIs are agreed and assigned Unique IDs.

Proposed Time and Work Plan

| Meeting | Date | Activity |
| --- | --- | --- |
| SA4#117-e | 14-23 February, 2022 | - Agreed New WID on immersive Real-time Communication for WebRTC (S4-220273) |
| SA#95-e | 15-24 March, 2022 | - Approved New WID on immersive Real-time Communication for WebRTC (SP-220241) |
| SA4#118-e | 6-14 April, 2022 | - Review time and work plan |
| SA4#119-e | 11-20 May, 2022 | - Review skeleton of TS 26.113 - Review titles and contents of permanent document - Agree time and work plan |
| SA#96 | 7-10 June, 2022 |  |
| SA4#120 | 22-26 August, 2022 (17-26 August for e-meeting) | - Update time and work plan - Update WID for Unique IDs & alignment with related Rel-18 WIs - Agree titles and contents of permanent document - Review immersive media I/Os requirements for iRTC client in terminal (with Audio and Video SWGs) - Review sensor information requirements for iRTC client in terminal - Review WebRTC protocol stack and potential separation of its control signal and user data |
| SA#97 | 14-16 September, 2022 |  |
| SA4#121 | 14-18 November, 2022 (9-18 November for e-meeting) | - Update time and work plan - Agree skeleton of TS 26.113 - Progress immersive media I/Os for iRTC client in terminal (with Audio and Video SWGs) - Progress sensor information for iRTC client in terminal - Progress WebRTC protocol stack and potential separation of its control signal and user data |
| SA#98 | 14-16 December, 2022 |  |
| SA4#122 | 20-24 February, 2023 (20 February – 1 March for e-meeting) | - Update time and work plan - Review 3D video representation requirements for iRTC client in terminal (with Video SWG) - Review integration of iRTC components into 5G system - Progress TS 26.113 |
| SA#99 | 22-24 March, 2023 |  |
| SA4#123 | 17-21 April, 2023 | - Update time and work plan - Draft immersive media I/Os for iRTC client in terminal (with Audio and Video SWGs) - Draft 3D video representation requirements for iRTC client in terminal based on the I/Os (with Video SWG) - Draft sensor information for iRTC client in terminal - Progress integration of iRTC components into 5G system - Progress TS 26.113 |
| SA4#124 | 22-26 May, 2023 | - Update time and work plan - Draft protocol stack for iRTC client in terminal with control signal and user data separated - Draft integration of iRTC components into 5G system - Progress TS 26.113 |
| SA#100 | June, 2023 (TBD) | - Share WI status and remaining schedule |
| SA4#125 | 21-25 August, 2023 (16-25 August for e-meeting) | - Update time and work plan - Agree immersive media I/Os for iRTC client in terminal (with Audio and Video SWGs) - Agree 3D video representation requirements for iRTC client in terminal based on the I/Os (transfer further works to Video SWG) - Agree sensor information for iRTC client in terminal - Agree protocol stack for iRTC client in terminal with control signal and user data separated - Agree integration of iRTC components into 5G system - Initiate communication with other 3GPP WGs and technical/standard organizations, as necessary - Progress TS 26.113 |
| SA#101 | September, 2023 (TBD) |  |
| SA4#126 | 13-17 November, 2023 (8-17 November for e-meeting) | - Complete TS 26.113 V1.0.0 - Complete permanent document - Agree TS 26.113 V1.0.0 - Endorse work item summary |
| SA#102 | December, 2023 (TBD) | - Present TS 26.113 V1.0.0 for approval - Present work item summary |