## SA4#120-e_Status
3GPP SA4 WI/SI Status Update
Name | WI_Code | WI_ID | Release | Is an exception Required ? | Target Completion Date(legends: Orange - Completion due by the immediate SA TSG plenary; Yellow: Completion date due after the current TSG cycle i.e., in approx. 6 months) | Completion %age till SA4#118-e | Completion %age till SA4#119-e | Completion %age till SA4#120-e | Specify whether Stage2 / Stage 3 | Name of the Rapporteur | Comments
Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 830005 | Rel-18 |  | 2022-12-22 | 20% | 20% | 20% | Stage 3 | Stéphane Ragot, Stefan Bruhn | Test specifications
EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 770024 | Rel-18 |  | 2023-12-12 | 33% | 35% | 40% | Stage 3 | Imre Varga
IMS-based AR Conversational Services (IBACS) | IBACS | 960042 | Rel-18 |  | 12/23 | NA |  | 5%
Enhancements to UE Testing (eUET) | eUET | 960043 | Rel-18 |  | 12/23 |  |  | 10%
Immersive Real-time Communication for WebRTC | iRTCW | 950014 | Rel-18 |  | 2023-12-12 | 0% | 5% | 10% | Stage 3
Generic architecture for Real-Time and AR/MR media (GA4RTAR) | GA4RTAR | 960044 | Rel-18 |  | 2023-03-01 | NA | NA | 25% | Stage 2 | Hakju Ryan Lee
Split Rendering Media Service Enabler (SR_MSE) | SR_MSE | 960045 | Rel-18 |  | 2023-09-01 | NA |  | 5%
5G Real-time Transport Protocols (5G_RTP) | 5G_RTP | 960046 | Rel-18 |  | 2023-06-01 | NA | NA | 3% | Stage 2 | Igor Curcio
5G Media Streaming Architecture Phase2 (5GMS_Ph2) | 5GMS_Ph2 | 960047 | Rel-18 |  | 2023-03-01 | NA | NA | 15%
Media Capabilities for Augmented Reality | MeCAR | 950015 | Rel-18 |  | 2023-12-01 | 5% | 8% | 15% | Stage 3 | Emmanuel Thomas | Spec editor: Gilles Teniou
Study on Typical Traffic Characteristics for XR Services and other Media | FS_XRTraffic | 870013 | Rel-17 |  | 2022-09-01 | 80% | 90% | 85% | Study | Thomas Stockhammer
Feasibility Study on 5G Media Service Enablers | FS_5G_MSE | 940010 | Rel-18 |  | 2022-09-23 | 25% | 30% | 60% | Study | Thomas Stockhammer
Feasibility Study on Smartly Tethering AR Glasses | FS_SmarTAR | 950013 | Rel-18 |  | 2023-03-10 | 10% | 30% | 40% | Study
Feasibility Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media | FS_AI4Media | 950011 | Rel-18 |  | 2023-12-12 | 5% | 10% | 15% | Study | Eric Yip | TR editor: Gilles Teniou
Feasibility Study on the enhancements for immersive Real-time Communication for WebRTC | FS_eiRTCW | 950012 | Rel-18 |  | 2023-06-12 | 0% | 10% | 30% | Study
Study on Media Streaming aspects of Network Slicing Phase 2 (FS_MS_NS_Ph2) | FS_MS_NS_Ph2 | 960048 | Rel-18 |  | 03/23 |  |  | 15% | Study
Feasibility Study on AR and MR QoE Metrics (FS_ARMRQoE) | FS_ARMRQoE | 960049 | Rel-18 |  | 12/23 |  |  | 5%
Feasibility Study on Audio Aspects for 5G Glasses-type AR/MR Devices (FS_Audio_5GSTAR) | FS_Audio_5GSTAR | 960050 | Rel-18 |  | 12/22 |  |  | 5%
* Currently the Stage 3 Release Freeze has been planned to be shifted from Sep '21 (ASN.1 freeze: Dec.21) to Mar '22 (ASN.1 freeze: Sep.22) [RP-202111]
* In Black are the WIs; In Blue are SIs
Completed SI/WI(s):
Operation Points for 8K VR 360 Video over 5G | 8K_VR_5G | 890009 | Rel-17 |  | Stage 3 | Ozgur Oyman, Thomas Stockhammer |  | completed during SA4#114-e
Study on Multicast Architecture Enhancements for 5G Media Streaming | FS_5GMS_Multicast | 870014 | Rel-17 |  | Stage 2 | Peng Tan |  | Completed during SA4#114-e
Study on Streaming Architecture extensions For Edge processing | FS_EMSA | 870015 | Rel-17 |  | Stage 2 | Imed Bouazizi
Extension for headset interface tests of UE | HInT | 880012 | Rel-17 |  | Stage 3 | Jan Reimes, Stéphane Ragot |  | Test specifications
Support of Immersive Teleconferencing and Telepresence for Remote Terminals | ITT4RT | 820003 | Rel-17 |  | Stage 3 | Igor Curcio, Simon Gunkel
Handsets Featuring Non-Traditional Earpieces | HaNTE | 860012 | Rel-17 |  | Stage 3 | Andre Schevciw |  | Test specifications
8K Television over 5G | 8K_TV_5G | 920011 | Rel-17 |  | Stage 3 | Thomas Stockhammer
5G Multicast-Broadcast User Service Architecture and related 5GMS Extensions | 5MBUSA | 920010 | Rel-17 | Yes, due to inter-WG dependencies | Stage 2 | Peng Tan
Study on VR Streaming Conformance and Guidelines | FS_VR_CoGui | 850004 | Rel-17 |  | Study | Igor Curcio
Study on 5G media streaming extensions | FS_5GMS_EXT | 900029 | Rel-17 |  | Study | Thorsten Lohmar, Iraj Sodagar
Study on 5G Glass-type AR/MR Devices | FS_5GSTAR | 880011 | Rel-17 |  | Study | Hakju Ryan Lee
Study on the use of NBMP in FLUS | FS_FLUS_NBMP | 870012 | Rel-17 |  | Study | Iraj Sodagar
5GMS AF Event Exposure | EVEX | 920008 | Rel-17 |  | Work | Richard BRadbury, Charles Lo |  |  | Stage 2 and Stage 3 | Charles Lo | Reliance also on Rel-17 CT3 spec changes
5G Multicast-Broadcast Protocols | 5MBP3 | 940008 | Rel-17 | Yes, due to stage 2 dependency | Work | Thomas Stockhammer |  |  | Stage 3
Edge Extensions to the 5G Media Streaming Architecture | 5GMS_EDGE | 920009 | Rel-17 |  | Work | Imed Bouazizi |  |  | Stage 2
Study on 5G Video Codec Characteristics | FS_5GVideo | 870011 | Rel-17 | Yes | Study | Thomas Stockhammer
Study on Media Production over 5G NPN | FS_NPN4AVProd | 910001 | Rel-17 |  | Study | Thorsten Lohmar
In the Pipeline: WIs
immersive Real-time Communication for WebRTC | iRTCW
IMS-based AR Conversational Services | IBACS
5G Real-time Transport Protocols | 5G_RTP
In the Pipeline: SIs
Feasibility Study on the enhancements for immersive Real-time Communication for WebRTC | FS_eiRTCW

## SA4#118-e_Status
3GPP SA4 WI/SI Status Update
Name | WI_Code | WI_ID | Release | Is an exception Required ? | Target Completion Date(legends: Orange - Completion due by the immediate SA TSG plenary; Yellow: Completion date due after the current TSG cycle i.e., in approx. 6 months) | Completion %age till SA4#117-e | Completion %age till SA4#118-e | Specify whether Stage2 / Stage 3 | Name of the Rapporteur | Comments
Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 830005 | Rel-18 |  | 2022-12-02 | 30% | 33% | Stage 3 | Stéphane Ragot, Stefan Bruhn | Test specifications
EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 770024 | Rel-18 |  | 2023-12-12 | 30% | 33% | Stage 3 | Imre Varga
5GMS AF Event Exposure | EVEX | 920008 | Rel-17 | Yes | 2022-03-08 | 60% | 75% | Stage 2 and Stage 3 | Charles Lo | Reliance also on Rel-17 CT3 spec changes
Edge Extensions to the 5G Media Streaming Architecture | 5GMS_EDGE | 920009 | Rel-17 |  | 2021-09-08 |  | 95% | Stage 2 | Imed Bouazizi
5G Multicast-Broadcast Protocols | 5MBP3 | 940008 | Rel-17 | Yes, due to stage 2 dependency | 2022-06-23 | 40% | 60% | Stage 3 | Thomas Stockhammer
Immersive Real-time Communication for WebRTC | iRTCW | 950014 | Rel-18 |  |  | NA
Media Capabilities for Augmented Reality | MeCAR | 950015 | Rel-18 |  | 2023-06-12 | NA | 5% | Stage 3 | Emmanuel Thomas | Spec editor: Gilles Teniou
Study on 5G Video Codec Characteristics | FS_5GVideo | 870011 | Rel-17 | Yes | 2022-06-23 | 90% | 95% | Study | Thomas Stockhammer
Study on Typical Traffic Characteristics for XR Services and other Media | FS_XRTraffic | 870013 | Rel-17 |  | 2022-06-23 | 80% | 80% | Study | Thomas Stockhammer
Study on Media Production over 5G NPN | FS_5G_4_AVProd | 910001 | Rel-17 |  | 2022-03-08 | 80% |  | Study | Thorsten Lohmar,
Feasibility Study on 5G Media Service Enablers | FS_5G_MSE | 940010 | Rel-18 |  | 2022-09-23 | 20% | 25% | Study | Thomas Stockhammer
Feasibility Study on Smartly Tethering AR Glasses | FS_SmarTAR | 950013 | Rel-18 |  | 2023-03-10 | NA | 10% | Study
Feasibility Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media | FS_AI4Media | 950011 | Rel-18 |  | 2023-12-12 | NA | 5% | Study | Eric Yip | TR editor: Gilles Teniou
Feasibility Study on the enhancements for immersive Real-time Communication for WebRTC | FS_eiRTCW | 950012 | Rel-18 |  | 2023-06-12 | NA |  | Study
Study
* Currently the Stage 3 Release Freeze has been planned to be shifted from Sep '21 (ASN.1 freeze: Dec.21) to Mar '22 (ASN.1 freeze: Sep.22) [RP-202111]
* In Black are the WIs; In Blue are SIs
Completed SI/WI(s):
Operation Points for 8K VR 360 Video over 5G | 8K_VR_5G | 890009 | Rel-17 |  | Stage 3 | Ozgur Oyman, Thomas Stockhammer | completed during SA4#114-e
Study on Multicast Architecture Enhancements for 5G Media Streaming | FS_5GMS_Multicast | 870014 | Rel-17 |  | Stage 2 | Peng Tan | Completed during SA4#114-e
Study on Streaming Architecture extensions For Edge processing | FS_EMSA | 870015 | Rel-17 |  | Stage 2 | Imed Bouazizi
Extension for headset interface tests of UE | HInT | 880012 | Rel-17 |  | Stage 3 | Jan Reimes, Stéphane Ragot | Test specifications
Support of Immersive Teleconferencing and Telepresence for Remote Terminals | ITT4RT | 820003 | Rel-17 |  | Stage 3 | Igor Curcio, Simon Gunkel
Handsets Featuring Non-Traditional Earpieces | HaNTE | 860012 | Rel-17 |  | Stage 3 | Andre Schevciw | Test specifications
8K Television over 5G | 8K_TV_5G | 920011 | Rel-17 |  | Stage 3 | Thomas Stockhammer
5G Multicast-Broadcast User Service Architecture and related 5GMS Extensions | 5MBUSA | 920010 | Rel-17 | Yes, due to inter-WG dependencies | Stage 2 | Peng Tan
Study on VR Streaming Conformance and Guidelines | FS_VR_CoGui | 850004 | Rel-17 |  | Study | Igor Curcio
Study on 5G media streaming extensions | FS_5GMS_EXT | 900029 | Rel-17 |  | Study | Thorsten Lohmar, Iraj Sodagar
Study on 5G Glass-type AR/MR Devices | FS_5GSTAR | 880011 | Rel-17 |  | Study | Hakju Ryan Lee
Study on the use of NBMP in FLUS | FS_FLUS_NBMP | 870012 | Rel-17 |  | Study | Iraj Sodagar
In the Pipeline: WIs
immersive Real-time Communication for WebRTC | iRTCW
IMS-based AR Conversational Services | IBACS
5G Real-time Transport Protocols | 5G_RTP
In the Pipeline: SIs
Feasibility Study on the enhancements for immersive Real-time Communication for WebRTC | FS_eiRTCW

## SA4#117-e_Status
Name | WI_Code | WI_ID | Release | Is an exception Required ? | Target Completion Date(legends: Orange - Completion due by the immediate SA TSG plenary; Yellow: Completion date due after the current TSG cycle i.e., in approx. 6 months) | Completion %age till SA4#116-e | Completion %age till SA4#117-e | Specify whether Stage2 / Stage 3 | Name of the Rapporteur | Comments
Support of Immersive Teleconferencing and Telepresence for Remote Terminals | ITT4RT | 820003 | Rel-17 |  | 2022-03-08 | 90% | 100% | Stage 3 | Igor Curcio, Simon Gunkel
Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 830005 | Rel-17 |  | 2022-12-02 |  |  | Stage 3 | Stéphane Ragot, Stefan Bruhn | Test specifications
Handsets Featuring Non-Traditional Earpieces | HaNTE | 860012 | Rel-17 |  | 2021-09-08 | 85% | 100% | Stage 3 | Andre Schevciw | Test specifications
EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 770024 | Rel-17 |  | 2022-06-10 | 30% | 30% | Stage 3 | Imre Varga
5GMS AF Event Exposure | EVEX | 920008 | Rel-17 | Yes | 2022-03-08 | 40% | 60% | Stage 2 and Stage 3 | Charles Lo | Reliance also on Rel-17 CT3 spec changes
Edge Extensions to the 5G Media Streaming Architecture | 5GMS_EDGE | 920009 | Rel-17 |  | 2021-09-08 | 80% |  | Stage 2 | Imed Bouazizi
8K Television over 5G | 8K_TV_5G | 920011 | Rel-17 |  | 2022-03-08 | 60% | 100% | Stage 3 | Thomas Stockhammer
5G Multicast-Broadcast User Service Architecture and related 5GMS Extensions | 5MBUSA | 920010 | Rel-17 | Yes, due to inter-WG dependencies | 2021-03-22 | 60% | 100% | Stage 2 | Peng Tan
5G Multicast-Broadcast Protocols | 5MBP3 | 940008 | Rel-17 | Yes, due to stage 2 dependency | 2022-06-23 | 0% | 40% | Stage 3 | Thomas Stockhammer
Study on VR Streaming Conformance and Guidelines | FS_VR_CoGui | 850004 | Rel-17 |  | 2022-03-08 | 90% | 100% | Study | Igor Curcio
Study on 5G Video Codec Characteristics | FS_5GVideo | 870011 | Rel-17 | Yes | 2022-06-23 | 80% | 90% | Study | Thomas Stockhammer
Study on the use of NBMP in FLUS | FS_FLUS_NBMP | 870012 | Rel-17 |  | 2021-09-08 | 100% | 100% | Study | Iraj Sodagar
Study on Typical Traffic Characteristics for XR Services and other Media | FS_XRTraffic | 870013 | Rel-17 |  | 2022-06-23 | 75% | 80% | Study | Thomas Stockhammer
Study on 5G media streaming extensions | FS_5GMS_EXT | 900029 | Rel-17 |  | 2021-09-08 | 60% | 100% | Study | Thorsten Lohmar, Iraj Sodagar
Study on Media Production over 5G NPN | FS_5G_4_AVProd | 910001 | Rel-17 |  | 2022-03-08 | 50% | 80% | Study | Thorsten Lohmar,
Study on 5G Glass-type AR/MR Devices | FS_5GSTAR | 880011 | Rel-17 |  | 2022-03-08 | 90% | 100% | Study | Hakju Ryan Lee
Study on 5G Media Service Enablers | FS_5G_MSE | 940010 | Rel-18 |  | 2022-09-23 | 0% | 20% | Study | Thomas Stockhammer
In the Pipeline: WIs
immersive Real-time Communication for WebRTC | iRTCW
IMS-based AR Conversational Services | IBACS
5G Real-time Transport Protocols | 5G_RTP
In the Pipeline: SIs
Feasibility Study on the enhancements for immersive Real-time Communication for WebRTC | FS_eiRTCW
* Currently the Stage 3 Release Freeze has been planned to be shifted from Sep '21 (ASN.1 freeze: Dec.21) to Mar '22 (ASN.1 freeze: Sep.22) [RP-202111]
* In Black are the WIs; In Blue are SIs
Completed SI/WI(s):
Operation Points for 8K VR 360 Video over 5G | 8K_VR_5G | 890009 | Rel-17 |  | 2021-06-11 | 100% |  | Stage 3 | Ozgur Oyman, Thomas Stockhammer | completed during SA4#114-e
Study on Multicast Architecture Enhancements for 5G Media Streaming | FS_5GMS_Multicast | 870014 | Rel-17 |  | 2021-06-10 | 100 % |  | Stage 2 | Peng Tan | Completed during SA4#114-e
Study on Streaming Architecture extensions For Edge processing | FS_EMSA | 870015 | Rel-17 |  | 2021-06-11 | 100 % (?) |  | Stage 2 | Imed Bouazizi
Extension for headset interface tests of UE | HInT | 880012 | Rel-17 |  | 2021-12-10 | 0.75 | 1 | Stage 3 | Jan Reimes, Stéphane Ragot | Test specifications

## SA4#115-e_Status
3GPP SA4 WI/SI Status Update
Name | WI_Code | WI_ID | Release | Impact on other 3GPP WGs except SA4 | Target Completion Date(legends: Orange - Completion due by the immediate SA TSG plenary; Yellow: Completion date due after the current TSG cycle i.e., in approx. 6 months) | Completion %age till SA4#114-e | Completion %age till SA4#115-e | Specify whether Stage2 / Stage 3 | Name of the Rapporteur | Comments
Extension for headset interface tests of UE | HInT | 880012 | Rel-17 |  | 2021-12-10 | 70% | 75% | Stage 3 | Jan Reimes, Stéphane Ragot | Test specifications
Support of Immersive Teleconferencing and Telepresence for Remote Terminals | ITT4RT | 820003 | Rel-17 |  | 2022-03-11 | 75% | 85% | Stage 3 | Igor Curcio, Simon Gunkel
Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 830005 | Rel-17 |  | 2022-12-02 | 20% |  | Stage 3 | Stéphane Ragot, Stefan Bruhn | Test specifications
Handsets Featuring Non-Traditional Earpieces | HaNTE | 860012 | Rel-17 |  | 2021-09-08 | 70% | 80% | Stage 3 | Andre Schevciw | Test specifications
EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 770024 | Rel-17 |  | 2022-06-10 | 27% | 30% | Stage 3 | Imre Varga
Study on 5G Glass-type AR/MR Devices | FS_5GSTAR | 880011 | Rel-17 |  | 2021-12-10 | 65% | 80% | Stage 3 | Hakju Ryan Lee
5GMS AF Event Exposure | EVEX | 920008 | Rel-17 |  | 2022-03-11 | 0% | 10% |  | Charles Lo
Edge Extensions to the 5G Media Streaming Architecture | 5GMS_EDGE | 920009 | Rel-17 |  | 2021-09-08 | 0% | 30% | Stage 2 | Imed Bouazizi | draft CR agreed at MBS, to be used as baseline.
8K Television over 5G | 8K_TV_5G | 920011 | Rel-17 |  | 2022-03-11 |  | 40% |  | Thomas Stockhammer | draft CRs available for all affected specs
5G Multicast-Broadcast User Service Architecture and related 5GMS Extensions | 5MBUSA | 920010 | Rel-17 |  | 2022-06-10 | 0% | 5% | Stage 2 | Peng Tan | get alignment on TS 26.502 structure
Study on VR Streaming Conformance and Guidelines | FS_VR_CoGui | 850004 | Rel-17 |  | 2021-12-10 | 20% | 20% | Stage 3 | Igor Curcio
Study on 5G Video Codec Characteristics | FS_5GVideo | 870011 | Rel-17 |  | 2021-12-10 | 70% | 75% | Stage 3 | Thomas Stockhammer | good progress, test and anchor results need to be generated
Study on the use of NBMP in FLUS | FS_FLUS_NBMP | 870012 | Rel-17 |  | 2021-09-08 |  | 100% | Stage 3 | Iraj Sodagar
Study on Typical Traffic Characteristics for XR Services and other Media | FS_XRTraffic | 870013 | Rel-17 |  | 2021-12-15 | 65% | 70% | Stage 3 | Thomas Stockhammer | little progress, but need TR documentation
Study on 5G media streaming extensions | FS_5GMS_EXT | 900029 | Rel-17 |  | 2021-09-08 | 40% | 50% | Stage 2 | Thorsten Lohmar, Iraj Sodagar
Study on Media Production over 5G NPN | FS_5G_4_AVProd | 910001 | Rel-17 |  | 2022-03-11 | 30% |  |  | Thorsten Lohmar,
* Currently the Stage 3 Release Freeze has been planned to be shifted from Sep '21 (ASN.1 freeze: Dec.21) to Mar '22 (ASN.1 freeze: Sep.22) [RP-202111]
* In Bold are the WIs
Completed SI/WI(s):
Operation Points for 8K VR 360 Video over 5G | 8K_VR_5G | 890009 | Rel-17 |  | 2021-06-11 | 95% | 100% | Stage 3 | Ozgur Oyman, Thomas Stockhammer | completed during SA4#114-e
Study on Multicast Architecture Enhancements for 5G Media Streaming | FS_5GMS_Multicast | 870014 | Rel-17 |  | 2021-06-10 | 75% | 100 % | Stage 2 | Peng Tan | Completed during SA4#114-e
Study on Streaming Architecture extensions For Edge processing | FS_EMSA | 870015 | Rel-17 |  | 2021-06-11 | 90% | 100 % (?) | Stage 2 | Imed Bouazizi

## SA4#114-e_Status
3GPP SA4 WI/SI Status Update
Name | WI_Code | WI_ID | Release | Impact on other 3GPP WGs except SA4 | Target Completion Date | Completion %age till SA4#113-e | Completion %age till SA4#114-e | Specify whether Stage2 / Stage 3 | Name of the Rapporteur | Comments
Extension for headset interface tests of UE | HInT | 880012 | Rel-17 |  | 2021-09-10 | 60% | 70% | Stage 3 | Jan Reimes, Stéphane Ragot | Test specifications
Support of Immersive Teleconferencing and Telepresence for Remote Terminals | ITT4RT | 820003 | Rel-17 |  | 2022-03-18 | 70% | 75% | Stage 3 | Igor Curcio, Simon Gunkel
Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 830005 | Rel-17 |  | 2022-12-04 | 20% | 20% | Stage 3 | Stéphane Ragot, Stefan Bruhn | Test specifications
Handsets Featuring Non-Traditional Earpieces | HaNTE | 860012 | Rel-17 |  | 2020-09-15 | 55% | 70% | Stage 3 | Andre Schevciw | Test specifications
EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 770024 | Rel-17 |  | 2022-06-11 | 27% |  | Stage 3 | Imre Varga
Operation Points for 8K VR 360 Video over 5G | 8K_VR_5G | 890009 | Rel-17 |  | 2021-06-11 | 95% | 100% | Stage 3 | Ozgur Oyman, Thomas Stockhammer | completed during SA4#114-e
Study on 5G Glass-type AR/MR Devices | FS_5GSTAR | 880011 | Rel-17 |  | 2021-12-17 | 50% | 65% | Stage 3 | Hakju Ryan Lee
Study on Multicast Architecture Enhancements for 5G Media Streaming | FS_5GMS_Multicast | 870014 | Rel-17 |  | 2021-06-10 | 75% | 100% | Stage 2 | Peng Tan | completed during SA4#114
Study on VR Streaming Conformance and Guidelines | FS_VR_CoGui | 850004 | Rel-17 |  | 2021-12-17 | 20% | 20% | Stage 3 | Igor Curcio
Study on 5G Video Codec Characteristics | FS_5GVideo | 870011 | Rel-17 |  | 2021-12-17 | 65% | 70% | Stage 3 | Thomas Stockhammer | excellent progress, but long way to go and also work item extended
Study on the use of NBMP in FLUS | FS_FLUS_NBMP | 870012 | Rel-17 |  | 2021-09-17 | 96% |  | Stage 3 | Iraj Sodagar
Study on Streaming Architecture extensions For Edge processing | FS_EMSA | 870015 | Rel-17 |  | 2021-06-11 | 90% |  | Stage 2 | Imed Bouazizi
Study on Typical Traffic Characteristics for XR Services and other Media | FS_XRTraffic | 870013 | Rel-17 |  | 2021-12-15 | 60% | 65% | Stage 3 | Thomas Stockhammer | little progress, but we will move based on PD
Study on 5G media streaming extensions | FS_5GMS_EXT | 900029 | Rel-17 |  | 2021-09-08 | 30% | 40% | Stage 2 | Thorsten Lohmar, Iraj Sodagar
Study on Media Production over 5G NPN | FS_5G_4_AVProd | 910001 | Rel-17 |  | 2022-03-22 | 5% | 15% |  | Thorsten Lohmar,
* Currently the Stage 3 Release Freeze has been planned to be shifted from Sep '21 (ASN.1 freeze: Dec.21) to Mar '22 (ASN.1 freeze: Sep.22) [RP-202111]
* In Bold are the WIs

## SA4#113-e_Status
3GPP SA4 WI/SI Status Update
Name | WI_Code | WI_ID | Release | Impact on other 3GPP WGs except SA4 | Target Completion Date | Completion %age till SA4#110-e | Completion %age till SA4#111-e | Completion %age till SA4#112-e | Completion %age till SA4#113-e | Specify whether Stage2 / Stage 3 | Name of the Rapporteur | Comments
Extension for headset interface tests of UE | HInT | 880012 | Rel-17 |  | 2021-09-10 | 10% | 25% | 50% | 60% | Stage 3 | Jan Reimes, Stéphane Ragot | Test specifications
Support of Immersive Teleconferencing and Telepresence for Remote Terminals | ITT4RT | 820003 | Rel-17 |  | 2021-06-11 | 50% | 55% | 60% | 70% | Stage 3 | Ozgur Oyman, Igor Curcio
Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 830005 | Rel-17 |  | 2022-12-04 | 15% | 20% | 20% | 20% | Stage 3 | Stéphane Ragot, Stefan Bruhn | Test specifications
Handsets Featuring Non-Traditional Earpieces | HaNTE | 860012 | Rel-17 |  | 2020-09-15 | 35% | 37% | 50% | 55% | Stage 3 | Andre Schevciw | Test specifications
EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 770024 | Rel-17 |  | 2022-06-11 | 27% | 27% | 27% | 27% | Stage 3 | Imre Varga
Operation Points for 8K VR 360 Video over 5G | 8K_VR_5G | 890009 | Rel-17 |  | 2021-06-11 | 0% | 25% | 85% | 95% | Stage 3 | Ozgur Oyman, Thomas Stockhammer
Study on 5G Glass-type AR/MR Devices | FS_5GSTAR | 880011 | Rel-17 |  | 17-Sep-21 | 5% | 10% | 20% | 50% | Stage 3 | Hakju Ryan Lee
Study on Multicast Architecture Enhancements for 5G Media Streaming | FS_5GMS_Multicast | 870014 | Rel-17 |  | 2021-06-10 | 10% | 20% | 60% | 75% | Stage 2 | Peng Tan
Study on VR Streaming Conformance and Guidelines | FS_VR_CoGui | 850004 | Rel-17 |  | 2021-06-21 | 10% | 20% | 20% | 20% | Stage 3 | Igor Curcio
Study on 5G Video Codec Characteristics | FS_5GVideo | 870011 | Rel-17 |  | 2021-09-17 | 30% | 45% | 55% | 65% | Stage 3 | Thomas Stockhammer
Study on the use of NBMP in FLUS | FS_FLUS_NBMP | 870012 | Rel-17 |  | 2021-06-21 | 20% | 30% | 40% | 70% | Stage 3 | Iraj Sodagar
Study on Streaming Architecture extensions For Edge processing | FS_EMSA | 870015 | Rel-17 |  | 2021-06-11 | 25% | 30% | 60% | 90% | Stage 2 | Imed Bouazizi
Study on Typical Traffic Characteristics for XR Services and other Media | FS_XRTraffic | 870013 | Rel-17 |  | 2021-09-17 | 25% | 40% | 55% | 60% | Stage 3 | Thomas Stockhammer
Traffic Models and Quality Evaluation Methods for Media and XR Services in 5G Systems |  |  |  |  | 2021-12-15
Study on 5G media streaming extensions | FS_5GMS_EXT | 900029 | Rel-17 |  | 2021-09-08 | NA | 0% | 5% | 15% |  | Thorsten Lohmar, Iraj Saudagar
Study on Media Production over 5G NPN | FS_5G_4_AVProd | 910001 | Rel-17 |  | 2022-03-22 |  |  | 0% | 5% |  | Thorsten Lohmar,
* Currently the Stage 3 Release Freeze has been planned to be shifted from Sep '21 (ASN.1 freeze: Dec.21) to Mar '22 (ASN.1 freeze: Sep.22) [RP-202111]
* In Bold are the WIs

## SA4#112-e_Status
3GPP SA4 WI/SI Status Update
Name | WI_Code | WI_ID | Release | Impact on other 3GPP WGs except SA4 | Target Completion Date | Completion %age till SA4#110-e | Completion %age till SA4#111-e | Completion %age till SA4#112-e | Specify whether Stage2 / Stage 3 | Name of the Rapporteur | Comments
Extension for headset interface tests of UE | HInT | 880012 | Rel-17 |  | 2021-09-10 | 10% | 25% | 50% | Stage 3 | Jan Reimes, Stéphane Ragot | Test specifications
Support of Immersive Teleconferencing and Telepresence for Remote Terminals | ITT4RT | 820003 | Rel-17 |  | 2020-12-18 | 50% | 55% | 60% | Stage 3 | Ozgur Oyman, Igor Curcio
Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 830005 | Rel-17 |  | 2022-12-04 | 15% | 20% | 20% | Stage 3 | Stéphane Ragot, Stefan Bruhn | Test specifications
Handsets Featuring Non-Traditional Earpieces | HaNTE | 860012 | Rel-17 |  | 2020-09-15 | 35% | 37% | 50% | Stage 3 | Andre Schevciw | Test specifications
EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 770024 | Rel-17 |  | 2021-06-11 | 27% | 27% | 27% | Stage 3 | Imre Varga
Operation Points for 8K VR 360 Video over 5G | 8K_VR_5G | 890009 | Rel-17 |  | 2021-03-12 | 0% | 25% | 85% | Stage 3 | Ozgur Oyman
Study on 5G Glass-type AR/MR Devices | FS_5GSTAR | 880011 | Rel-17 |  | 17-Sep-21 | 5% | 10% | 20% | Stage 3 | Hakju Ryan Lee
Study on Multicast Architecture Enhancements for 5G Media Streaming | FS_5GMS_Multicast | 870014 | Rel-17 |  | 2021-06-10 | 10% | 20% | 60% | Stage 2 | Peng Tan
Study on VR Streaming Conformance and Guidelines | FS_VR_CoGui | 850004 | Rel-17 |  | 2021-06-21 | 10% | 20% | 20% | Stage 3 | Igor Curcio
Study on 5G Video Codec Characteristics | FS_5GVideo | 870011 | Rel-17 |  | 2020-12-17 | 30% | 45% | 55% | Stage 3 | Thomas Stockhammer
Study on the use of NBMP in FLUS | FS_FLUS_NBMP | 870012 | Rel-17 |  | 2021-09-21 | 20% | 30% | 40% | Stage 3 | Iraj Sodagar
Study on Streaming Architecture extensions For Edge processing | FS_EMSA | 870015 | Rel-17 |  | 2021-06-11 | 25% | 30% | 60% | Stage 2 | Imed Bouazizi
Study on Typical Traffic Characteristics for XR Services and other Media | FS_XRTraffic | 870013 | Rel-17 |  | 2020-06-18 | 25% | 40% | 55% | Stage 3 | Thomas Stockhammer
Study on 5G media streaming extensions | FS_5GMS_EXT | 900029 | Rel-17 |  | 2021-09-08 | NA | 0% | 5% |  | Thorsten Lohmar, Iraj Saudagar
* Currently the Stage 3 Release Freeze has been planned to be shifted from Sep '21 (ASN.1 freeze: Dec.21) to Mar '22 (ASN.1 freeze: Sep.22) [RP-202111]
* In Bold are the WIs

## SA4#111-e_Status
3GPP SA4 WI/SI Status Update
Name | WI_Code | WI_ID | Release | Impact on other 3GPP WGs except SA4 | Target Completion Date | Completion %age till SA4#110-e | Completion %age till SA4#111-e | Specify whether Stage2 / Stage 3 | Name of the Rapporteur | Comments
Extension for headset interface tests of UE | HInT | 880012 | Rel-17 | None | 2021-09-10 | 10% | 25% | Stage 3 | Jan Reimes, Stéphane Ragot | Test specifications
Support of Immersive Teleconferencing and Telepresence for Remote Terminals | ITT4RT | 820003 | Rel-17 | None | 2020-12-18 | 50% | 55% | Stage 3 | Ozgur Oyman, Igor Curcio
Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 830005 | Rel-17 |  | 2022-12-04 | 15% | 20% | Stage 3 | Stéphane Ragot, Stefan Bruhn
Handsets Featuring Non-Traditional Earpieces | HaNTE | 860012 | Rel-17 |  | 2020-09-15 | 35% | 37% | Stage 3 | Andre Schevciw | Test specifications
EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 770024 | Rel-18 |  | 2021-06-11 | 27% | 27% | Stage 3 | Imre Varga
Operation Points for 8K VR 360 Video over 5G | 8K_VR_5G | 890009 | Rel-17 | None | 2021-03-12 | 0% | 25% | Stage 3 | Ozgur Oyman
Study on 5G Glass-type AR/MR Devices | FS_5GSTAR | 880011 | Rel-17 | None | 2021-06-11 | 5% | 10% | Stage 3 | Hakju Ryan Lee
Study on Multicast Architecture Enhancements for 5G Media Streaming | FS_5GMS_Multicast | 870014 | Rel-17 |  | 2020-12-17 | 10% | 20% | Stage 2 | Peng Tan
Study on VR Streaming Conformance and Guidelines | FS_VR_CoGui | 850004 | Rel-17 | None | 2021-06-21 | 10% | 20% | Stage 3 | Igor Curcio
Study on 5G Video Codec Characteristics | FS_5GVideo | 870011 | Rel-17 |  | 2020-12-17 | 30% | 45% | Stage 3 | Thomas Stockhammer
Study on the use of NBMP in FLUS | FS_FLUS_NBMP | 870012 | Rel-17 |  | 2021-09-21 | 20% | 30% | Stage 3 | Iraj Sodagar
Study on Streaming Architecture extensions For Edge processing | FS_EMSA | 870015 | Rel-17 |  | 2020-12-17 | 25% | 30% | Stage 2 | Imed Bouazizi
Study on Typical Traffic Characteristics for XR Services and other Media | FS_XRTraffic | 870013 | Rel-17 |  | 2020-06-18 | 25% | 40% | Stage 3 | Thomas Stockhammer
* Currently the Stage 3 Release Freeze has been planned to be shifted from Sep '21 (ASN.1 freeze: Dec.21) to Mar '22 (ASN.1 freeze: Sep.22) [RP-202111]
* In Bold are the WIs