3GPP TSG-SA WG4 Meeting #134	S4-251871

Dallas, US, 17 - 21 November 2025

# Source:	Beijing Xiaomi Mobile Software

# Title:	Draft Work Plan for FS_QStream-MED

# Document for:	Agreement

# Agenda Item:	17.1

# Introduction

This contribution contains a draft work plan for the proposed Study Item on Evaluation of QUIC-based protocols for on-demand and live video services (FS_QStream-MED).

It is a Rel-20 study, expected to be hosted by the MBS SWG.

# 2	Objectives

The objectives of the study are the following:

- Identify the delivery characteristics of segmented media delivery services and applications to be considered in this study, e.g. low latency video streaming, live streaming, on-demand and short-form video platforms.

- Define the evaluation criteria:

A) Determine the set of existing metrics to be collected (e.g. possibly from TS 26.247, TR 26.944, ITU-T P.1203 etc.), that are reflecting QoE, e.g. playback time from live edge, start-up time, etc. and, if needed, their respective QoS metrics.

B) Document potential impact of deploying QUIC-based streaming technologies on the media delivery architecture defined in TS 26.501, taking into account: current CDN architectures, the 3GPP core network architecture defined in TS 23.501; and identify advantages and disadvantages for deployments. For example, caching efficiency, ability to scale, ability to provide a distributed deployment and readiness of general purpose implementations.

- Design a test framework for collecting the selected metrics for evaluating the baseline (DASH over HTTP 1.1) with other technologies, such as QUIC-based streaming technologies based on those identified in TR 26.804, i.e. DASH over HTTP/3, MoQ, MPEG-DASH over WebTransport, MPEG-DASH Part 6 over QUIC.

- Evaluate the selected technologies, by collecting the QoE metrics of objective #2A, using the framework from objective #3, for the use cases identified in objective #1, under 3GPP network conditions, using mobile network traces. Develop the network simulation setup, select the network traces and identify relevant applications (Objective 1), possibly in collaboration with other relevant work items within SA4.

- Based on the collected QoE metrics, identify which streaming services and which relevant video coding tools (such as layered video coding, particularly temporal subsequences) can benefit from a QUIC-based protocol, comparing to DASH over HTTP 1.1 as a baseline.

Note:	Each service and application may have different requirements on those metrics, hence this analysis will be done per service and application.

- Communicate the progress of this study to relevant SDOs such as the IETF MoQ Working Groups, and solicit collaboration with organizations conducting similar work such as SVTA.

# 3	Work plan

The following time plan is proposed for the execution of the FS_QStream-MED study item objectives.

| Meeting | Study Item on Evaluation of QUIC-based protocols for on-demand and live video services |
| --- | --- |
| SA4#134 (17–21 November 2025, Dallas, US) | - Agree study item description - Discuss potential work plan |
| SA#110 (9–12 December 2025, Baltimore, US) | - Approve new study Item |
| Post SA4#134 MBS SWG calls (date/time TBD, submission deadline: TBD) | - Finalize work plan - Work on specification skeleton for TR 26.9xx |
| SA4#135 (9–13 February 2026, Goa, India) | - Agree on work plan. - Agree on specification skeleton - Initiate work on objective 1 (select services and application use cases) - Initiate work on objective 2A (identify QoE metrics) |
| Post SA4#135 MBS SWG calls (date/time TBD, submission deadline: TBD) | - Progress objectives 1 and 2A - Initiate work on objective 2B (study impact on architectures) |
| SA4#135-bis-e (13–17 April 2026) | - Complete work on objective 1 - Progress work on objective 2 - Initiate work on objective 3 (test framework design) - Communicate with other 3GPP WG and external organizations if necessary (objective 6) |
| Post SA4#135-bis-e MBS SWG calls (date/time TBD, submission deadline: TBD) | - Progress objectives 2 and 3 |
| SA4#136 (11–15 May 2026, Montreal, Canada) | - Complete work on objective 2 - Progress work on objective 3 - Initiate work on objective 4 (phase 1: selecting network scenarios and network traces) - Communicate with other 3GPP WG and external organizations if necessary (objective 6) |
| Post SA4#136 MBS SWG calls (date/time TBD, submission deadline: TBD) | - Progress work on objectives 3 and 4 |
| SA4#137-e (24–28 August 2026, online) | - Complete work on objective 3 - Progress work on objective 4 (phase 2: run experiments) |
| Post SA4#137-e MBS SWG calls (date/time TBD, submission deadline: TBD) | - Progress work on objective 4 |
| SA4#138 (16–20 November 2026, Calgary, Canada) | - Complete work on objective 4 - Initiate work on objective 5 (result analysis) - Send TR 26.9xx for information to SA |
| SA#114 (8–11 December 2026, US) | - Presentation of TR 26.9xx to SA |
| Post SA4#138 MBS SWG calls (date/time TBD, submission deadline: TBD) | - Progress work on objectives 4 and 5 - Start working on conclusions and recommendations for future work. |
| SA4#139 (22–26 February 2027, South Korea) | - Complete work on all objectives - Finalize conclusions and recommendations for future work. - Send TR 26.9xx for approval to SA |
| SA#115 (16–19 March 2027, TBD) | - Approval of TR 26.9xx in SA |

# 4	Proposal

It is proposed to agree on the work plan proposed in section 3 and, if needed, further refine after the approval of the SID.