## SA5 OAM work plan for Rel-1 (2)
SA WG5 Meeting #149 |  |  | S5-234440
22-26 May, 2023
|  |  |  | Jan, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24 | Feb, 25? | Apr, 25? | May, 25? | Aug, 25?
|  |  |  | #153 | #154 | #155 | #156 | #157 | #158 | #159 | #160 | #161 | #162
|  |  |  | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan
Rel-15/Rel-16/Rel-17 maintenance
Combined (xx WIDs)
Sum | bar: #153 to #162
Rel-18 maintenance
Combined (xx WIDs)
| Sum |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Rel-18 Alignment (if needed with SA/RAN/CT WGs)
Combined (xx WIDs)
Total (Maintenance) |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Buffer (TEI19, overflow, other)
| Buffer |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
[14 empty] | Sum | Average perc. maintenance + buffer
Total (Maintenance + Buffer) |  |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 60 | 0.33333
Available for Rel-19 SIDs/WIDs |  |  |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 120
| NOTE: ONLY EXAMPLES BELOW |  |  | Jan, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24 | Feb, 25? | Apr, 25? | May, 25? | Aug, 25?
Rel-19 SID/WID Potential topic | Study TU (Planned) | Normative TU (Planned) | Total TU (Planned) | #153 | #154 | #155 | #156 | #157 | #158 | #159 | #160 | #161 | #162 | Study TU (Used) | Study % Compeletion after SA5#153 | Study % Compeletion after SA5#154 | Study % Compeletion after SA5#155 | Work % completion after SA5#156 | Work % completion after SA5#157 | Normative TU (Used) after SA5#157 | Normative TU (Used) after SA5#158 | Normative TU (Used) after SA5#159 | Total TU (Remaining) | Additonal Total TU requested (vs orig plan)
AI/ML management | 6 | 6 | 12
MDA | 3 | 3 | 6
Closed control loop | 3 | 3 | 6
Open source / Zero touch management | 3 | 3 | 6
Autonomous Intelligent Networks | 5 | 5 | 10
Intent driven management service | 3 | 3 | 6
Digital Twin Network management | 3 | 3 | 6
5G Perf. measurements and KPIs | 3 | 3 | 6
Mgmt of 5G Satellite Backhaul/NTN | 1 | 1 | 2
Data management | 3 | 3 | 6
SBMA | 3 | 3 | 6
CICD support for 3GPP NFs | 3 | 3 | 6
Security management | 1 | 1 | 2
Plan/transaction management | 3 | 3 | 6
Management of cloud-based systems | 3 | 3 | 6
Energy Efficiency | 3 | 3 | 6
Deterministic comm. serv. assurance | 3 | 3 | 6
Management aspects of RedCap for 5G | 2 | 2 | 4
Mgmt of Integrated sensing/comm. | 3 | 3 | 6
Exposure of NM services to Verticals | 3 | 3 | 6
Generic Rel-18 LSs
Rel-19 alignment (not in SA5 scope)
TEI19_xxx
TEI19_xxx
TEI19_xxx
Total | 60 | 60 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
NOTE1: Planning is based on max 18 TUs per meeting (including 6 TU for maintenance + buffer, ie 12 available for SID/WIDs)

## SA5 CH work plan for Rel-19
SA WG5 Meeting #149 |  |  | S5-234440
22-26 May, 2023
|  |  |  | Jan, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24 | Feb, 25? | Apr, 25? | May, 25? | Aug, 25?
|  |  |  | #153 | #154 | #155 | #156 | #157 | #158 | #159 | #160 | #161 | #162
|  |  |  | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan
Rel-15/Rel-16/Rel-17 maintenance
Combined (xx WIDs)
Sum | bar: #153 to #162
Rel-18 maintenance
Combined (xx WIDs)
Sum | bar: #153 to #162
Rel-18 Alignment (if needed with SA/RAN/CT WGs)
Combined (xx WIDs)
Total (Maintenance) |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Buffer (TEI19, overflow, other)
| Buffer |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
[14 empty] | Sum | Average perc. maintenance + buffer
Total (Maintenance + Buffer) |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 40 | 0.33333
Available for Rel-19 SIDs/WIDs |  |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80
| NOTE: EXAMPLES BELOW |  |  | Jan, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24 | Feb, 25? | Apr, 25? | May, 25? | Aug, 25?
Rel-19 SID/WID Potential topic | Study TU (Planned) | Normative TU (Planned) | Total TU (Planned) | #153 | #154 | #155 | #156 | #157 | #158 | #159 | #160 | #161 | #162 | Study TU (Used) | Study % Compeletion after SA5#153 | Study % Compeletion after SA5#154 | Study % Compeletion after SA5#155 | Work % completion after SA5#156 | Work % completion after SA5#157 | Normative TU (Used) after SA5#157 | Normative TU (Used) after SA5#158 | Normative TU (Used) after SA5#159 | Total TU (Remaining) | Additonal Total TU requested (vs orig plan)
tbd | 0 | 0 | 0
Generic Rel-18 LSs
Rel-19 alignment (not in SA5 scope)
TEI19_xxx
TEI19_xxx
TEI19_xxx
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
NOTE1: Planning is based on max 12 TUs per meeting (including 2 TU for maintenance + 2 TU buffer, i.e. 8 available for SID/WIDs)